ANNUAL REPORT

ON THE IMPLEMENTATION OF THE ASSISTANCE UNDER IPA

Prepared by

The National IPA Coordinator office in coordination with NAO, Management structure, CFCD and contribution from IPA coordinators from the Ministry of Justice, Ministry of Interior, Ministry of Transport and Communication, Ministry of Environment and Physical Planning, Ministry of Local Self Government, Cabinet of the Deputy Prime Minister for Economic Affairs, Ministry of Agriculture, Forestry and Water Economy, Ministry of Education and Science, Ministry of Labour and Social Policy, Ministry of Information Society and Administration and Ministry of Finance

Date

March 2021

Table of Contents

I       Executive Summary	3

II       Information per Sector	24

Rule of Law and Fundamental Rights – Sub sector Justice and Home Affairs	24

Rule of the Law, Sub sector Justice	24

Rule of Law and Fundamental Rights – Sub sector Home Affairs	39

II a. Performance indicators in the sector Rule of law and Fundamental Rights covering both direct and indirect management	43

Democracy and Governance, Sub sectors PAR, PFM, and Union Programmes and EUIF	65

Democracy and Governance, Sub sector PAR	65

Democracy and Governance, Sub sector PFM	67

II a. Performance indicators in the PAR sector covering both direct and indirect management	72

Democracy and Governance, Union Programmes	79

II a. Performance indicators in the sector Democracy and Governance – Support to the participation in the Union Programmes	88

Democracy and Governance, EUIF	89

EUIF Summary table	90

II a. Performance indicators in the sector Democracy and Governance – EUIF	94

Environment and Climate Action	97

II a. Performance indicators in the Environment and Climate Action sector covering both direct and indirect management.	107

Transport	110

II a. Performance indicators in the Transport sector covering both direct and indirect management	117

Agriculture and rural development	119

II a. Performance indicators in the Agricultural and Rural Development sector covering both direct and indirect management.	127

Competitiveness and Innovation	131

II a. Performance indicators in the Competitiveness and Innovation sector covering both direct and indirect management	135

Education, Employment and Social Policy	141

II a. Performance indicators in the Education, Employment and Social Policy sector covering both direct and indirect management	150

Cross-Border Cooperation	159

II a. Performance indicators in Cross Border Cooperation Programmes	171

Annual Report on the implementation of IPA II assistance under direct and indirect management by the Republic of North Macedonia submitted by the National IPA Coordinator

# I       Executive Summary

- Reference to the objectives of the Indicative Strategy Paper and a brief overview of the challenges in the sectors

To meet the priorities set for the EU financial assistance for the 2014-2020 period, the Indicative Strategy Paper (ISP) selects meaningful and realistic objectives, identifies key actions and actors, describes expected results, indicates how they will be measured and monitoring, and, finally, establishes the indicative financial allocations. This Annual Report is very relevant to assess the status of the implementation of the ISP. All the programming documents are either already under implementation or with already drafted Action Documents submitted for quality control. This means that in this report, it is possible to draw a first assessment of the IPA support input to implement the ISP. Although the ISP establishes six sectors, the country, in accordance with the European Union Delegation (EUD), set up eleven sectors.

The sectors’ main challenges were carefully identified during the elaboration of the Strategic Responses for IPA III 2021-2027. They are as follows:

- Public Administration Reform (PAR)

Public Administration Reform Strategy 2018–2022, in line with SIGMA principles, identifies four core areas to be improved in the implementation period: (i) Policy creation and coordination; (ii) Public Service and HRM; (iii) Responsibility, accountability, and transparency; and (iv) Service delivery.  Consequently, the main challenges in this sector can be grouped into the following topics: to improve the professionalism, transparency, accountability and independence of the public administration at central and municipal level; to strengthen the effectiveness of the organization of the public administration; to improve the quality of the services to citizens and businesses and equal and free access to public information with a particular focus on the development of e-services and e-procurement, and to increase the training to central and local government administrations and raise public awareness to ensure implementation of the Law on General Administrative Procedures.

Action Plan of the Public Administration Reform Strategy was revised in 2020 as foreseen in the Strategy. The second annual report on implementing the Action Plan covering the period January 2019–December 2019 was prepared and adopted by the PAR Council and the Government. According to the same, 97% of the activities were implemented within the foreseen timeframe. Simultaneously, the EC Progress report states that MISA improved its capacities to drive the reform on a technical level. While the challenges related to decentralisation include strengthening all the competences transferred and yet to-be-decentralised to ensure the full implementation of all relevant laws and strategies throughout the country, comprehensive reform at the central level penetrates every part of the public administration, reshaping the institutional and structural organisation, methods for service delivery, as well as recruitment, promotion, and selection processes.

- Public Financial Management (PFM)

In the field of the PFM, the implementation of the PFM Reform Programme 2018-2021, adopted in December 2017, represents a challenge from the point of view of resources mobilisation and the necessary additional financial support needed, taking into consideration the areas covered by the Strategy (revenue collection, budget preparation and execution, public procurement, assets, cash and debt management, granting of concessions and state aid, public internal financial control and external audit). In addition, the preparation of the mid-term budgetary framework and improved budget classification needs to be enhanced. The key challenge is to increase the transparency of the PFM and ensure public information on the full budget cycle, as well as the modernisation of the IT tools and the optimisation of the business processes, along with achieving interconnectivity and interoperability of the customs and tax IT systems with the EU systems. Greater political commitment and operational improvements are needed to facilitate inter-institutional cooperation, implement established procedures, and ensure timely implementation of the programmes.

Till present, the Annual Action Programme for Democracy and Governance 2017 and 2018 are addressing the following overall objectives: - to contribute to a more effective EU integration process (2017); - to reform public administration in line with the Principles of Public Administration (2017); and - to improve governance and ensure fiscal sustainability and sound use and management of the public funds (2018).

Ministry of Finance and other national institutions have been implementing very ambitious PFM reform agenda elaborated in the PFM Reform Programme 2018-2021. To carry out the programme, the EU has allocated 18,6 million EUR from IPA 2018, to be implemented through several projects which are directly linked to the implementation of certain measures from the Programme (budget planning and execution, internal control, public procurement, tax and customs policy and system and revenue collection).

MoF have already prepared strategies and reform laws that will enable all this to take effect:

- The new Law on Budgets is fundamental, setting fiscal rules and establishing a Fiscal Council for greater control, medium-term budgeting and establishing an integrated public financial management system to better plan and create a register of public entities and increase transparency. Organic Budget Law (OBL) was reviewed and adopted by the Government at the beginning of January 2021 and subsequently has entered the Parliamentary procedure.

- The Government adopted Revised Fiscal Strategy for 2021-2023 with an outlook up to 2025 in December 2020.

- Public Debt Management Strategy for 2021-2023 with an outlook up to 2025 (adopted by the Government in December 2020), which defines limits for the three levels of debt (state, guaranteed and the total public debt in the next five years) as well as for the debt structure, in the direction of prudent management of the same.

- The Government adopted New PIC Law in December 2020 and now is in the parliamentary procedure for adoption. The new Laws expected to further strengthen the grounds for implementing Public Internal Financial Control (PIFC) across the entire public sector.

- Implementing the Strategy for Tax System Reform 2021-2025 (adopted by the Government in December 2020) should ensure greater fairness in taxation, better revenue collection, and a tax system that will encourage investment and innovation and thus economic growth, greater tax responsibility, higher tax transparency, higher quality of services, digitalization, and green taxation.

- Ministry of Finance remains fully committed to improving fiscal transparency. As of February 2020, North Macedonia’s citizens have had the opportunity to be informed about the public debt through the new transparency tool javendolg.open.finance.gov.mk, prepared by the Ministry of Finance with support by IRI and USAID. Debt, its trends by years, repayment, disbursements for 2020 and its financing manner are thoroughly presented thereon.

- In June 2020, the Open Finance portal data set was broadened with data for transactions of municipalities in the same format as data for budget institutions within the Central Budget.

- The financial indicators from the financial operations of the public enterprises and trade companies at the central level, as part of the budget documentation, are presented for the first time within the Fiscal Strategy of Republic of North Macedonia 2020-2022. The new Fiscal Strategy of Republic of North Macedonia 2021-2023, in addition to data on total revenues and expenditures on annual basis, is improved with data on realization in the first quarter of 2020, as well as data on the amount of capital investments expressed through investment programmes of public enterprises and companies at the central level.

- As of October 2020, the Ministry of Finance, as a regular practice, has started with publishing data on revenues and expenditures of the public companies and state-owned companies at the enterprise level and data on the execution of the local government budget (fiscal table for local government), quarterly.

- Additionally, Ministry of Finance published a new web page.

- Implementation of IFMIS is the top-priority project for the Ministry of Finance within the PFM Agenda. IFMIS is regulated in the Organic Budget Law (OBL) which sets the legal base for its implementation. The OBL enforcement and IFMIS are expected to significantly improve the good governance and performance of the main functions of the Ministry of Finance (budget planning and execution, public debt management, monitoring public investments, data analytics and business intelligence).This project is expected to be supported by WB loan blended with the EU’s IPA 2018 grant funds. MoF has started the procedure for amending the IPA 2018 Financing Agreement (FA) to reallocate IPA funds to IFMIS to be implemented under indirect management with international organization-World Bank.

- Justice (JUST)

This sector must address the challenges identified in the Strategy for Judicial Reform 2017-2022 and Action Plan, adopted in the “Urgent Reform Priorities” frame. The Strategy’s main priorities are related to independence and impartiality, quality, liability, efficiency, transparency, access to justice, functioning of the administrative justice and misdemeanours. However, there are some more urgent challenges in the sector, such as, for instance: restoring the independence of judges and that the Judicial Council and the Council of Public Prosecutors exercise their function of protecting judges and prosecutors; ensure appointments and promotion on merit-based and performance management system based on qualitative and qualitative standards; and regularly use and audit the Automated Court Case Management Information System (ACCMIS). During the elaboration of the Strategic Response, within the frame of IPA III, the following priorities were identified: - to strengthen the independence, impartiality, and transparency of the judicial system; and – to improve the quality, effectiveness and efficiency of the judicial system and the judicial services to the citizens.

Concerning human rights, the general challenge is to increase the promotion and protection of disadvantaged groups. Another critical challenge is the improvement of conditions of prisons and other places of detention (this challenge is currently addressed through a loan of the Council of European Bank (CEB) to improve the quality of the detention places). As concern the freedom of expression, the main challenge is to strengthen the broadcasting reform and its independence, and the professional behaviour of all media stakeholders. As concern the Strategic Response for IPA III, two key priorities are identified: - to establish a robust national framework for fundamental rights; and – to fight discrimination and ensure the protection of children, and women, people with disabilities and minorities.

In the fight against corruption, the institutional cooperation and capacities of the following bodies should be strengthened and improved: The Public Prosecutor’s Office against organised crime and corruption, the Ministry of Interior, the Public Prosecution Offices, the State Commission for the Prevention of Corruption, the Agency for the management of Confiscated Assets and the State Audit Office. In this sense, the Strategic Response for IPA III determines two main priorities: - to strengthen the institutional system and the legal framework to prevent corruption; and – to strengthen the institutional system dealing with repression of corruption.

- Home Affairs (HA)

In the Home Affairs sector, there is a need to continue improving the country’s external borders’ effective management and ensure the implementation of visa, migration, and asylum policies, in line with the EU acquis. The Ministry of Interior needs to continue to reform the police and enhance the effectiveness and transparency of special investigative measures and more pro-active investigation of organised crime, including financial investigations. More specifically, the challenges under organised crime are related to improving the track record on investigation, prosecution, and conviction of cases of organised crime and money laundering; the strengthening of cooperation between the various law enforcement agencies through the National Coordination Centre for the Fight against Organised Crime; and the fight against trafficking in human beings and the smuggling of migrants. From an operational point of view, it is relevant to note that there are several essential strategies in the sector. However, they are not implemented with adequate commitment.

During 2020, the Home Affairs sector actively participated in the IPA III programming process and prepared the Strategic Responses for the two thematic areas.

- Environment and climate change (ENV)

Once the National Strategy on Environment and Climate Change was adopted in January 2018, the main challenges within this sector are the following: to improve the implementation and enforcement of water, nature protection and waste legislation in line with the acquis; to enhance coordination between the government, central level institutions and municipalities to actively work towards improving air quality; to intensify efforts to implement the adopted regional waste management plans and establish an integrated regional waste management system; and to initiate the implementation of the Paris Agreement also through the development of a comprehensive strategy on climate-related action consistent with the EU 2030 framework.

- Transport (TR)

Within the framework of the National Transport Strategy 2018-2030, adopted in December 2018.  the 1st Annual Report on the implementation of the National Transport Strategy 2018-2030 has been prepared for the implementation period until 2019. The data collection for the previous period was done in January until March 2020, by a written procedure requesting information from the relevant institutions. This first report was adopted on 17th November 2020 by the Government of the Republic of North Macedonia. The challenges facing this sector are mainly related to the strengthening of administrative capacity and operational capacity for all modes of transports, inspection bodies and develop enforcement capacity to reduce fatalities along road and rail infrastructure. Other relevant challenges refer to the implementation of connectivity reform measures in rail reform and the opening of rail transport for domestic and regional undertakings, as well as on setting-up a national system for collecting data on road crashes; to adopt legislation on intelligent transport systems (ITS) and combined transport; and to produce a strategic framework for implementing ITS and the core networks. The ITS will provide variety of traffic data and the number and type of vehicles that move along corridor X, as well as meteorological data along the route throughout the year which can be used for statistical and analytical purposes. The introduction of an ITS is closely linked to approximation with the directives from the EU transport acquis.  The approximation of this legislation will be carried out in parallel with the following two activities: 1. Provision, Installation and Commissioning of Equipment for ITS Implementation; and 2. Preparation of National ITS strategy. The timeline for start of this activity is Quarter 1 of 2021.

One of the key objectives in the transport sector in the coming period is to reduce the GHG emissions from the transport which is in line with the European Green Deal. With support, financing and implementation of concrete measures as set in the NTS 2018-2030, contribution could be made to reducing pollution in the country and re-thinking growth that is mindful of the environmental limits.

The transport sector strategic documents and cross-sectoral planning documents are in line with the objectives of 2030 Agenda for Sustainable Development, thematic priority No 9: Industry, innovation and infrastructure and thus aims to improve connectivity, reduce transport emissions and support efficient transportation services as a key driver of economic development. The National State statistical office is producing and integrating a set of indicators that provide statistical support for monitoring the degree of implementation of the concept of sustainable development in the country.

Planned areas of intervention and key-priorities for the period 2021- 2027, in line with the NTS 2018-2030:

- Construction of new and reconstruction, rehabilitation, and modernization of existing railway links along the Core and Comprehensive network according to the EU technical standards to provide quality and safe TEN-T connections with the neighbouring EU members and the wider region in the Western Balkans.

- Construction of new and reconstruction, rehabilitation, upgrading and modernization of the road network on the Core and comprehensive network according to the EU technical standards to provide quality and safe TEN-T connections with the neighbouring EU members and the wider region in the Western Balkans.

- Support multimodality and sustainable transport systems, with stronger integration of various transport modes.

- Improvement of the road and rail safety, through intervention in infrastructure and soft measures implementation, including but not limited to preparation of strategic documents, capacity building of the relevant stakeholders, improvement of the administrative capacities, communication activities and campaigns, surveys, and analysis etc.

- Promoting modal shift through advancement of transport services with quality and innovations as well as improvement of availability, affordability, and accessibility of the transport services, to the vulnerable groups.

- Further reducing the transport impact on the environment through introducing and supporting green transport modes and increasing transport and infrastructure efficiency with using smart and IT tools.

- Advancement of sector planning and development through preparation of sector and project documentation (planning documents, project preparation studies such as feasibility studies, cost-benefit analyses, environment impact assessments, design documentation, tender documentation).

- Further elevation and advancement of the transport sector integration to the EU transport area with approximation of the legal framework with the EU acquis and EN standards and increasing transport stakeholder capacity to assume the obligations of an EU membership.

- Competitiveness and Innovation (C&I)

Improving socio-economic development through fostering economic growth and job creation is the priority objective of this sector. The focus is on creating a competitive and export-oriented economy based on knowledge an innovation at the local, national, and international level. In this context, the main challenges in the sector are the following: to enhance harmonisation with the EU acquis and strong implementation record in the area of the internal market, particularly the free movement of goods (including quality infrastructure, market surveillance and consumer protection, and customs controls), free movement of services and competition and state aid; to improve the legal and institutional framework for business creation and operations; to improve access to finance, especially for women, and business services, as well as the business-related infrastructure, including at local level; and to enhance research and innovation capabilities through cooperation between universities, industry and Government, including the participation in the UE’s Horizon 2020 programme and the development of a Smart Specialisation Strategy.

During 2019 and 2020, a 2019 Action Document for Competitiveness and Innovation sector was elaborated, submitted, and approved whose specific objectives are to improve compliance of the local economy with the EU acquis in free movement of good, service, consumer protection, market surveillance and company law, and to support start-ups and SMEs in selected under-developed regions to grow, produce added value and create local living.

In 2020, Budget Support “EU for Social and Economic Resilience in North Macedonia” was negotiated in the frame of the 2020 Annual Action Programme. This Action will support North Macedonia in mitigating the negative socio-economic impact of COVID-19 by providing support for governmental measures focused on improving the resilience of the micro and small enterprises and on supporting the reintegration of unemployed women and men into the labour market.

- Agriculture and Rural Development (ARD)

To ensure sustainable development of the agri-food sectors and rural areas in line with the EU acquis and policies and ensuring food safety is the main objective in the sector. In this sense, the main challenges of the sector are related to the strengthening of administrative capacity, including improvement of IT systems, at all levels of the administration and public bodies to implement agricultural reforms and policies and to ensure efficient absorption of IPA and IPARD funds; to improve the competitiveness of the agriculture sector; to improve the safety of human beings and animal health; to improve the alignment process of the Farm Accountancy Data Network; and to intensify the alignment of policies in the area of common market organization.

During 2020, among consultation with the Sector Working Group on Agriculture and Rural Development and other relevant national authorities, donors, and civil society, MAFWE prepared a technical draft of IPA III Strategic Response.

In the same relation, MAFWE drafted an Action Document, which will contribute to improve sustainable competitiveness of North Macedonian economy and to the achievement of the specific objectives of IPA III Window 4 Thematic Priority 2: Private sector development, trade, research, and innovation; and Thematic priority 3: Agriculture and rural development. This Action will improve the North Macedonia economy’s sustainable competitiveness to achieve a greened, recovered, and modernized economy. Regarding ARD, the Action will focus on the preparation of the country for participation in the EU Common Agricultural Policy, harmonize agriculture with the European standards and increase the competitiveness of the agricultural production.

- Education, employment, and social policies (EESP)

Once the Comprehensive Education Strategy 2018-2025 and action plan was adopted in February 2018, the main challenges concerning the education area have to done with different aspects: the implementation of the new education strategy; the support for teacher training, teacher professional development and an effective process of assessment; and the improvement of access to quality education for all, in particular pre-school enrolment, children with disabilities and children from Roma communities. Another relevant challenge to match demand and supply on the labour market is strengthening the Vocational Education and Training (VET) and the Adult Education System in close cooperation with the private sector and social partners.

As regards the area of employment and social policies, the challenges facing the country are related to the labour market inclusion of youth, long-term and unskilled, including women; the alignment of the newly adopted Anti-Discrimination Law with the EU acquis and its implementation mechanisms; the capacity of the Labour Inspectorate and the institutional and financial resources to address poverty and implement the social inclusion policies including the Roma action plans and the new Deinstitutionalisation Strategy and Action Plan 2018-2027.

The outbreak of COVID-19 affected the sector adversely, reverted some of the positive developments in the labour market and confirmed the relevance of all listed challenges. The economic impacts of COVID-19 are expected to create further vulnerability and push more people into poverty.

2019 Action Document and a Sector Reform Contract for this sector were elaborated/negotiated in 2018-2019 with the Financing Agreements being signed in March 2020. Specific objectives are, respectively, to improve social, education, and education of people belonging to the most vulnerable groups and to improve quality, relevance and inclusiveness of the national vocational education and training system and improve employment opportunities for young women and men.

- Local and Regional Development (LRD)

The main challenges of this new sector, established in 2019, have to do with the objectives and goals within the Programme for Sustainable Local and Decentralization and Action Plan 2015-2020, which are in line with the problems recognised in the ISP and Country progress reports, namely: 1) good governance and development of an institutional framework for integrated local growth and development, 2) encouraging knowledge-based growth through strengthening local competitiveness and innovation, 3) fostering inclusive growth by providing equal access to local services for all citizens and 4) promoting sustainable growth through local development based on social welfare and responsible use of natural resources.

The methodology for preparing the new Decentralisation Programme for 2021–2026 has been designed and relayed in the reporting period. The new Programme for Sustainable Local Development and Decentralization has been prepared and is in Governmental procedure. The priorities of the new Programme are focused on strengthening the capacities of municipalities for existing competences and the transfer of new ones; better management of public finances, e-services, appropriate response to crises; local development through greater accountability and transparency; and the development of credible capacities and relevant frameworks for integrated and inclusive local development - programming, planning, and projects preparation.

In addition to the above, the assessment of the implementation of the Law on Local Self-Government and the assessment of the implementation of the Law on the City of Skopje were completed.

The Municipal Development Index (MDI) was formulated and initially measured in some municipalities.

Following the SWG held in September 2019, an Action Document 2020 “EU for municipalities” was elaborated, which overall objective is to increase the effectiveness and efficiency of local governance, while the specific objective is to pilot smart solutions for addressing community challenges in partnership with local authorities of EU Member States.  This Action Document is implemented by the EU Delegation in Skopje and is focused on innovation and sustainability in most sectors of competence of the LSG, except basic infrastructure:

- Innovative municipal services

- Local jobs and skills in knowledge economy

- Social care and community social service

- Sustainable growth and circular economy/ public utilities

The total budget amount is around 6 million euros, and the Ministry of Local Self-Government will provide the national co-financing.

In the area of regional development, the evaluation of the Strategy for the Regional Development 2009-2019 and the Regional Development Programmes has been done in the reporting period. Also, the new Law on Balanced Regional Development has been prepared and is enacted by the Parliament on 27 of January 2021.

The Strategy for Regional Development 2021-2031 has been prepared and is in parliamentary procedure. This main strategic document in regional development was developed through a comprehensive consultative process that includes 12 sectoral studies that were presented and discussed on the six thematic workshops organized by the Ministry for Local Self-Government. Besides this, a system for improving inter-ministerial coordination for balanced regional development, SIRERA, has been established.

The annual funds for balanced regional development were also increased each year and in 2020 have exceeded 7 million euros.

- Roma Integration (RI)

As concern the challenges of the Roma Integration sector, which was established in 2019, the main ones are related to creating conditions for increased integration in the labour market; providing comprehensive social protection systems that offer minimal funds that provide a decent life; developing programmes for continuing the education and overcoming the premature abandonment of the education system; improving the quality and access to public services, especially health, social services, housing and transportation; overcoming the high level of social exclusion and discrimination; and strengthening of the policies for supporting family, social networks and the protection of children’s rights.

- Status of the implementation of the Sector Approach and Roadmap

A horizontal challenge for all sectors is the implementation of their roadmaps and the achievement of a complete Sector Approach. All sectors are making progress in achieving the targets established by their roadmaps; however, not all of them are progressing at the same pace. In particular, the Home Affairs and Environment sectors are lagging, while all the other have considerable achievements. The criteria “Budget” needs to be improved in all sectors since, at present, all the strategies are being implementing based on national annual budgets. Progress is expected with the adoption of the new organic budget.

During 2020, most of the meetings of the SWGs related to the accomplishment of the Sector Approach criteria were organised for the Performance Assessment Framework (PAF).  The set of indicators have been agreed at the SWG level for the sectors active under IPA II. More than 200 indicators are agreed upon. The next step includes that the Government of the Republic of North Macedonia finally decides on the set of indicators and that the PAF is fully operational. The Information note for the Government is being drafted by the Secretariat for European Affairs (SEA).

- Involvement in programming

In March 2020, IPA II Annual Programme for 2020 was approved and signed by the EC. IPA II Annual Programme for 2020 is in a total amount of 45.950.000 euro and includes the following actions:

Action 1: EU for municipalities.

Action 2: Support for participation in Union Programmes.

Action 3: EU for Rule of Law.

Action 4: EU on improved border management and migration.

In September 2020, the first amendment of the IPA II Annual Programme for 2020 was approved and signed by the EC with a total amount of 50 million EUR as a performance award for the reform agenda of the country in the past three years.  Under this amendment two actions have been programmed:

- Mechanism to support the European integration process; and

- Sector budget support for social and economic recovery from the Covid 19 consequences

IPA II Annual Program for 2019 is in total amount of 58.600.000 euro and includes the following actions:

Action 1: EU support for Competitive and Fair Markets

Action 2: EU support for Rural Development and competitive and sustainable agriculture

Action 3: EU for Youth -Technical Assistance

Action 4: EU for Inclusion SBS

At sectoral level, for the IPA AR 2020, four Programming periods are still relevant: 2017, 2018, 2019 and 2020. Under IPA 2017 Annual Action Programme, four Action Documents were elaborated and adopted. In 2018, the Financing agreement for the Annual Action programme was signed on 5th November 2018 in total amount of EUR 44.643.780:

- Employment and social policy - 23.700.000 EUR.

- Public administration reform – 11.200.000 EUR.

- Participation in the Union Programmes – 7.293.780 EUR.

- European Union Integration Facility - 2.450.000 EUR.

For the preparation of these programming documents more than 20 meetings of the SWGs, including International Organisations, donors, Embassies and CSOs were organised in 2020 on bilateral and technical level. Next to the sectoral programming, it is necessary to mention the programming of the European Union Integration Facility (EUIF), the preparation of the Operational Identification Sheets (OIS) under the sectors Transport and Environment and Climate Action, as well as the IPA applications for the major infrastructural projects (wastewater treatment plant in Bitola and Tetovo). The Union Programmes (UPs) was carried out with the same modalities of the previous years.

In December 2019, the IPA 2019 Annual Action Programme was approved and signed by the EC in total amount of 58.600.000 EUR:

- EU supports Rural Development and Competitive Sustainable Agriculture 20.500.000 EUR

- EU supports Competitive and Fair Markets 14.250.000 EUR

- EU for inclusion 7.350.000 EUR

- EU for Youth Sector Reform Performance Contract 16.500.000 EUR

- Involvement in Multi-country actions and any related issues

NIPAC Office is the authority responsible for communicating and consulting the proposed actions in each programming year. The NIPAC Office participates in the IPA Multi-country programmes forum organised on regular biannual basis by DG NEARBY. Due to the Covid-19 pandemics and the introduced travelling restrictions, in 2020 only one forum was organised, and it was held, virtually on 14-15 December 2020. The forum was used for discussion regarding the one-pager outlines proposed within MC IPA programme 2021-2022, as well as for presentation and discussion on the Programming Framework for the new IPA III instrument. Following the conducted consultation process on the MC IPA 2021-2022 one-pager outlines, EC is currently developing the relevant Action Documents.

The EC has proposed the following actions within the MC IPA programme 2021-2022:

Multi- country Programme 2021-2022

MCP 2021-2022

Window 1 – Rule of law, fundamental rights, and democracy

Regional Security in the Western Balkans - Support to Border Security

Civil Society Facility (CSF) and Media programme 2021-2023 multi-annual facility

Protection sensitive migration governance in the Western Balkans

Regional Security in the Western Balkans - Support to Border Security

Supporting evidence-based policy- making on justice system performance and anticorruption in the Western Balkans and Turkey

Regional Roma Action in Western Balkans and Turkey

Regional Security in the Western Balkans - Support to the fight against Terrorism and Countering and Preventing Violent Extremism

Window 2 – Good governance, acquis alignment, good neighbourly relations, and strategic communication

EU support to confidence-building in the Western Balkans

EU4Youth: Erasmus+ international activities supported through IPA III

EU Integration Facility, including EU support for the participation of IPA III beneficiaries in EU agencies

Governance of public finances and economic reforms

Sub-national Governance Facility for Western Balkans and Turkey - PILOT PHASE

Support to the Regional School of Public Administration (RESPA)

EU support to Statistics in the Western Balkans and Turkey

Strategic Communication about the European Union

Logistic support to Technical Assistance and Information Exchange (TAIEX)

EU Scheme for Young Professionals in the Western Balkans

Window 3 – Green agenda and sustainable connectivity

Civil Protection Support – Prevention, Preparedness and Response to Natural Disasters in the Western Balkans and Turkey

EU4 Connectivity: through the EU contribution to the Energy Community budget

EU4 Connectivity, Green and Digital Transition through the Western Balkans Investment Framework (WBIF)

Western Balkans Regional Energy Efficiency Programme (REEP) And Green For Growth Fund (GGF)

EU4 Connectivity: Support to the preparation of infrastructure investment projects

EU4 Connectivity: through the EU contribution to the Transport Community Permanent Secretariat budget

The Western Balkans Guarantee Facility

Window 4: Competitiveness and inclusive growth

Capacity building of veterinary and plant health services in the Western Balkans

Support to the Implementation of the Common Regional Market (CRM)

Support to Competitiveness and Sustainability in the Western Balkans and Turkey

Support for private sector under the Western Balkans Enterprise Development and Innovation Facility (WB EDIF)

Participation of the Western Balkans in international tests

Strengthening social protection, health and employment systems and policies in the Western Balkans with SOCIEUX +

Competitive and Sustainable Regional Tourism in the Western Balkans

Window 5 - Territorial and cross border cooperation

Regional technical assistance for cross-border cooperation among IPA Beneficiaries

The NIPAC Office submitted the comments on the proposed one-page outlines following the consultations with the relevant national authorities within the deadline given by the EC, i.e., 22 January 2021.

Within 2020, the following decisions have been adopted with regards the Multi Country envelope:

- On 24 June 2020, the European Commission adopted a Special Measure on EU regional support to COVID-19 SME recovery in the Western Balkans in 2020 (Commission Implementing Decision C (2020) 4287).

- On 25 June 2020, the European Commission adopted the Multi-country Action Programme for the year 2020 – part 1 (Commission Implementing Decision C (2020) 4356).

- On 28 July 2020, the European Commission adopted the Multi-country Action Programme for the year 2020 – part 2 (Commission Implementing Decision C (2020) 5209).

- On 29 October 2020, the European Commission adopted the Multi-country Action Programme for Connectivity for the year 2020 (Commission Implementing Decision C (2020) 7433).

Within 2020, the following adoptions of amendments with regards the Multi Country envelope have been concluded:

- On 26 June 2020, the European Commission adopted the amendments to the Commission Implementing Decision C(2019) 8410 of 19.11.2019 adopting a Multi-country Action Programme for Western Balkans Guarantee for the years 2019- 2020 (Commission Implementing Decision C(2020) 4295).

- On 22 September 2020, the European Commission adopted the amendments to the Commission Implementing Decision C(2018) 8516 of 5.12.2018 adopting a Civil Society Facility and Media Action Programme for the years 2018-2019 (Commission Implementing Decision C(2020) 6599).

- On 28 December 2020, the European Commission adopted the amendments on the Commission Implementing Decision C (2019) 8410 of 19.11.2019 adopting a Multi-country Action Programme for Western Balkans Guarantee for the years 2019- 2020 (Commission Implementing Decision C (2020) 9654).

On the implementation side, the NIPAC Office appreciates the regular biannual reports for the implementation of the respective programmes, since these reports are the only sources for information on the implementation.

However, to improve the follow-up of the Actions financed through regional support of MC IPA, NIPAC Office suggests improving the coordination of line ministries through NIPAC, having into account that all IPA-related Programmes are administered through NIPAC. The direct communication of the EC with the beneficiary institutions causes difficulties for NIPAC to collect information and report on the progress and achievement made in different projects.

As concerns the status of implementation of the activities under the WBIF during 2020, the main data are presented in the tables below.

| NIC Contact point | Evgenija Serafimovska Kirkovski- Head of NIPAC office Suzana Peneva, State Councillor – Ministry of Finance |
| --- | --- |
| NIC Meetings (previous meeting held/upcoming meeting) | NIC Second level meeting with Environment Sector held on 25 November 2020 NIC Second level meeting with Transport Sector held on 27 November 2020 NIC Second level meeting with Energy Sector held on 30 November 2020 NIC Second level meeting with Social Sector held on 04 December 2020. NIC First level meeting held on 14 December 2020 (online) |
| Single Project Pipeline | Total number of Projects: | Sin§§§daggle Project Pipeline |
|  | 163 | 8,536,450,469 EUR |
| SSPPs | BRI | SSPPs | BRI | SSPPs | BRI |
| Total number of projects / total estimated value | 2 Project(Digital Connectivity) 88.000.000 EUR | Total number of projects / total estimated value | 2 Project(Digital Connectivity) 88.000.000 EUR | Total number of projects / total estimated value | 2 Project(Digital Connectivity) 88.000.000 EUR |
| SPP Revision | SPP Revised in the First Level NIC meeting that took place on 14 December 2020; 29 new projects were added. The SPP was officially adopted by the Government on 5 January 2021 on its 37 session. |
| NIC framework Key issues |  |
| Submission of Application under 24 TA WBIF Call | WB24-MKD-TRA-01 - Orient/East-Med Corridor: Construction of Rail Corridor VIII in North Macedonia, Sections Kumanovo - Deve Bair WB24-MKD-TRA-02 -Orient/East-Med Corridor: Modernisation of Skopje - Kicevo Railway Line on Corridor VIII WB24-MKD-TRA-03 - Technical Assistance for preparation of Technical documentation at Detailed design level for construction of Toll Station on Orient/East-Med Corridor: North Macedonia – Kosovo Road Interconnection, BC Blace – Skopje (Stenkovec Interchange) Motorway Section |
| TA and Grant applications approved on the 23rd WBIF SC meeting on 10-11 December 2020 | WB-IG05-MKD-SOC-01: North Macedonia, Rehabilitation of Physical Education Facilities in Primary and Secondary Schools and Acquisition of Sports Equipment 3,069,000 Eur;(Investment round 5) WB24-MKD-TRA-03 - Technical Assistance for preparation of Technical documentation at Detailed design level for construction of Toll Station on Orient/East-Med Corridor: North Macedonia – Kosovo Road Interconnection, BC Blace – Skopje (Stenkovec Interchange) Motorway Section – 300,000 EUR (TA approved through written procedure.) |
| TA and Grant applications not approved on the 23rd WBIF SC meeting on 10-11 December 2020 | WB-IG05-MKD-ENV-01- Construction of the Wastewater Treatment Plant for City of Skopje (Investment grant round 05 project) WB24-MKD-TRA-01 - Rail Corridor VIII, Section Kumanovo – Beljakovce: Supervision Services and Project Implementation Unit Assistance (24 TA round project) |

At the end of 2020 and after the meeting of the 23rd WBIF Steering Committee that took place on 10-11 December 2020 (online meeting), a TA round 25 and Investment round 6 call was launched for projects in the sectors transport, energy, environment, social and digital connectivity.

- Donor coordination

In 2020, major progress in donor coordination can be reported. Thirteen meetings of the SWGs chaired by the competent minister were held and at least 18 meetings of the SWG at technical level were held. In the tables below it is presented the list of the main meetings held, as well as the list of donors included in these meetings.

Main meetings of the SWGs

| SWGs in Plenary session | Subject |
| --- | --- |
| Health | Establishment and presentation of a study on secondary and tertiary health structure and presentation of the draft Rules of Procedure. |
| Environment | IPA III SR and AFs |
| EESP | IPA III SR and AFs |
| C&I | IPA III SR and AFs |
| Judiciary, Corruption and Fundamental rights | IPA III SR and AFs |
| PAR and Digital Economy | IPA III SR and AFs |
| Transport | IPA III SR and AFs |
| PFM | IPA III SR and AFs |
| Justice | SR on Judiciary, Fight against corruption and Fundamental rights |
| EESP | SR |
| PAR/DE | SR |
| Health | SR |
| HA | SR |

| SWGs at technical level | Subject |
| --- | --- |
| All IPA coordinators, NIPAC, EUD | IPA III |
| Justice | SR plus AD |
| Justice | Targets of the strategic response |
| PFM | Monitoring |
| ARD plus Fishery | Targets of the strategic response |
| HA | Targets of the strategic response |
| LRD | Targets of the strategic response |
| ENV | Targets of the strategic response |
| EESP plus Health | Targets of the strategic response |
| C&I | Targets of the strategic response |
| PAR | Targets of the strategic response |
| Energy plus Digital Agenda | Targets of the strategic response |
| Energy | Targets of the strategic response |
| Energy | Monitoring |
| ERP | Targets of the strategic response |
| HA (Organized crime) | Targets of the strategic response |
| HA (Organised crime) | Targets of the strategic response |
| HA (PPO) | Targets of the strategic response |

Main donors, IFIs, Embassies and CSOs involved in the meeting of the SWGs

| Donors and International Organisations | EUD, UNDP, UNICEF, UNHCR, UNFPA, UNWOMAN, OSCE, Council of EU, International Centre for Migration, International Labour organisation, Intern organisation for Migration (IOM), International Org. for Electoral Systems, GIZ, British Council Swiss Agency for Development, USAID, |
| --- | --- |
| IFIs | World Bank, EBRD, KFW and CEB |
| Embassies | Italian, Hungarian, Swedish, German, Czech, Greek, Bulgarian, Dutch, British, Spanish, French, US, Swiss, Chinese (PRC) |
| CSOs | International Republican Institute IRI, Macedonian Yung Lawyers, Association MYLA, ZENIT, Macedonian Judges association, Foundation Open Society Macedonia, Human Rights Institute, European Policy Institute, Macedonian Ecological Society, We Effect, Civil Associations “Rural Development, Macedonian Association of Agricultural Cooperatives, Co-operative res Group, National Federation of Farmers, EDRM European movement of RM, NAPM, Association of Agriculture Economists, Food and Agriculture organisation, Rural Development Network, European Movement -RM, NFF National Federation of Farmers, CNVP, ISA, Foundation step by step, Adult education centre, National Civil Education Centre, HERA, HUMANOST, REACTOR, National Network and violence against woman, Friedrich-Ebert-Stiftung, Euro think, Macedonian Civic Education Centre, Recourse centre of Parents with children with special needs, VET Centre, Nansen dialogue Centre, Association of Communal Serviced Providers, Macedonian Chamber of Information and communication Technologies, Economic Chamber of Macedonia, Crimson Development Foundation, American Chamber of Commerce in Macedonia, EPI -Skopje, MCMS, LAG Agro Lider-Prilep, Institute for Sociological Research and Sustainable Development Struga, ECCO awareness |

Under indirect management by RoNM:

- Overall implementation of IPA assistance under indirect management

Within IPA II (2014-2020), the management of IPA funds is divided between direct and indirect management structures in the Republic of North Macedonia. Having in mind the perspectives of the Republic of North Macedonia for the future management of the Structural Instruments, the national authorities in the period 2014-2020 focused their activities on fulfilling the conditions for granting the right of the Republic of North Macedonia to implement the EU budget in several sectors i.e. Justice and Interior, Environment and Climate Change, Transport and Education, Employment and Social Policy. In all these programmes, which are implemented under the indirect management, CFCD has a role of the Contracting Authority; responsible for tendering, contracting and payment, and at the same time is heading the whole Operating Structure. As part of the IPA Operating Structure, the following institutions are involved in the system of indirect management of the IPA funds, responsible for the technical implementation of the contracts:

- Ministry of Justice and Ministry of Interior - for Action Programme of the Republic of North Macedonia for 2014 - IPA / 2014 / 037-701.

- Ministry of Environment and Physical Planning and Ministry of Transport and Communication (including the Public Enterprise for State Roads) - for Multi-annual Sectoral Operational Programme of the Republic of North Macedonia for the Environment and Climate Change and Transport for the period 2014-2020.

- Ministry of Labour and Social Policy and Ministry of Education and Science - for Action programme of the Republic of North Macedonia for 2017 (Action 4: EU support for Education, Employment and Social Policy (Results 2 and 3)).

Having in mind the fact that the programme’s governance system is established and accredited to include a body in addition to the Ministry of Finance (CFCD) and other institutions that are beneficiaries of IPA assistance, efficient functioning of the system and timely implementation of the programme in large part depends on the capacities in terms of the number of employees and the necessary knowledge for project management of the IPA structures, as well as in the other parts of these institutions involved in the implementation of projects and their promptness to implement the projects from the appropriate programme.

The reason for the late start with the implementation of the programme is, above all, the untimely preparation of the required tender documentation due to the late definition of the projects and the prioritization of the same by the line ministries and beneficiary institutions. This situation, subsequently, causes delays in the preparation of the tendering documents and in implementation of all planned tender procedures, which afterwards cause late contracting for the envisaged contracts. Beside the delays in the preparation of the Operation Identification Sheets (OIS), it is important to emphasize the importance of timely and quality preparation of tender documents. Also, the already submitted tender documents prepared by the line ministries are often with not sufficient quality, which further prolongs the procedure, because their finalization is needed to be done by the CFCD instead only to be checked and further aligned with the PRAG provisions.

As part of the quality assurance process, the Central Financing and Contracting Department continuously monitors the “Rejection Rate”. This includes measuring of two parameters, i.e., “Internal Rejection Rate”, which is calculated based on the exchange of tender documents between the Central Financing and Contracting Department and the Beneficiary Institutions, and the “External Rejection Rate”, which is calculated based on the exchange of tender documents between the Central Financing and Contracting Department and the EU Delegation within the process of “ex-ante” controls.

The Lessons Learned Analysis (LLA), as a tool that is used to improve the quality of the work of the indirect management structures.

Currently, the very important risk is the capacities of the structures responsible for the implementation of IPA II. During 2020, there was an evident outflow of trained and professional staff in all IPA beneficiary institutions. It was an outflow of employees who were in the structure from the very beginning of its formation and in whose knowledge and capacities it has been invested for many years. The rate of outflow of qualified and qualified staff is alarming in the following institutions: MS 17%, CFCD 13%, NIPAC Office 20%, Ministry of Environment and Physical Planning 10, Ministry of Education and Science 33% and Ministry of Justice 20%. The situation in all institutions is worrying. Due to the large staff outbreak, staff capacities are insufficient to meet the basic principles and criteria for the proper functioning of the system.

Given the worldwide pandemic of COVID – 19, SEA and NIPAC Secretariat consequently had to adapt to the newly introduced modus operandi, slow-down and reorganize in its work and in organizing capacity building activities.

On 7th of June Parliamentary elections were held. Consequently, the new Parliament voted for a new government, and this resulted in a change on the helm of SEA – i.e., new NIPAC.

Apart from the new circumstances, there was an unexpected new development: on 9th of September 2020 there was a fire in the SEA premises, this brought the operation almost to a complete halt, and after two months a movement to new premises was organized. Approximately at the same time, SEA became fully operational, with full observance of COVID-19 protocols on protection.

During 2020, following changes on the key working positions in the Management and control system have been done:

- With decision of the Government of the Republic of North Macedonia, number 44-7940/1 as of 1st September 2020, new National IPA Coordinator (NIPAC) was appointed. Mr. Nikola Dimitrov, Deputy Prime Minister for European Affairs was appointed as NIPAC.

- As of 4th October 2020, the Head of the operating structure and Head of the Central financing and contracting department (CFCD), Ms Radica Koceva left her position. With decision number 04-9434/1 30th December 2020, via public call, Ms. Ermira Fida was employed as Head of the Central financing and contracting department (CFCD).

- Regarding the key managerial position, with internal call the positions of Head of National fund unit and Head of the NAO support unit, within the Management Structure (IPA Funds Management Department) were filled as of 21st January 2020. With internal transfer within the Ministry of finance (decision number 04-6474/1 as of 9th October 2020), the Assistant Head of the Management Structure (IPA Funds Management Department) was moved as Assistant Head of the Central financing and contracting department (CFCD).

- During 2020 the following changes of the working arrangements have been introduced by the competent authorities:

- The amendment of all sections of the internal Manual of procedures of the Management Structure (version 2.0) as of December 2020 was approved by NAO on 11th January 2021 and by the Minister of finance on 15th January 2021. This comprehensive change includes the recommendations given by the experts within a project for technical assistance in the area of certification of expenditures and monitoring of the ex post sustainability of the investment projects by the NAO as well as the recommendations given by the auditors of DG NEAR in the last final report for verification mission performed during June 2019.

- The version 1.1 - of the Section P - IT – Strategy and General Policies for CFCD and for the Management Structure and Service Management was changed and version 1.0 of the new Section Information Security Policy was introduced and both entered into force by approval of HOS, NAO and the Minister of finance as of 14thFebruary 2020.

Brief information about functioning of the management and control system

For the Annual Programme 2014, updated Consolidated Action Plan of Internal Control Weaknesses and appropriate actions that need to be taken by the management for their removal has been drafted by NAOSO.  The Consolidated action plan comprising the following weaknesses identified in the frame of NAO assessment, during 2020:

- Staff weaknesses in MS/OS and NIPAC Office and

- Ineffective internal audit function in the OS (MoJ).

In addition, improving the design of the Information Security is also noted as needed activity that should be implemented.

Based on the preformed assessment by the NAO it could be concluded that the identified weaknesses on the management and control system, although are a significant weakness, yet in practice does not jeopardize the effective functioning of the overall management and control system.

The NAO and MS, the Operating Structure, including CFCD and IPA Structures - Line Ministries/Beneficiary Institutions, as well as the other concerned parties continued to work for overcoming the deficiencies identified within the Audit Reports by DG NEAR and the Audit Authority.

Staff planning, recruitment, retention, training, and appraisal Regularly, in accordance with the Internal Manual of Procedures, IPA structures prepare indicative workload analysis covering 3 years’ period that is essential for optimal calculation of the number of employees in certain period and proper distribution of the tasks among them. WLA is updated each year, in accordance with the changes of employment and needs for employees to assure the execution of regular activities of IPA structures. Based on the prepared separate WLA per institution, Management Structure prepared consolidated WLA analysis for 2020. According to the prepared Consolidated Workload Analysis for 2020, the needed optimal number of employees in the IPA structures for implementing Annual Action Programme 2014 implemented under indirect management was estimated on 113 employees. Now of preparation of the Consolidated WLA in April 2020 the number of employees in the IPA structures was 83 or on the level of the whole IPA structure 73% of the necessary optimal number of employees has been filled. However, huge constrain is considered the vacant managerial positions in the institutions (7 out of 30 needed employees are managerial positions). Also, it is evident turnover of staff especially on the key working positions where experienced and trained staff is leaving the IPA structure. This may cause serious influence on the overall capacity of the structure, especially in terms of quality. In the table below are presented the data regarding the number of the human resource capacities in the structures for implementation of CAP 2014 calculated according to the WLA for 2020 and the number of the employees at the end of 2020: Institution Number of staff on 31.12.2019 Number of staff needed as per WLA 2020 Realized new recruitments 2020 Left the position 2020 Number of staff on 31.12.2020 Occupancy rate Turnover rate Management Structure 17 19 1 3 15 79% 18% CFCD 39 54 7 5 41 76% 13% NIPAC office 15 26 4 3 16 62% 20% Ministry of Interior 5 7 1 0 6 86% 0% Ministry of Justice 5 7 0 1 4 57% 20% Total 81 113 13 12 82 73% 15% Having in mind the DG NEAR audit - regarding delays in the staff recruitment cycle, can be reported as of the side of NAO/MS urgency letter was submitted to the NIPAC/Operating Structure on 01.07.2020 (Letter No. 10-5209/1) in order IPA structures to identify the needs for new employment, before budget cycle preparation in the institutions starts. This activity had final purpose all institutions to have the real recruitment needs identified in order within the following budget period funds for employment to be secured on time. In addition, MS, Manual of Procedures was amended in order WLA analysis to be prepared by the end of June in the current year for the following year. This should be also applied in the NIPAC/OS manual of procedures as well in the IA to be aligned with the budget preparation. However, from the practice it can be noted that it is very hard to secure funds all new employments needed, yet this is ongoing process, and all urgent needs are tackled with utmost importance. By the preparation of this AMD self-assessment report, it can be reported: Management Structure - public calls for employment of 7 staff members were published in December 2020, and are in final stage. However still Decisions for employment are not adopted to be reported number of people engaged in MS under this public calls. In addition, internal vacancy was announced on 09.02.2021 for promotion of one employee within MS The procedure is ongoing. Internal vacancy for promotion of one more employee should be announcedin the second half of February 2020. CFCD - public calls for employment of 6 staff members were published in December 2020, and are in final stage. However still Decisions for employments are not adopted to be reported number of people engaged in MS under this public calls. In addition, internal vacancy was announced 09.02.2021 for promotion of 3 employees within CFCD (Head of Unit - 2 positions, GACU and PCU and adviser 1 position) - the procedure is ongoing. Internal vacancy for promotion of two more employees should be announced in the second half of February 2020. NIPAC Office has initiated procedure for 5 new employments (the procedure is in stage of obtaining opinion by the MoF). MoJ has planned one employment (senior associate) within the recruitment plan of the ministry for 2021. The procedure is in phase of obtaining opinion from the MISA (Ministry of Information Society and Administration). MoI does not have requested new employments since the optimal number of employees is reached. In addition, Government of Republic of North Macedonia on season held on 09th of February 2021 adopted conclusion where line ministries in the operating structure are obliged urgently to revise their recruitment plans according to the needs within IPA structure and to fulfil empty working posts within the IPA structures by the end of first quarter 2021. Accordingly, with the same conclusion, Ministry of Finance is obliged to give consent for these employments. Regarding the staff capacities, it can be summarised that the rate of filled necessary working posts vs the needed indicated in the WLA for 2020 is 73% and its lower than 2019. The rate for key positions is 67% and it has trend of increasing during the year, while the rate for fulfilment of non-key staff positions is 74% and its lower than 2019. The overall rate of turnover is high - 15% on programme level and it is above the targeted 5%-10%. Having in mind that the turnover of staff in the abovementioned institutions is evident, it is necessary a staff retention policy to be established. Based on the conclusion adopted by the Government in January 2021 and initiated by NIPAC, working group was established to prepare and propose retention and motivation policy proposal to the Government. It is expected during first quarter of 2021 to have mature model of retention and motivation policy in place. Regarding the training, IPA Training Centre is established in the Secretariat for European Affairs to meet the training needs of the whole IPA structure in the Republic of North Macedonia. Although the IPA Training Centre is formally established, still, the trainings for the IPA staff within the Republic of North Macedonia are not organized and realised in practice. Training process is also introduced in the Law on Administrative Servants which is coordinated and implemented by the Agency for Administration. However due to the advanced stage of implementation of the IPA programmes under de-centralised and indirect management, the experienced staff enables coaching and training the new employees via on a job training and learning by doing. Financial management Based on the financial projections submitted by CFCD through the year and based on the various analyses performed by NF, budget liquidity for the national co-financing and IPA funds was analysed and appropriate measures were undertaken by NF to ensure smooth implementation of the planned projections. Pursuant to Article 18(4) and Article 33(3) of the Framework Agreement for IPA II, NAO sent to the Commission a Forecast of its Likely Payment Request for the Programme on 15th January 2020 and 20th July 2020. Status of implementation of the forecast for payments for 2020 submitted by CFCD. Action Programmes Projections for payment received from CFCD in January 2020 Realised projections for payment in 2020 % of realisation 1 2 3 4=3/2 Justice Sector 3,119,929.16 2,941,406.65 94% Home Affairs Sector 2,854,518.01 92,962.16 3% Total 5,974,447.17 3,034,368.81 51% The analyses refer to the EU contribution express in Euro In July 2020 CFCD submitted revised projections for payment for 2020. This point is being stressed by NF/NAO in the past years on a regular base. Forecast of its Likely Payment Request submitted by NAO to EC are prepared based on these projections. Being aware of the situation, NF performs additional analyses taking into consideration the experience and disbursement pace from previous years, problem encountered, monthly meetings info, availability of funds in the national budget, etc. Once, having all this information processed, NF prepares Forecast of its Likely Payment Request, which in the past several years differ from CFCD disbursement plan. Overall status of the implementation for IPA II 2014 Annual Programme by separate action is presented in the table below: Overall implementation of IPA II 2014 Annual Programme National Programmes IPA Allocations Contracted amount Paid amount % of contracted vs. IPA Allocations % of paid vs. IPA Allocations 1 2 3 4 5=3/2 6=4/2 АP 2014 – Justice Sector Programme 13,000,000.00 6,891,068.47 6,379,598.08 53% 49% АP 2014 – Home Affairs 7,000,000.00 5,847,486.51 3,085,930.66 84% 44% UPA 6,717,811.25 6,435,546.58 6,435,546.58 96% 96% Total 26,717,811.25 19,174,101.56 15.901.075,32 72% 60% Performance indicator analysis The disbursement rate for CAP 2014 at the end of 2020 is 60% in total compared with the budget of signed Financing Agreement. Around 51% of the disbursement plan in total was achieved till the end of 2020 compared with the Forecast of Likely payment request sent to EC. By institution, MoJ has 94% of realisation, while MoI has 3% of realisation of the disbursement plan. Comparing the projections for payment submitted in January and July for the period July-December 2020 there is 12% discrepancy i.e., more exactly by sector: Sector Justice – 4-time increased projections, Sector Home Affairs - 40% decreased projections. Lack of cooperation and input in preparation of the projects from the Line Ministries is evident. Total de-committed amount is around 7,6 million euros. General Concerns for the functioning of the system are: The capacities in the OS are inadequate to the workload needs, both in view of the insufficient number of staff, but mostly due to the lack of qualified and experienced staff in all OS. Ineffective internal audit function in the OS for all IPA Components, both due to lack of staff and lack of expertise. Failure to adopt the Retention Policy Paper, which cause frequent turn-over of the IPA staff in all institutions which are part of the decentralised IPA structures. Concerns regarding CFCD. In 2020, the turnover of staff continued, with the highlight point when the position of Head of CFCD was left vacant, along with the position of Deputy head of CFCD. The lack of managerial staff was felt in the decision making process, quality control, and has also left a message of urgent remedial actions to be taken. It is inevitable to be stressed out that the issue of non-fulfilment of key positions in CFCD which crawl as of 2019 (Head of EU Procurement and Contracting Unit and Head of General Affairs and Control Unit) significantly jeopardize the proper functioning of the system as a whole and it should be noted as a final call for urgent efforts to be made regarding the strengthening of the administrative capacities which affect the system. The latest developments with staff turnover, particularly in the Contracting Authority, seriously affected the overall performance of the Operating Structure in terms of delivering quality and mature documents, and especially in securing the overall control functions at all levels. By end of 2020 the rate of fulfilled key positions in CFCD accounted around 50%, meaning that only 4 positions were filled out of 9 needed. Besides, the turnover of non-managerial staff is also evident. The annual turnover rate in CFCD is continuously over the acceptable level, over the years is around (7% in 2017 and 14% in 2018, 24% in 2019, 13% in 2020). Concerns regarding CAP Changes in the management staff from the previous year, and work overload to only few people working on IPA posts during 2020 has affected the overall work in the IPA structures, which resulted in delaying the activities related to the timely implementation of the projects for which the contracts are signed (this concern relates to MoI). In addition to this, the capacities of the structures responsible for the implementation of IPA 2 are huge risk at the moment. During 2020, although fighting the pandemics with COVID-19, it was also a “fight” with proper implementation of projects and work in the system as a whole. Preventive measures slowed down the work dynamics, and lack of administrative capacities along with work overload led to lack of motivation to work in IPA structures. Corrective measures: Vacant positions in CFCD, particularly the key managerial position, should be immediately filled with adequate and experience staff. Staff in the beneficiary institutions should also be coached by the IPA structures on defining the needs of the institutions and proper requirements, but also on basic PRAG principles and their role as final beneficiaries. The retention and motivation policy measures for all IPA staff should be urgently adopted and implemented as soon as possible in order to avoid future turn-over of high qualified and experienced staff working on the IPA funds. The professional skills of the employees working in IPA structure should be regularly improved through high quality trainings in different areas of expertise, including sharing the experience with other countries and similar bodies/institutors.

For the Annual Action Programme for 2017

The following weaknesses during 2020 are identified:

- Staff weaknesses in MS/OS and NIPAC Office;

- Delays in the implementation of the Procurement Plan;

- Limited number of offices for conducting evaluations in camera and not sufficient archive space in CFCD;

- Unrealistic payment forecasting.

In addition, improving the design of the Information Security is also noted as needed activity that should be implemented (for the MoES).

Taking into consideration the preformed assessment by the NAO on the corrective measures undertaken, it could be concluded that the identified weaknesses on the management and control system should not be considered as significant weaknesses which jeopardize the effective functioning of the overall management and control system.

The NAO and MS, the Operating Structure, including CFCD and IPA Structures - Line Ministries/Beneficiary Institutions, as well as the other concerned parties continued to work for overcoming the deficiencies identified within the Audit Reports by DG NEAR and the Audit Authority.

Staff planning, recruitment, retention, training, and appraisal According to the prepared Consolidated Workload Analysis for 2020, the needed optimal number of employees in the IPA structures for implementing Annual Action Program 2017 implemented under indirect management was estimated on 116 employees. Now of preparation of the Consolidated WLA in April 2020 the number of employees in the IPA structures was 84 or on the level of the whole IPA structure 72% of the necessary optimal number of employees has been filled. However, huge constrain is considered the vacant managerial positions in the institutions (9 out of 32 needed employees are managerial positions). Also, it is evident turnover of staff especially on the key working positions where experienced and trained staff is leaving the IPA structure. This may cause serious influence on the overall capacity of the structure, especially in terms of quality. In the table below are presented the data regarding the number of the human resource capacities in the structures for implementation of AAP 2017 calculated according to the WLA for 2020 and the number of the employees at the end of 2020: Institution Number of staff on 31.12.2019 Number of staff needed as per WLA 2020 Realized new recruitments 2020 Left the position 2020 Number of staff on 31.12.2020 Occupancy rate Turnover rate Management Structure 17 19 1 3 15 79% 18% CFCD 39 54 7 5 41 76% 13% NIPAC office 15 26 4 3 15 62% 20% Ministry of Labour and Social Policy 7 9 1 0 8 89% 0% Ministry of Education and science 3 8 2 1 4 50% 33% Total 81 116 15 12 84 72% 15% MoES has planned 2 new employments for 2021 and one promotion. The procedure is in phase of obtaining approval on the changes of the recruitment plan within Ministry of Finance. MLSP has planned 2 new employments in 2021, one managerial – Head of monitoring and evaluation Unit and one non-managerial – Advisor for implementation of EU pre-accession assistance in the Unit for coordination and implementation of EU financial instruments. However, till preparation of this self-assessment report the procedure is still not initiated from the MLSP. Regarding the staff capacities, it can be summarised that the rate of filled necessary working posts vs the needed indicated in the WLA for 2020 is 72%. The rate for key positions is 65%, while the rate for fulfilment of non-key staff positions is 76%. The overall rate of turnover it is above the targeted 5%-10% and is 15% on programme level (same as in 2019 which is continuous high trend). Having in mind that is evident turnover of staff in the abovementioned institutions, it is necessary to be established a staff retention policy. Based on the conclusion adopted by the Government in January 2021 and initiated by NIPAC working group was established to prepare and propose retention and motivation policy proposal to the Government. It is expected during first quarter of 2021 to have mature model of retention and motivation policy in place. Financial management Financing Agreement under the Annual Action Programme for 2017 from IPA II IPA2017/040-200, IPA/2017/040-202 has been signed between the EC and the Government of Republic of North Macedonia on 2nd November 2018. Addendum on this Programme was signed on 10th October 2019. Based on the financial projections submitted by CFCD through the year and based on the various analyses performed by NF, budget liquidity for the national co-financing and IPA funds was analysed and appropriate measures were undertaken by NF to ensure smooth implementation of the planned projections. Pursuant to Article 18(4) and Article 33(3) of the Framework Agreement for IPA II, NAO sent to the Commission a Forecast of its Likely Payment Request for the Programme on 15th January 2020 and 20th July 2020. Status of implementation of the forecast for payments for 2020 submitted by CFCD. Annual Programmes Projections for payment received from CFCD in January 2020 Realised projections for payment in 2020 % of realisation 1 2 3 4=3/2 MLSP 1.438.819,19 0,00 0% MES 1.500.000,00 0,00 0% UPA 175.000,00 175.000,00 100% Total 3.113.819,19 175.000,00 6% The analyses refer to the EU contribution express in Euro. Overall status of the implementation for Annual Action Programme for 2017, by separate action is presented in the table below: National Programmes IPA Allocations Contracted amount Paid amount % of contracted vs. IPA Allocations % of paid vs. IPA Allocations MLSP 7.000.000,00 5.006.190,00 1.211.450,81 72% 17% MES 5.650.000,00 0,00 0,00 0% 0% UPA 5.834.173,00 5.834.173,00 5.834.173,00 100% 100% Total 18.484.173,00 10.840.363,00 7.045.623,81 59% 38% The analyses refer to the EU contribution express in Euro Performance indicator analysis The disbursement rate for AAP 2017 at the end of 2020 is 38% in total compared with the budget of signed Financing Agreement. No payments were realised during 2020 except for the community programmes. The overall contracting rate is 59%, however it is evident risk in MoES where no contract is signed under this programme. It can be concluded that during 2020 the targets regarding the budget execution indicators are met on very low level (no realisation of contracting neither disbursement plan has been made with except to community programmes). The core of this issue is mainly arising from the very low contracting rate and not fulfilment of the procurement plans for MoES. The main reason for this is not respecting the deadlines for submission of the tender documentation and low quality of the already submitted tenders. Therefore, the delays in contracting caused delays in the payments. In July 2020 CFCD submitted revised projections for payment for 2020. Comparing the projections for payment submitted in January and July for the period July-December 2020 there is 52% discrepancy i.e decreased projections or more exactly for Sector Education – 100% decreased projections, Sector Employment – 12% decreased projections. Lack of cooperation and input in preparation of the projects from the Line Ministries is evident. Corrective measures: CFCD to ensure direct involvement of the IPA coordinators and its internal cooperation with involvement of procurement and monitoring officers providing valuable information of the tender procedures as well contract progress status, so the financial managers can prepare realistic projections for payment, which are base for forecasting payment requests to EC. Regarding Delays in the implementation of the Procurement Plan (especially for MoES) realistic planning and setting deadlines in the respective Procurement Plan and prioritisation of the tender procedures. Reporting on monthly basis. (CFCD and Line ministries). Ongoing monitoring on the implementation of the activities stated in the Procurement Plan in accordance with the provisions from the working arrangements. Regular coordinative meeting to be organized. (NAO/NIPAC). Foreseen in the Consolidated Action Plan of Internal Control Weaknesses for 2020 for the Annual Action Programme for the Republic of North Macedonia for education, employment and social policy for 2017. General Concerns: The capacities in the OS are inadequate to the workload needs, both in view of the insufficient number of staff, but mostly due to the lack of qualified and experienced staff in all OS. Administrative capacities of the final beneficiaries and evaluation committee members are also not satisfactory, which results not properly defined requirements in the tender documents or lengthy evaluation procedures. Ineffective internal audit function in the OS for all IPA Components, both due to lack of staff and lack of expertise. Failure to adopt the Retention Policy Paper, which cause frequent turn-over of the IPA staff in all institutions which are part of the decentralised IPA structures. Concerns regarding CFCD. In 2020, the turnover of staff continued, with the highlight point when the position of Head of CFCD was left vacant, along with the position of Deputy head of CFCD. The lack of managerial staff was felt in the decision making process, quality control, and has also left a message of urgent remedial actions to be taken. It is inevitable to be stressed out that the issue of non-fulfilment of key positions in CFCD which crawl as of 2019 (Head of EU Procurement and Contracting Unit and Head of General Affairs and Control Unit) significantly jeopardize the proper functioning of the system as a whole and it should be noted as a final call for urgent efforts to be made regarding the strengthening of the administrative capacities which affect the system. The latest developments with staff turnover, particularly in the Contracting Authority, seriously affected the overall performance of the Operating Structure in terms of delivering quality and mature documents, and especially in securing the overall control functions at all levels. By end of 2020 the rate of fulfilled key positions in CFCD accounted 4 positions filled out of 9 needed. Besides, the turnover of non-managerial staff is also evident. The annual turnover rate in CFCD is continuously over the acceptable level, over the years is around (7% in 2017 and 14% in 2018, 24% in 2019, 13% in 2020). Concerns regarding AAP Changes in the management staff from the previous year, and work overload to only few people working on IPA posts during 2020 (in relation to this programme - Ministry of Education and Science) has affected the overall work in the IPA structures, which resulted in delaying the activities related to the time contracting and proper and timely implementation of the projects for which the contracts are signed. In addition to this, the capacities of the structures responsible for the implementation of IPA 2 are huge risk at the moment. During 2020, although fighting the pandemics with COVID-19, it was also a “fight” with proper implementation of projects and work in the system as a whole. Preventive measures slowed down the work dynamics, and lack of administrative capacities along with work overload led to lack of motivation to work in IPA structures. Corrective measures: Vacant positions in CFCD, particularly the key managerial position, should be immediately filled with adequate and experience staff. Staff in the beneficiary institutions should also be coached by the IPA structures on defining the needs of the institutions and proper requirements, but also on basic PRAG principles and their role as final beneficiaries. The retention and motivation policy measures for all IPA staff should be urgently adopted and implemented as soon as possible in order to avoid future turn-over of high qualified and experienced staff working on the IPA funds. The professional skills of the employees working in IPA structure should be regularly improved through high quality trainings in different areas of expertise, including sharing the experience with other countries and similar bodies/institutors. Based on the above mentioned, during the implementation of the Programmes under IMBC, all the institutions have respected their responsibilities and tasks established in the Internal Manual of Procedures, agreements signed and positive legislation. The Annual Management Declarations during the implementation the previous and current Programmes under IMBC have been submitted by NAO to EC based on these tools for monitoring, where NAO reports on the effectiveness and efficiency of the management and control system based on all the relevant information, considering the work of the internal audit service and Audit Authority.

# II       Information per Sector

# Rule of Law and Fundamental Rights – Sub sector Justice and Home Affairs

# Rule of the Law, Sub sector Justice

- Involvement in programming

So far, two IPA Action Documents were prepared and financed under IPA 2014 and IPA 2020. The activities related to IPA 2014 are almost completed, while the ones under IPA 2020 are at the beginning of their implementation. The main features of the IPA AD 2020 are as follows:

Overall Objective: To strengthen rule of law.

Specific Objective: To strengthen justice and home affairs systems and reinforce the respect to human rights.

Results:

- Improved independence, accountability, quality, and effectiveness of the justice system.

- Stronger capacity to effectively implement modern investigation techniques in fighting organised crime and terrorism.

- Improved enforcement record in fighting corruption.

- Enhanced protection of Human Rights and stronger uptake of alternative means to detention.

- Strengthened freedom of expression.

Total cost: 19,300,000 EUR

EU Contribution: 18,900,000EUR

In Spring 2020, the programming of IPA III started with the preparation of the following documents:

| Strategic Response(s) | Action Fiche(s) | Action Document(s) |
| --- | --- | --- |
| Judiciary | EU for Efficient Judiciary and Enhanced Prevention of Corruption | EU support for strengthen the Rule of Law in the North Macedonia (IPA 2021) |
| Fight against corruption |  |  |
| Fundamental Rights |  |  |

The Action Fiche was sent in June 2020 from the Ministry of Justice to SEA to be adopted by the Government. In the second half of 2020, the latest version of Action Fiche was sent to Brussels for inter-service consultation and relevance evaluation. The IPA III Action Document “EU support for strengthen the Rule of Law in the North Macedonia” for 2021, will be implemented under direct management.

The activities included in the AD aim at improving the efficiency of the judicial system and the efficiency of the prevention and the fight against corruption. The expected outputs are:

1.Enhanced digitalisation of state institutions in the judiciary and anti-corruption areas.

2.Strengthened capacities of the Constitutional Court to control the constitutionality and legality of the adopted normative acts.

3.Technical documentation for the training premises of the Academy for Judges and Public Prosecutors

4.Raised public intolerance to corruption.

Indicative budget: 9,6 million EUR

EU funding: EUR 8,5 million

National funding: EUR 1.1 million (including EUR 100,000 provided by the grant beneficiaries)

By the end of 2021/ beginning of 2022, the Financial Agreement for 2021 is expected to be signed.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

Detailed information on the implementation of the Roadmap is presented in Annex 4 of the Report. The table below summarises the objectives achieved and the concrete actions that will be implemented to fully accomplish the Roadmap.

| Criteria: Strategic Planning | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached. |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached. |
| Criteria: Coordination | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached. |
| Criteria: Performance | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached. |
| Criteria: Budget | Self-assessment: Half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Remarks: Most of the targets have been reached or substantially reached. The ones that are yet to be reached will be reached in 2021with the support of the TA Project “Support to the Management of EU Funds”. There is a delay in the achievement of the targets under the criterion Budget since the Ministry of Finance has not yet elaborated the procedures for the preparation of the medium-term budget. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The coordination with other instruments is articulated as follows:

- Coordination meetings within the SWG that has the role to coordinate all the stakeholders active in the sector.

- Bilateral relationships with donors.

- Relationships with IFIs.

The following meetings of the SWGs were organised in 2020:

| Plenary Session |
| --- |
| Date | Number of participants | Discussed topics |
| 25.06.2020 30.10.2020 | 35-40 35-40 | Overview IPA III and Strategic Response for W I Rule of law, fundamental rights, and democracy - Thematic priority 1. Judiciary/Thematic priority 2. Fight against corruption/ Thematic priority 5. Fundamental Rights and presentation of the Action Fiche/s for IPA III Action Programmes for 2021 and 2022 Presentation of the Strategic responses for IPA III WINDOW 1 - RULE OF LAW, FUNDAMENTAL RIGHTS AND DEMOCRACY Thematic priority 1: Judiciary Thematic priority 2: Fight against corruption Thematic priority 5: Fundamental rights |
| Thematic Sessions |
| Date | Number of participants | Discussed topics |
| 05.10.2020 09.11.2020 | 35-40 30 | Strategic Response for Window 1: Rule of law, fundamental rights and democracy- Thematic priorities 1 Judiciary, 2 Fight against Corruption, 5 Fundamental Rights and 6 Democracy |

The following donors, Embassies and CSOs were present at these meetings.

| Donors | Embassies | CSOs |
| --- | --- | --- |
| EU Delegation | Dutch | Foundation Open Society - Macedonia |
| Council of Europe | UK | Eurothink/IPA Mechanism |
| GIZ | USA | MYLA |
| UNICEF |  | Institute for Huan Rights (IHR) |
| OSCE | Italian | Association for Development Initiatives Zenit |
|  | French | European Policy Institute (EPI) |
|  | Bulgarian | Coalition for Fair Trial |
|  |  | Association for Democratic Initiatives (ADI) |

At present, in the sub-sector “Judiciary”, the following programmes financed by the donors are under implementation:

| Donor | Budget | Project Title/ objective of the project | Implementation period |
| --- | --- | --- | --- |
| British Embassy | £65,960 | Establishing efficient and effective environmental compliance mechanism | Project pending approval Oct 2020 – March, 2021 |
|  | £43,958 | Monitoring merit-based appointments in senior public service | Project Pending Approval October 2020- March 2021 |
|  | £958,225 | Improved policies through civic participation | April 2020 – March, 2022 |
|  | Up to £ 20 M | Regional Rule of Law initiative | December 2020 March 2024 |
|  | £329,727 | Bringing change - Good governance and effectiveness of the public administration | August 2018 - March 2020 |
|  | £95,700 | Action for more transparent, accountable and effective JC | June 2018 - March 2020 |
|  | £183,365 | Design of a performance indicator matrix for the Public Prosecutor’s Office in Republic of North Macedonia | June 2018 - March 2019 |
|  | £257,823 | Enhancing transparency, legal certainty, and efficiency of the judicial system in North Macedonia | June 2019 - March 2020 |
|  | £ 525,445 | The RNM through the improved performance of justice sector institutions | June 2019 – March 2020 |
| Embassy of Netherland | 128,283 € | Strengthening the Professionalism, Competence, and Integrity of Young Lawyers in North Macedonia through an internship programme in justice institutions | January 2020 – January 2022 |
|  | 77,854 € | Quality System for Evaluation of Judges’ | November 2019–November 2020 |
|  | 79,144 € | Model for Implementation of the Law on Probation’ | November 2019 – November 2021 |
|  | 650,000 € | Together for Accountability’ –Project for Support of the Special Public Prosecution in North Macedonia | March 2018 - March 2020 |
|  | 1,938,703 € | Improving Prison Environment for Children and Juveniles’ | January 2018 – December 2020 |
|  | 98,400 € | Towards Accountable Public Enterprises’ | October 2019 – October 2021 |
|  | 87,506 € | Vulnerability to corruption in public service employments’ | July 2019 – June 2020 |
|  | 63,384 € | Anti-corruption education for high school students | January 2019 – December 2020 |
|  | 131,857 € | Mediate, do not hesitate. Objective: To contribute to increasing the overall usage rate of the mediation as an alternative dispute resolution. | September 2020-September 2022 |
|  | 24,628 € | Constitutional Court – Guarantor of the Rule of Law’ Objective: Inform on the Constitutional Court’s performance and available mechanisms for protection of the constitutionality and legality of laws and acts, and the constitutionally guaranteed human rights; Improve data collection through continuous monitoring and analyzing of the work of the Constitutional Court; | September 2020-August 2021 |
|  | 51,594 € | VidiVaka Visual and Interactive Storytelling for the Judiciary System and Accountability’ Objective: raised knowledge of the public on the judiciary, through new, innovative, and interactive media production, so they can navigate through complex procedures and make decisions based on relevant information. | September 2020 - August 2021 |
|  | 954,850 € | ‘Enhancing the efficiency, accountability and transparency of the Judicial Council of North Macedonia.’ Objective: strengthen the capacities and competencies of the Judicial Council (JC); exchange expertise with the Dutch Council for the Judiciary (Cfj) through a peer-to-peer approach. | September 2020 - September 2024 |
|  | 1,901,624 € | Strengthening Enforcement in North Macedonia, Serbia, Kosovo, Albania Objective: Strengthening RoL in pre-accession countries of the WB by strengthening their capacities to ensure an efficient and effective enforcement of civil judgements and other enforceable titles; strengthen the private enforcement agents’ systems in dealing with cross-border enforcement and make them more accountable by strengthening relevant mechanisms for monitoring and control | September 2020-September 2024 |
| UNICEF | 5,000 € | Improving primary and secondary legislation related to prevention from and responding to violence against children | January – December 2020 |
|  | 5,000 € | Increase the capacity of the institutions to monitor the situation of violence against children | January – December 2020 |
|  | 15,000 € | Increase access to rehabilitation, re-socialisation, education and health services of children in the correctional facilities, through advocacy and capacity development | April - December 2020 |
| GIZ | 3,000,000 € for the Western Balkan | GIZ Global Program Combating Illicit Financial Flows - Western Balkan region goal is to improve conditions for the fight against illicit financial flows (IFFs), both within and out of the regions, across sectors and national borders. | January 2019-January 2022 |
|  | 17,915,000 € | Countering Serious Crimes in the Western Balkans - to enhance the capacities of authorities in the Western Balkans to fight organised crime and terrorism including preventing and countering violent extremism by enhancing cooperation within the region and with the EU. | July 2020-June 2023 |
|  | 3,000,000 € | Open Regional Fund for SEE-Legal reform - to improve regional cooperation in the Western Balkans to implement legal reforms in the framework of EU approximation, with a special focus on fostering sustainable economic development. | January 2019-December 2021 |
| UNODC | 2,500,000 € | To build the capacities of South Eastern Europe to conduct financial investigations to effectively detect, deter and prosecute money laundering and the financing of terrorism as well as enhance regional and inter-agency cooperation | 2017-2020 (March) |
|  | 4,450,000 € | To promote rule of law and good governance through targeted border control measures at ports and airports | 2020-2023 |
| USAID | USD 9.4 million | Civic Engagement Project (CEP) - supports constructive engagement by civil society organizations (CSOs) on anti-corruption, transparency, and rule of law policies and issues; and increases and sustains youth engagement in public life in North Macedonia. | August 2016 –August 2021 |
|  | USD 400,000 | USAID/OTI – supports capacity building of the Judicial Council and the State Commission for Prevention of Corruption | March 2019 - June 2020 |
| OSCE | 345,731.00 € | Support North Macedonia in advancing Rule of Law and Human Rights | January-December 2020 |
| Council of Europe | 1,050,000. € | Enhancing the capacities of the penitentiary system and the external oversight mechanism in North Macedonia | 24 May 2019 – May 2022 |
|  | 775,000 € | Action against Economic Crime in the Republic of North Macedonia | 24 May 2019 – May 2022 |
|  | 715,000 € | Preventing and combating trafficking in human beings in North Macedonia | 24 May 2019 - May 2022 |
|  | 800 000 € | Supporting enhanced access to higher quality Free Legal Aid services in North Macedonia | 24 May 2019 - May 2022 |
|  | 510,000 € | Freedom of Expression and Freedom of the Media in North Macedonia (JUFREX 2) | 24 May 2019 - May 2022 |
|  | 250,000 € | Promotion of diversity and equality in North Macedonia | 24 May 2019 - May 2022 |
| US Embassy | USD 20,000 | INL is planning to equip three courtrooms at the Skopje Appellate Court with audio recording equipment. | February-June 2020 |
|  | USD 160,000 | INL funded new website and an e-learning platform for the Academy for Judges and Prosecutors in calendar year 2019. In 2020, INL will strengthen the Academy’s use of distance learning options. Additionally, INL will partner with the Academy to conduct programming focused on strengthening leadership and management skills among chief judges and prosecutors, RICO (Racketeer Influenced and Corrupt Organizations)-related capacity building, and follow-on training on special investigative measures, in partnership with DCAF. | Throughout 2020 |
|  | USD 45,000 | INL’s has an ongoing grant to the Macedonian Judges’ Association to support the work of the Judiciary-Media Council. | Calendar 2019-2020 -221 |
|  | USD 31,000 | INL’s grant to the Macedonian Judges’ Association to support the work of the Judiciary-Media Council remains ongoing. | Calendar 2019-2020 |
|  | USD 188,982 | INL continues to fund the OSCE’s SPO Trial Monitoring Project. | December 2016- June 2020 |
|  | USD 100,000 | INL will provide technical assistance (equipment donations and trainings) to the Financial Police to augment their capacities to probe financial crimes, seize assets, and fight corruption. | Throughout 2020 |
|  | USD 30,000 | INL’s investment in graduate-level legal clinics in criminal law continues at UKIM and SEEU. INL plans to expand the program to a third university in 2020. | February-June 2020 |
|  | USD 20,000 | INL will again sponsor the week-long Ohrid School of Natural Law, organized, and implemented by MANU Strategic Research Center. | July 2020 |
|  | USD 10,000 | INL supports a moot court competition among law students. | September-Dec.2020 |
|  | USD 100,000 | INL is working with Embassy partners to provide a targeted equipment donation to the Ministry of Interior’s Anti-TIP and Human Smuggling Task Force, located within the Public Security Bureau’s Organized and Serious Crimes Division. | Summer 2020 |
|  | USD 130,000 | INL will furnish and provide access control equipment (security scanners) for the Idrizovo Courtroom | January 2021 |
|  | USD 40,00 | INL will sponsor with DCAF to sponsor events on special investigative measures as a follow-up to a U.S. study trip in October 2019 and bench book on special investigative measures. | 2020-2021 |
|  | USD 5,000 | INL will sponsor one-day virtual annual regional judicial conference in cooperation with the Macedonian Judges’ Association. This would be fifth year that INL sponsors this event. | November 2021 |
|  | USD 5,000 | INL sponsors with the Association of Criminal Law and Criminology (ACLC) by funding research and providing office equipment for ACLC. | Until December 2020 |
|  | USD 780,000 | Trial advocacy and skill development – DOJ/OPDAT delivers continuing legal education in partnership with the Academy for Judges and Prosecutors focused on trial advocacy skills, digital evidence, anti-corruption, counterterrorism, and acquisition of foreign-stored evidence, ECHR caselaw, and other salient topics. Judicial mentorship – OPDAT partners with U.S. judges to promote the exchange of ideas and best practices through one-on-one mentorship. Support for legislative amendments - OPDAT supports legislative amendments impacting judicial and prosecutorial institutions by attending working groups and providing advice/input on draft amendments. Assistance for investigative centres - OPDAT partners with other international donors to assist in the development of functional investigative centres. Community outreach - OPDAT works with the Public Prosecution Office and the Prosecutorial Association to encourage open dialogue with the community through increased interaction and communication. | 01 October 2019 – 30 September 30 2020 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II has an impact on the sector, either through the preparation of Action Programmes or through the implementation of TA projects or through the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, the following table shows the main improvements on the functioning of the sector.

Strategic Planning: On November 28, 2017, the Government adopted the Justice Sector Reform Strategy (JSRS) with the 2017-2022 Action Plan. The Ministry of Justice (MоJ) has established operational Working group (WG) as mechanism for monitoring of the progress of the implementation of activities thus involving representatives of all judicial institutions. The Council for monitoring of the implementation of the JSRS on 06.02.2019 adopted the First Annual Report on the Implementation of the JSRS (2017-2022). The Government amended the Decision for establishment of the Council for monitoring on the implementation of the JSRS on 22.12.2020. First meeting of the Council with the new Minister of Justice and new members was held on 28.12.2020. Due to the COVID 19 situation, second annual report covers two years of implementation, i.e., 2019 and 2020. Second annual report was adopted by the Council on 28.12.2020. Based on the review on progress implementation foreseen in the Action Plan of the Strategy, from the total of 227 activities envisaged in the Action Plan, 114 are fully implemented, 35 activities are ongoing, 15 are late, 44 activities are carried out continuously, 13 activities have a later deadline, while 6 activities depend on the previous adoption of legal changes. The main achievements of the JSRS are the following: Independence and impartiality Adopted new Law on Judicial Council, Rulebook for the manner of ranking for the candidates for judges from the Academy for judges and public prosecutors. Adopted new Law on Public Prosecution office and amendments of the Law on Council for Public Prosecutors. Commission for audit for the allocation of court cases (ACCMIS) continues the audit of the courts and prepared second semiannual report. New Law on Case Flow Management in the courts was adopted. Quality The Judicial Council adopted the Rulebook for election of judges in the higher court. With the new Law on Public Prosecution office, a merit system for election on public prosecutors has been established. Decisions for election with detailed elaboration are published on the web sites of the Judicial Council and Council of Public Prosecutors. New concept for evaluation of the work on public prosecutors was established with the new Law on PPO. Appellate courts on regular basis are holding sessions for harmonization of the case law. Law on notaries, Law on enforcement and Law on bar exam were amended and electronic exams were repealed with oral exams. HR Strategy for the Judicial network was adopted by the JC on 11.11.2020 and HR Strategy for the Public Prosecution network was adopted by the State Public Prosecutor on 02.12.2020. Liability New Law on Public Prosecution office was completely harmonized according to the latest practice on the European court of human rights and the opinions on the Venice commission. In the new Law on PPO, provisions on disciplinary measures and the grounds for disciplinary procedure were amended. The amendments of the Law on Council of Public Prosecutors introduced liability for members of the Council. New members of the Advisory Body for Judicial Ethics were appointed. Efficiency Continuously monitoring of judicial efficiency using the indicators of EU Justice Scoreboard (result list), CEPEJ and other international standards. Judicial Council on an annual basis adopts Action plan for cases which are in the system more than three, seven and ten years. Functional Analyses for the appellate courts, Supreme court, Judicial Council, Administrative court and High Administrative court and the Academy for judges and Public Prosecutors were adopted. In 2021 a functional analysis for 27 basic courts will be prepared. Transparency Judicial Council adopted a Strategic plan for communication. Minutes from the Commission for audit for the allocation of court cases are published on the web site of the Ministry of justice. Free legal Aid Trainings for the employees in the regional offices of the Ministry of justice for application on the new Law on Free Legal aid were conducted. New web site pravnapomos.mk is fully operational for the citizens. Memoranda for cooperation in the field of free legal aid were signed between Ministry of justice, Legal clinics, Bar Association and NGOs. Budget on Free Legal Aid for 2020 was increased from three to five million denars. Attorney ship Improvement of the cooperation between the MoJ and the BRM in connection with the content and practical application of the legal fees. Enforcement Amendments on the Law on enforcement and new enforcement tariffs with cost reduction adopted. Notary ship Amendments on Law on Notary and new notary tariffs with cost reduction adopted. Mediation Increased Number of cases resolved through mediation. 319 cases were solved with mediation in 2020. Electronic register system for mediators was introduced. Criminal New Criminal Code, New Law on Criminal Procedure, New Law on special state fund for compensation of victims of crimes, New Law on Children justice and a new Law on international cooperation in criminal matters are in the final stage of preparation. Administrative Adopted new Law on administrative disputes. ICT There is a new ICT organization in the judiciary. The new Law on Courts introduced the establishment of a Council for Information and Communication Technology in the judiciary, primarily as a coordinating function of ICT policies in the judiciary.

Administrative Capacity: The institutional set-up is largely in place. In 2019, within the project "Increased Effectiveness in Delivering Justice through Improving the Performance of Judicial Institutions" implemented by the Centre for Legal Research and Analysis (CPIA) and PwC Macedonia, funded by the Good Governance Fund, United Kingdom, Government prepared 3 functional analyses: - Functional Analysis of the Public Prosecutor's System in the Republic of North Macedonia, - Functional Analysis for the Supreme Court of the Republic of North Macedonia, - Functional Analysis of the Courts of Appeal in the Republic of North Macedonia. Further support for the implementation of the Strategy was provided by the IPA 2015 EUIF project “Support the Justice Sector Reform Process” completed in January 2021. With the expert support, the human resources strategy for the judicial network and the human resources strategy for the prosecutorial network were developed. In 2021, a functional analysis for 27 basic courts will be prepared. The established probation offices in 9 cities (Skopje, Kumanovo, Tetovo, Bitola, Shtip, Veles, Strumica, Ohrid, and Prilep) are operational and work on probation cases. 30 probation officers are working now in the probation offices in the country. Investigation centres have been established. On 7 February 2020, the Public Prosecutor of the Republic of North Macedonia adopted a Decision on Selection of Investigators in the Investigative Centres in the Basic PPO for Organized Crime and Corruption, the Basic PPO Skopje, the Basic PPO Tetovo, and the Basic PPO Kumanovo. The candidates were selected based on an internal announcement issued by the MoI and the Financial Police. Five investigators have been selected in the Basic PPO for Organized Crime and Corruption, 7 investigators have been selected in the PPO Skopje, 2 investigators in the PPO Tetovo and 2 investigators in the PPO Kumanovo. The selected investigators started performing their duties in the investigation centres as of 01.03.2020. On 7 February 2020, the Public Prosecutor of the Republic of North Macedonia adopted a Rulebook on organization and manner of operation in the investigation centres.

Performance: With the support of the IPA 2014 EU Integration Facility “Support for the management of EU funds projects”, during 2020, it was put in place the Performance Assessment Framework (PAF), to support the monitoring process of the sector reforms, including Justice (https://pafnorthmacedonia.mk/PAF/).

Budget: There is a budget of 6,000,000 EUR for the implementation of the Strategy for the reform of the judicial system and the Action Plan for 2017-2022. There is no sectoral budget since numerous institutions that are under different branches of power administer the justice sector.

Under indirect management by RoNM:

- OS(s) in place and related changes, if relevant:

Operational Agreement for the Country Action programme for 2014 was signed between NIPAC, HOS and IPA Coordinator, no. 10-2689/2 on 06.07.2017. According to the Act of Systematization and Organization of the Ministry of Justice (Ref.No.01-2162/2 as of 19.06.2015), the EU Department within the Ministry of Justice is divided into two Units - EU Negotiation and Integration Unit and the Unit for IPA Projects (IPA Unit). OS within the Ministry of Justice includes four (4) employees:

The designated IPA Coordinator is the Head of Department for European Union.

Three employees in IPA Unit appointed as Head of IPA Unit, Advisor as Programming Officer, and Junior Associate as Monitoring Officer. In 2020 there were changes in the OS. One (1) person who was employed as advisor for Technical Implementation leave the job position. The results of the WLA for 2021 indicated that the optimal number of staff needed is 7, including the SPO/IPA coordinator who is the Head of the EU Department.  According the WLA for 2021, an employment of three additional employees in IPA unit is needed. (One High monitoring officer, one advisor for Technical implementation and one junior associate for TI).

- Information on the implementation of Action programmes under indirect management in the sector

Under IPA II Action Programme 2014 for Justice sector, by 23.12.2018 total of 18 projects/contracts, were contracted in amount of 7.937.370,76 EUR (IPA contribution 6.855.747 EUR and national co-financing 1.081.624 EUR).

- Service Framework contract: "Preparation of works tender dossier for construction/reconstruction of Public Prosecutor’s Offices countrywide “contracted in amount of 190.570,00 EUR.

- Service Framework contract:  "Preparation of works tender dossier for reconstruction of prison Bitola and courtroom facility in Prison Shuto Orizari" contracted in amount of 153.450,00 EUR.

- Service Framework contract: "Preparation of Technical Specification for supply of ICT for the Justice Sector Institutions" contracted in amount of 158.100,00 EUR.

- Service Framework contract: "Technical assistance for the Evaluation Committee for the Grant Scheme (assessors)" contracted in amount of 44.045,00 EUR:

- Twining: "MK 14 IPA JH 02 18 - Strengthening of the penitentiary system and the probation service" contracted in amount of 950.000,00 EUR.

- Twining Light: "Strengthening the capacities of the authorized bodies for fight against crime" contracted in amount of 250.000,00 EUR.

- Service (supervision) (Competitive negotiated procedure): "Supervision of works for construction of the court room in prison Idrizovo - Skopje and reconstruction of prison in Bitola" contracted in amount of 212.000,00 EUR.

- Service (supervision) (Competitive negotiated procedure): " Service contract for supervision of works for construction/reconstruction of PPOs" contracted in amount 154.670,00 EUR.

- Grant: "Strengthening the Impact of the Civil Society in Effective Justice Sector Reforms" contracted in amount of 1.017,319,02 EUR.

- "Supply of specialized vehicle (van) for transportation of convicted/detained persons" contracted in amount of 98.610,00 EUR.

- "Supply of equipment (office furniture) for Public Prosecutor’s Offices countrywide and PPO for organised crime and Ministry of Justice" contracted in amount of 214.495,00 EUR.

- Supply contract (International open procedure): " -Supply of ICT of relevant justice sector institutions ICT in the penitentiary and probation system" - LOT 2, contracted in amount 778.870,00 EUR.

- Supply contract (International open procedure): " Supply of relevant justice sector institutions " – LOT 3, contracted in amount of 98.810,00 EUR.

- Supply contract (International open procedure): " -Supply for relevant justice sector institutions, " - LOT 4, contracted in amount of 297.078,00 EUR.

- Works’ contract (Local open tender): " Works for construction/reconstruction of PPOs" - LOT 1, contracted in amount of 585.751,19 EUR;

- Works’ contract (Local open tender): " Works for construction/reconstruction of PPOs" - LOT 2, contracted in amount of 498.490,84 EUR;

- Works’ contract (Local open procedure): " Works for reconstruction of Prison Bitola and Court Room facility in Prison Idrizovo-Skopje" - LOT 1, contracted in amount of 1.257.517,09 EUR.

- Works’ contract (Local open procedure): " -Works for reconstruction of Prison Bitola and Court Room facility in Prison Idrizovo-Skopje" - LOT 2, contracted in amount of 977.588,62 EUR.

Two (2) Tender procedures/Contracts under IPA II (2014-2020) in total amount of 5.176.150,00 EUR were cancelled:

- Service contract (International Restricted procedure): "Support to Justice Sector and Reform Process" and

- Supply contract (International open procedure): "Supply for Upgrade of ICT infrastructure, interconnection of relevant justice sector institutions, E-services and databases/develop of the ICT in the penitentiary and probation system" - LOT 1.

- Main achievements in the sector

The main achievements in the sector that are connected to the implementation of projects under indirect management are presented in the table below.

| Contract title | Status | Expected result | Achieved results |
| --- | --- | --- | --- |
| 1.Service Framework contract: "Preparation of works tender dossier for construction/reconstruction of Public Prosecutor’s Offices countrywide”. IPA/AP2014/2.3JUS/LOT2/24 | Completed | Needs Assessment Report (NAR) of the 21 Basic Public Prosecutor’s Offices, presenting the key findings of the current situation. Preparation and compilation of Detailed Design and tender dossier according to PRAG. | All expected results fully achieved. |
| 2.Service Framework contract: "Preparation of works tender dossier for reconstruction of prison Bitola and courtroom facility in Prison Shuto Orizari" IPA/AP2014/2.3JUS/LOT2/23 | Completed | Detailed assessment of current situation and preparation of scope of work in the prison Bitola and courtroom facility in Prison Skopje prepared. Preparation and compilation of the works tender dossier (volume 3, 4 and 5) according to PRAG procedures. | All expected results fully achieved. |
| 3.Service Framework contract: "Preparation of Technical Specification for supply of ICT for the Justice Sector Institutions" IPA/AP2014/2.3JUS/Lot7/17 | Completed | Prepared Report presenting initial review and verification of status. Prepared Action Plan for the implementation of the Strategy. Prepared Technical Specification/s, market studies and indicative cost estimation in accordance with PRAG regulations for the supply of equipment for the Justice Sector Institutions. | All expected results fully achieved. |
| 4.Service Framework contract: "Technical assistance for the Evaluation Committee for the Grant Scheme (assessors)" IPA/AP2014/2.3JUS/Lot7/18 | Completed | Assistance to the Contracting Authority in selecting the best-quality Concept Notes and Full Application proposals for the Restricted Call for Proposals for IPA II 2014 Grant Scheme | All expected results fully achieved |
| 5.”Supply of Integrated Penitentiary Management System for DES”-LOT 2 | Completed. Warranty period started on 15.05.2020 and will end on the date of issuance of Final Acceptance Certificate, i.e. 15th May 2021 | -Renewal of the ICT hardware and infrastructure and development of new information system – IPMS for DES - To cover the business processes and information flow that will allow DES to perform supervision over the PCIs. -Project initiation and planning completed on 31/03/2019 -Analysis and Design phase completed on 30/05/2019 -Customization and development of new functionalities (Delivery and Installation) 26/11/2019 - Testing and verification (testing of the hardware and software) completed on 25/12/2019 -Deliverables concerning the hardware component, delivery and installations, and the test version were successfully implemented. -Hardware testing for the centralized solution testing completed on 17/12/2019. - Finalization of testing set for 24/12/2019.Following the finalization of testing, team prepared final training list for end users of the new solution including user-manuals. Training of Trainers for 15 key users conducted in December 2019. End-User training commenced in January and finished with System administrator roles and management of the system by the DES on 26/02. Although in line with the Administrative Order No.1, issued by Contracting Authority (Letter Ref.No.12-1302/1 as of 08th February 2020) the end date of the implementation period i.e. date of issuance of Provisional acceptance Certificate was 29.02.2020, due to the Statement for impossibility of proceeding with PAC caused by the COVID-19, the period for Provisional acceptance was extended till 16th May 2020. | All expected results fully achieved |
| 6.” Supply of Integrated Information Management System for the Council of Public Prosecutors" LOT 3 | Completed Provisional Acceptance Certificate was issued on 24.02. 2020.warranty period expire on 24th February 2021 Final Acceptance Certificate shall be issued within 30 days after expiration of the warranty period I e24th March 2021 latest. | Delivered and installed the equipment for Integrated Information Management System in the Council of Public Prosecutors starting with the process of their digitalization, then registering the documents in specific books and processing them among employees. Delivery of training materials. | All expected results fully achieved. |
| 7.” Supply of ICT for justice Sector institutions" LOT 4 | Completed | Delivered and installed ICT equipment (PC, Servers, storage, etc.) on 4 (four) locations: Supreme Court, Public Prosecutor Office, Ministry of Justice, Academy for judges and public prosecutors Personal Computer 107 Server Type 1 5 Server Type 2 (Backup Server) 1 Storage Solution 2 FC Switch 1 Network Switch 10 Server Rack UPS 2 PC UPS 50 Web Oriented Mail Server Software Solution 1 Backup Solution 1 Video monitoring system for server room 1 Projection Screen 1 Videoconferencing solution 1 Interactive whiteboards 2 Audio mixer 2 Interpretation equipment 1 Server room Air conditioning unit 2 | All expected results fully achieved |
| 8.Twining “Strengthening of the penitentiary system and the probation service" | Due to the situation caused by COVID-19 virus considered as a force majeure and the occurred obstacles in the performance of the activities as per the Contract, the project was suspended. on 29.04.2020, The suspension was lifted in December 2020 the implementation will continue until 6th of April 2021. | The project started with its implementation on 31st August 2018 when the Resident Twinning Advisor according to the twinning contract arrived at the BC. Kick off Meeting was held on 21.11.2018. Up to 11.03.2020 were held 7 Steering committees. “Performance Evaluation system (PES)” introduced; training of trainers’ workshop and exemplary study in a pilot prison conducted. The standards developed for measuring employees’ performance under agreed criteria (KPIs, job descriptions) with the BC. A network of collaborators and a Contact List of all institutions involved in the execution of probation works have been established. Individual memoranda of understanding between DIS and the City of Skopje, the Municipality of Bitola, the Municipality of Stip and public enterprises that operate in these municipalities were signed. Established cooperation with the Academy for Training of Judges and Prosecutors, focus is on delivering trainings for probation officers, judges, public prosecutors, employees of the MoI and the Centers for Social Work. Trainings of probation officers on the application of the risk assessment instrument, preparation of probation reports and execution of probation works are continuously held. Specialized staff in implementing video surveillance supervision trained. Total number of workshops is 60 (31 for prison officers and 29 for probation officers). Total number of trained judges, prosecutors, professional associates is 101. |  |
| 9.” Supervision of works for adaptation/refurbishing of basic publlic prosecution offices” | Ongoing | Supervision service of quality control, control of quantities, supervision of the work progress, analyses of expenses as well as working on administrative questions during the construction and the defect liability period. After the construction period is completed, the 12 months Defect Liability Period begins. In case of incidental damages, the Supervisor will inspect the construction and start with preparation of the Workplan for organizing incidental missions. |  |
| 10.” Works for adaptation/refurbishing of BPPO’s” -LOT 1 | Completed. | Basic public prosecution offices in Veles, Kumanovo, Shtip, Kochani and Strumica are refurbished; the working conditions are improved in line with EU and international standards. | All expected results fully achieved |
| 11.” Works for adaptation/refurbishing of BPPOs” LOT 2 | Completed | BPPO’sinTetovo, Kavadarci, Ohrid, Kumanovo, Kocani, Veles Shtip are refurbished ; the working conditions are improved in line with EU and international standards. | All expected results fully achieved |
| 12.Works for construction of the court room in prison Idrizovo - Skopje and reconstruction of prison in Bitola LOT 1 | Completed. Warranty period expires on 28.02.2021. | Construction of Court Room facility in Prison Idrizovo-Skopje will enable the trials of the detained persons for serious crimes to take place within the area of the Prison Idrizovo. Within the warranty period First visit on the Courtroom was made in June 2020, for which a report was submitted by the supervisory body within the warranty period. The next visits: September, December and the last one with the end of the warranty period - the end of February. | All expected results fully achieved |
| 13.Works for construction of the court room in prison Idrizovo - Skopje and reconstruction of prison in Bitola LOT 2 | Completed. Warranty period expires on April 21, 2021. | Reconstruction of the Prison in Bitola on an area of 2300m²), to improve the prison system and the conditions for detained and convicted persons in accordance with European standards. First visit within the warranty period was made in July 2020, for which a report was submitted by the supervisory body within the warranty period. The next visits for the Prison in Bitola are planned for October, January and the last one with the end of the guarantee period - April. | All expected results fully achieved |
| 14."Supervision of works for construction of the court room in prison Idrizovo - Skopje and reconstruction of prison in Bitola | Ongoing The Supervision Contract expires on 21.04.2021. | The contractor ensures that services for supervision of the construction works are in accordance with all the requirements for quality control, control of quantities, supervision of the work progress, analyses of expenses as well as working on administrative questions during the construction and the defect liability period. |  |
| 15.Twining Light: "Strengthening the capacities of the authorized bodies for fight against crime" | Completed. 8 months (10 months with a suspension of 2 months) Project start: 23 January 2019 Project end: 22 November 2019 | Project Steering Committees The Project Steering Committee (PSC) Meetings took place three times:1st PSC Meeting was held on 1 April 2019, the 2nd PSC Meeting on 27 June 2019 and the3rd PSC Meeting on 21 November 2019. Project Components All missions of Component 1 and 2 completed. A final conference was held on 22 November 2019 as an – internal – wrap-up eventduring which German experts gave short presentations about the project and special investigativemeasures with special emphasis on financial investigations and discussed their experiencewith colleagues from all beneficiary institutions. Outcomes - a comprehensive list of recommendations resulting from assessments of a largenumber of legal provisions including aspects of data protection in the field of specialinvestigative measures, - a list of recommendations concerning the enhancement of cooperation between thevarious BC institutions involved in special investigative measures, including a systemfor statistical data collection and performance management - a training needs assessment, - a training curriculum for Public Prosecutors and staff members of all BC institutions, - the successful preparation of in total ten prosecutors (eight from Basic PPO forCombating Organized Crime and Corruption and two from Basic PPO Skopje) toact as trainers in trainings, workshops and on the job support in the field of specialinvestigative measures, - a number of ten trainings successfully delivered by these trainers for Public Prosecutorsand staff members of the other BC institutions with supervision and coachingby MS experts. - recommendation about the collection of statistical data in the field of special investigativemeasures and performance management, - recommendation about communication between relevant authorities to implementspecial investigative measures more efficient and effective. | All expected results fully achieved |
| 16.“Supply of specialized vehicle (van) for transportation of convicted/detained persons" | Completed | Supply of 3 (three) specialized vehicle for transportation of convicted/detained persons for Directorate for execution of sanctions. | All expected results fully achieved |
| 17."Supply of equipment (office furniture) for Public Prosecutor’s Offices countrywide and PPO for organised crime and MoJ" | Partial Provisional Acceptance signed | Supply, delivery, unloading, installation and putting into operation of office furniture to the 11 Public Prosecutor’s Offices countrywide (Tetovo, Gostivar, Kichevo Ohrid, Bitola, Kavadarci, Veles, Kumanovo, Stip, Kocani, Strumica), PPO for organised crime and Ministry of Justice. Office Desk 318 Executive Office Desk 29 Small Office Desk 113 Small Office Table 17 Conference Room Table 9 Staff meeting Conference Room Table 1 Mobile Pedestal 378 Office Chair 457 Conference Chair 199 Metal Storage Cabinet 308 Wood Storage Cabinet 65 Metal Storage Rack 20 | All expected results fully achieved. |
| 18. Grant Contract: Strengthening the Impact of the Civil Society in Effective Justice Sector Reforms” | On-going | Six grant contracts were signed within this programme. Each grant contract addresses one issue related to the involvement of the Civil Society in the Justice Sector. The grant contracts are under implementation. Grant Contract NRC: “Strengthening the Access to Free Legal Aid by Roma and other Vulnerable Groups. Grant Contract IHR: “Joint involvement for better performance of judiciary” Grant Contract ADI: “Monitoring and improvement of the institutions' s capacity for fighting organized crime and corruption. Grant Contract EPI & Zenith: “Partnership Justitia: Regaining Citizens’ Trust” Grant contract MYLA:” Legal support service for vulnerable victims of violent crimeGrant Contract FLOROZON: “Equal Access for Effective Justice” |  |

- Recommendations for further actions

The main recommendations according to the last Monitoring Committee (MC), held on the14.10.2020, are as follows:

- The national authorities shall increase the administrative capacity by 1) adopting staff retention policy for the IPA structures; 2) providing sufficient number of staff; 3) put in place a strategy for ensuring the training of the IPA structures and strengthening the IPA training function (participation in trainings and workshops organized under IPA projects must be promoted by high management to staff); and 4) spreading best practice established in the management of the EU assistance into the whole of the public administration, until next IPA MC meeting.

- Sustainability of EU projects remains a persistent problem. The country's commitment to make use of the outputs and results of IPA projects, to maintain the delivered infrastructure facilities and to put in use the developed IT systems, needs to be strengthened.  National authorities must regularly monitor how sustainability issues are being addressed. In case projects' outputs are not used, financial corrections should be applied by NAO to the end beneficiaries. Implement the recommendations and outputs from the IPA project supporting NAO with due attention on adoption of the IPA II Decree, the Guidelines for final beneficiaries, as well as the Agreement for transfer of ownership by the end of 2020.

- The outstanding conclusions from the previous IPA MC must be addressed as a matter of priority.

- Address the Audit Authority's and other audit findings and recommendations, within the deadline agreed between the auditors and the auditees. Continuously decrease the open findings in follow-up audits.

- Procedures for direct management have been drafted with support of IPA funds. Adopt and put into implementation the procedures by the end of 2020.

- The State Commission for Prevention of Corruption to provide information on the functionality of IT equipment procured under IPA 2013 LOT 1, by end of October 2020.

- The Line institutions in cooperation with NIPAC office to ensure timely circulation of supporting documents for the Sector Working Groups meetings.

# Rule of Law and Fundamental Rights – Sub sector Home Affairs

- Involvement in programming

So far, five IPA Action Documents were prepared. Two were financed under IPA 2014, one was financed under IPA 2016 and two were financed under IPA 2020. The ADs financed under IPA 2020 addressed the fight against organised crime and terrorism (one result within one AD in common with Justice – Please refer to the description provided in the chapter Involvement in programming under Sub sector Justice) and migration and border management.

The main features of the IPA AD 2020 on Migration are as follows:

Overall Objective: To strengthen border and migration capabilities of the national authorities including combatting and preventing migrant smuggling and human trafficking in line with international standards.

Specific Objective: To enhance the operational capacity of the border police and improve the border and migration management capacities and assistance of the Transit Reception Centres.

Results:

- Strengthened operational capacity of border police authorities (including guest borders guards) in North Macedonia to carry out border control, in line with EU standards.

- Improved management and capacity of the border control migration flows, including registration and identification of new arrivals, in line with EU standards Improved independence, accountability, quality and effectiveness of the justice system.

Total cost: 4,000,000 EUR

EU Contribution: 4,000,000EUR

Indirect management with the International Organisation of Migration (IOM).

In the first half of 2020, the Home Affairs sector started working on activities regarding the IPA III programming process. As part of this process, several meetings on a technical level and two plenary sessions were held. On 1st of June 2020 a technical coordination meeting was held with the members of the SWG Home Affairs and other members to be acquainted with the programming process and the activities planned. The first plenary session of the SWG Home Affairs was held on 29.06.2020 and was chaired by the Minister of Interior. The aim of this session was the presentation of project proposals for funding under the IPA III programme. Before this plenary session, the members of this SWG had several meetings on a technical level. As a result of these meetings, two proposals were prepared and presented during the plenary session, one for the area fight against organised crime/ security and the second for migration and border management.

During the second half of 2020, the activities of the SWG Home Affairs were dedicated to the preparation of Strategic Responses for the thematic areas organised crime/security and migration and border management. Several consultative meetings were organised with the different institutions in order to prepare these documents. The Strategic Reponses were presented during the second plenary session held on 18.12.2020 and chaired by the Minister.

As a result of the continuous activities in the IPA III programming process, the following documents were prepared:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 1 – Rule of law and Fundamental Rights, Thematic Priority 3: Fight against organised crime / security and Thematic Priority 4: Migration and border management | EU for organised crime/security EU for migration and border management | EU against organised crime, in support of trade and human rights |

The Action Documents will contribute to achieve the Specific Objectives of Window 1 Thematic Priority 4.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

| Strategic Planning | Self-assessment: Half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| --- | --- |
| Administrative Capacity | Self-assessment: Less than half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Coordination | Self-assessment: Half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Performance | Self-assessment: Less than half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Budget | Self-assessment: Less than half of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Remarks: Progress has been made in two of the criteria related to strategic planning and coordination. There is still place for improvement in the area. For the criterion “Budget”, the Ministry is in the same situation of all the other ministries; it is necessary to wait for an input from the Ministry of Finance. |

- Coordination with other instruments and/or donors/ IFI's within the sector

Considering the presence of many donors in the sector, the Government has made efforts through the Programme Based Approach (PBA) “Home Affairs” Sub-Sector Working Group to ensure efficient donor coordination to avoid possible overlapping and alignment with the national priorities, which can be further enhanced and supported. The Ministry of Interior is the leading institution for the HA Working group consisted of representatives from Ministry of Finance, Financial Police Office, PPO, Ministry of Justice, Financial Intelligence Office, Customs Administration, Secretariat for European Affairs, and other institutions if necessary, and the representatives from the donor community: EU, UNDP, UK, USAID, IOM, UNHCR and CSOs.

The following meetings of the SWGs were organised in 2020:

| PLENARY SESSION |
| --- |
| Date | Number of participants | Discussed topics |
| 29.06.2020 | 24 participants | IPA III programming |
| 18.12.2020 | 50 participants | Strategic Responses |
| THEMATIC SESSION |
| Date | Number of participants | Discussed topics |
| 01.06.2020 | 22 participants | IPA III programming process |
| 09.06.2020 | 8 participants | IPA III programming process thematic area Asylum |
| 10.06.2020 | 6 participants | IPA III programming process thematic area Border Management |
| 10.06.2020 | 7 participants | IPA III programming process thematic area Organised Crime |
| 11.06.2020 | 13 participants | IPA III programming process thematic area Organised Crime |

The following donors, IFIs, Embassies and CSOs were present at these meetings:

| Donors | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| IOM |  | EU | Foundation Open Society Macedonia; |
| UNHCR |  |  | ZENIT; |
|  |  |  | European Political Institute – EPI |

At present, in the sector Home Affairs the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| Kingdom of Norway | Circa 1 million EUR | IBAS-system | 2009-still on going |
| UNHCR | Circa 50,000 EUR | IBAS-system | 2009-still on-going |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning, and budgeting

Strategic Planning: The monitoring of the strategies on Police development and on trafficking in human being and illegal migration is ongoing. During 2020, the Strategy for further capacity development of CSI units on regional and local level 2020-2025 and Action Plan have been prepared and officially approved by the Minister.

Administrative Capacity: Many institutions are involved in the Home affairs sector: Ministry of Finance – Customs, Financial Police, FIU; Public prosecution; Ministry of Health; Ministry of Labour and Social Policy, among other bodies. There is an insufficient number of staff in most of the institutions.

Performance: There is no progress made in 2020 in achieving the targets for this area. There is no Master Plan put in place so there is no possibility for reaching the targets. However, a comprehensive Performance Assessment Framework including the main relevant indicators was prepared and is available under PAF (pafnorthmacedonia.mk)

Budget: Still there is no unified methodology for costing of the implementation of the strategies. There is not multi-annual sector budget. There is no link between strategies, action plans and sector budgeting. There is a fragmented approach to budget elaboration and no appropriations of the various public sector institutions. The accomplishment of steps and targets of the roadmap in this area for 2020 is quite limited.

Under indirect management by RoM: IPA 2014

- OS(s) in place and related changes, if relevant:

The Operational Agreement for IPA II programme was signed in July 2016. This Agreement regulates the relations between the SEA as National IPA Coordinator, CFCD as contracting authority and the Ministry of Interior as beneficiary institution. This agreement applies only on actions part of the Country Action Programme for the year 2014. The organisation of the IPA Structure within the Ministry of Interior is in accordance with provisions given in the Operational Agreement and the Manual of Procedures for IPA II. At present, the structure of the IPA in the Ministry of the Interior is composed of 6 employees. (IPAC, Head of IPA Unit, two chief advisers for technical implementation and two advisers for monitoring).

- Information on the implementation of Action programmes under indirect management in the sector

# During 2020, one project under the IPA 2014 Action Programme, which is implemented under indirect management, was implemented in the Ministry of Interior. The supply contract “Supply of equipment for implementation of Business Continuity and Disaster Recovery System and modernization of the IT infrastructure in the MoI HQ” Lot 1: Supply of IT hardware, fibre optic cables and licenses for all systems with design development and training in two sites” (€ 5.391.211,78). The implementation started on the 28th of January 2019. It is still an ongoing project.

- Main achievements in the sector

| Contract title | Status | Expected result | Achieved results |
| --- | --- | --- | --- |
| Supply contract ,, Supply of equipment for implementation of Business Continuity and Disaster Recovery System and modernization of the IT infrastructure in the MoI HQ Lot 1: Supply of IT hardware, fibre optic cables and licenses for all systems with design development and training in two sites -IPA 2014 | Ongoing | The subject of the contract is supply, delivery, unloading, installation, integration with the existing system, testing, commissioning and putting into operation of adequate technical equipment (hardware and software and HVAC) including training and design, development, migration and final roll-out of all systems for establishing of Business Continuity and Disaster Recovery Data Center of the Ministry of Interior (MoI). |  |

- Recommendations for further actions

The main recommendations related to Home Affairs sector according to the last Sectoral Monitoring Committee Meeting on rule of law and fundamental rights held on the 21st of October 2020 are as follows:

- SEA, Ministry of Justice and Ministry of Interior to organize monthly progress review meetings with the Operating Structure, NIPAC Office, CFCD and EUD on justice and home affairs ongoing projects to monitor the implementation of IPA 2014, 2016 and 2020 contracts/projects. SEA to invite the relevant stakeholders depending on the needs and issues subject of discussion. Start from November 2020.

- Project Establishment of Business Continuity and Disaster recovery data centre funded under IPA 2014. The Ministry of Interior will complete the works necessary to accommodate the optical cable by end-June 2021 and will provide for timely and smooth finalisation of the supply contract.

The Ministry of Interior has conducted the procurement, ie the tender procedure is completely completed and a framework agreement has been concluded with an economic operator. The holder of the procurement is required to prepare a revised design within 30 days according to the contract order, and after the preparation of the revised design within 180 days to perform the construction works.

- Project Construction works of the new Reception Centre for Foreigners in Skopje under IPA 2016 - provide the construction permit by 26 October 2020.

The Building Permit for the for the construction of the New Reception Centre for foreigners issued on 24.12.2020 by the Ministry of transport and communications.

- Integrated Border Management strategy to be prepared by end-December 2020 and adopted by end-January 2021.

The process is ongoing.

- Ministry of Justice and Ministry of Interior in cooperation with NIPAC office (in SEA) to ensure the supporting materials for the Sector working groups meetings to be circulated 5(five working days) before the date of the meeting.

The Ministry of Interior with the support of NIPAC office (in SEA) is circulating the supporting materials for the Sector working groups meetings in accordance with the deadlines.

# II a. Performance indicators in the sector Rule of law and Fundamental Rights covering both direct and indirect management

Indicators per programme

| Financing Agreement/Programme reference | Indicator for sector Rule of law and Fundamental Rights | Source | Baseline | Milestone (2017) | Target (2020) and 2023 for IPA 2020 | Final target (Year) and 2025 for IPA 2020 | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP indicator | Composite indicator (Access to Justice (WJP) and Judicial Independence (WEF) | Elaboration of the EU Commission WJPWEF | 46.8 (2012) | 55.00 | 58.86 |  | 0.54 and NA | NA and NA | 0,53 (WJP) 2,3 (WEF) | 0,54 (WJP) 2,4 (WEF) | 0,53 (WJP) NA |
| CSP indicator | Composite indicators Global Corruption (TI) and Control of Corruption (WB) | Elaboration of the EU Commission Transparency International and WB | 48.83 (2010) | 56.00 | 58.00 |  | 37 and NA | 5 (CPI) | 37 (CPI) | 35 (CPI) | 35 (CPI) NA |
| CSP indicator | Composite indicator Freedom of Press (FH) and Press Freedom (RWB) | Elaboration of the EU Commission FH and RSF | 33.20 (2010) | 37.25 | 31.05 |  | (49.04) 62 and 36.09 | 64 and 35.74 | 59 and 32,43 | 31,66 (RSF) | NA 31,28 (RSF) |
| SUB SECTOR JUSTICE |  |
| IPA2014 /037-701.3 | 3. Degree of implementation of the national strategy on justice in % | Ministry of Justice / EC Progress Report; | 0 (2014) | 10 | 60 | 100 (2022) | 0 | 0 | 10 | Around 50%. | Around 60%. |
| IPA2014 /037-701.3 | 1. Justice sector reform adopted | Ministry of Justice | 0 (2015) | 1 | 1 | 1 (2022) | 0 | 1 | 1 | 1 | 1 |
| IPA2014 /037-701.3 | 5.Established strategic planning, research, analysis and monitoring units at the MOJ, JC, Supreme Court, appellate courts, CPP, PPO and a designated EU Law implementation body | Project monitoring report | Poor planning (2014) | Advancing | Advancing | Strong planning (2022) | Poor planning | Poor planning | Advancing | Advancing | Advancing |
| IPA2014 /037-701.3 | 2. Average level of public trust in the judiciary based on the standard CEPEJ satisfaction service of the court users |  | 0 (2016) | 3 | 4 | 5 (2025) | 0 | 0 | No data | No data | No data |
| IPA2014 /037-701.3 | 6. Number of violations d before the European Court of Human Rights under Art. 6 ECHR per year (separate figures for length of court proceedings/fair trial) | Annual Report of European Court of Human rights | Length of proceeding 1 (2014) fair trial 3 (2014) |  | Length of proceeding 1 (2014) fair trial 1 (2014) | Length of proceeding 0 (2022) fair trial 0 (2022) | Length of proceeding 1 fair trial 5 | Length of proceeding 2 Fair trial3 | Length of proceeding 0 Fair trial3 | Length of proceeding 1 Fair trial 3 | Length of proceeding 1 Fair trial 4 |
| IPA2014 /037-701.3 | 7. Degree of interoperability between justice sector institutions and other relevant authorities | Ministry of Justice | no interoperability (2014) | Advancing | Advancing | Interoperability established (2022) | No interoperability | on-going | On-going | Advancing | Advancing |
| IPA2014 /037-701.3 | 8. Legal and institutional framework to manage and coordinate ICT reforms in the justice sector created | Ministry of Justice | No Framework (2014) | Advancing | Advancing | Framework established (2022) | No framework | ICT Strategy adopted on 20.02.2018 | Changes in the Law on Courts for set up Council for ICT Coordination in Justice | Advancing. Adopted a Rulebook on the composition and manner of operation of the Council | Legal established and Institutional on-going. |
| IPA2014 /037-701.3 | 9. Level of operationalization of Investigative Centre(s) within the Public Prosecution Office | Ministry of justice | Investigative centre established, but not operational (2013) | Improved | Investigative centre(s) fully operational | Investigative centre(s) fully operational (2022) |  | on-going | on-going | on-going | Four investigative centres established. |
| IPA2014 /037-701.3 | 10. Fully operational probation service | Ministry of Justice | No probation service (2013) | Advancement | Advancement | Fully operational (2022) |  | on-going | Fully operational | Fully operational | Fully operational |
| IPA2014 /037-701.3 | 11. Bitola prison reconstruction | Ministry of Justice | 0 (2013) | 0 | 1 | 1 (2022) | 0 | 1 | 1 | To be finished March 2020 | Completed |
| IPA2014 /037-701.3 | 4. Level of satisfaction with the state of administration of justice by way of user satisfaction surveys at the end of Action implementation | Ministry of Justice | 0 (2014) 0 | 30% | 50% | 70% (2022) | 0 | 0 | No data | Average grade of the perception for the judiciary is 2.5/5 | We don’t have conducted surveys in 2020 |
| SUB SECTOR HOME AFFAIRS |
| Financing Agreement/ Programme reference | Indicator for sector Rule of law and Fundamental Rights | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value 2020 |
| IPA/2014/037-701.5 | 1. (Adoption of the) Strategy for Forensic Department Development and Action plan for its implementation | Progress Report Monitoring Report Project Report | There is no Strategy for Forensic Department Development and Action plan in place (2010) | Strategy and Action Plan adopted | Strategy and Action Plan adopted | Strategy and Action Plan adopted (2020) | 0 |  |  | N/A | Strategy and Action Plan adopted |
| IPA/2014/037-701.5 | 2. % of the staff engaged in Crime scene investigation | Project report | 0 | 50 | 100 | 100 (2020) | 0 | NA | NA | N/A | N/A |
| IPA/2014/037-701.5 | 3. 100% of the evidence detected and recovered from the crime scene is properly secured, packed, and distributed to the laboratories in the Forensic department | Monitoring report | 0 | 80 | 100 | 100 (2020) | 0 | NA | NA | N/A | N/A |
| IPA/2014/037-701.5 | 4. Increased number of investigations initiated. | Ministry of Interior | 110 | 105 | 110 | 110 (2020) |  | NA | NA | N/A | N/A |
| IPA/2014/037-701.5 | 5. Revised structure of the Forensic Department at central regional and local level adopted; | Project data | Reorganisation of the Forensic Department at central, regional, and local level in place. | Reorganisation initiated | Reorganisation completed | Fully operational (2022) |  | NA | NA | N/A | N/A |
| IPA/2014/037-701.5 | 6. Average duration of criminal investigations | Ministry of Interior | 100 | 95 | 90 | 90 (2020) |  | NA | NA | N/A | N/A |
| IPA/2014/037-701.5 | 7. Number of investigations concluded | Ministry of Interior | 100 | 110 | 115 | 115 (2020) |  | NA | NA | N/A | N/A |
| IPA/2014/037-701.4 | 1. % of employee trained | Ministry of Interior | 40 | 40 | 40 | 40 (2020) |  | NA | NA | N/A | N/A |
| IPA/2014/037-701.4 | 2. Information systems developed and installed for border control, fully compatible with Schengen Information System | Project Report | 1 | 0 | 1 | 1 (2022) |  | 0 | 0 | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 16. Number of joint investigations (raising trend) | National Authorities | 10 (2016) |  | 50 | 50 (2020) |  | NA | NA | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 15. Degree/level of implementation of the national anti-terrorism strategy (% of implemented measures) | National Authorities | 15 (2016) |  | 100 | 100 |  | NA | NA | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 14. Emergency call 112 in operation - No of calls and % of emergency calls | National Authorities | 0 (2016) |  | 100000 | 100000 | 0 | 0 | 0 | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 13. No of direct beneficiaries | National Authorities | 0 (2016) |  | 500000 | 500000 | 0 | 0 | 0 | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 12. No of persons serviced by the reception centre | National Authorities | 0 (2016) |  | 150 | 150 | 0 | 0 | 0 | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 11. Country fully covered by Tetra IV | National Authorities | 80 (2016) |  | 100 | 100 |  |  |  | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 10. Number of people trained | National Authorities | 0 (2016) |  | 1200 | 1200 | 0 | 0 | 0 | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 9. No of legal texts developed and adopted in line with the "better regulation" approach, | National Authorities | 0 (2016) |  | 3 | 3 | 0 | 0 | 0 | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 8. 112 emergency call operations smoothly | National Authorities | 0 (2016) |  | 100 | 100 |  | 0 | 0 | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 7. Increase in the requests for services and of the completed request for services (Forensic laboratory) |  | 10205 (2016) |  | 12000 | 12000 |  |  |  | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 6. Number of resolved cases based on efficient exchange of information and joint investigation. - of them No of cases benefiting women or vulnerable groups | National Authorities | 100 (2016) |  | 125 | 125 |  |  |  | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 5. Number of migrants / asylum seekers / victims of human trafficking who are not treated in line with the international standards | IOM | 5 (2016) |  | 3 | 0 (2022) |  |  | NA | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 4. Improved track record in the fight against illegal migration, trafficking in human beings, organised crime, terrorism and radicalization (number of investigated and completed cases) | National Authorities | 150 (2016) |  | 170 | 170 |  |  | NA | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 3. Level/degree of implementation of the recommendations of the Greta report | Greta report | 10 (2016) |  | 100 | 100 |  | NA | NA | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 2. Security of the citizens improved | UNDP Human Security Index | 81 (2014) |  | 70 | 66 | 82 | NA | NA | N/A | N/A |
| IPA 2016/039-618/02.02/MK/ | 1. Improved rule of law standard | Worldwide Governance Index (0 = lowest and 100 = highest) | 55.77 (2014) |  | 60 | 60 | 41.83 | 47 | NA | N/A | N/A |
| IPA 2020/041831.02 | Level of preparation of North Macedonia in dealing with migration related issues. | European Commission Report | Assessment at action entry and end |  |  | Quality assessment |  |  |  |  | Chapter 24: moderately prepared |
| IPA 2020/041831.02 | Enhance capacity to monitor migration flows; number of border checks, registration performed Number of refugees benefitting from assistance | Ministry of Interior Illegal and prevented illegal crossing for the period January - December – Department for Crime Intelligence and Analysis – Public Security Bureau |  |  |  |  |  |  |  |  |  |
| IPA 2020/041831.02 | Number of refugees benefitting from assistance | Ministry of Health, Ministry of Labour and social protection, International Organisation of Migration |  |  |  |  |  |  |  |  |  |
| IPA 2020/041831.02 | Number of working days of national border police officers spent on border (Sum of number of working days delivered by each redeployed border police officer per year) | Project report - | 4,380 working days (Southern border) |  | 4,380 working days (Southern border) | 4,380 working days (Southern border) |  |  |  |  |  |
| IPA 2020/041831.02 | Number of average days (per month) spent on border by guest borders guards | Project report - | 3000 presence days per month (2019) |  | 3000 presence days per month | 3000 presence days per month |  |  |  |  |  |
| IPA 2020/041831.02 | Number of hours training for border police officers (number of trained officers multiplied by the number of hours of training received by each trained officer). | Project report - | 1953 trained officers x hours/year (2018_) |  | 1953 trained officers x hours/year | 1953 trained officers x hours/year |  |  |  |  |  |
| IPA 2020/041831.02 | Number of specialised equipment for border surveillance and control and systems for registration of migrants | Project report - |  |  |  | Target will be decided at the time the Contribution Agreement contract will be prepared |  |  |  |  |  |
| IPA 2020/041831.02 | Number of migrants receiving assistance, including education assistance (number of migrants receiving assistance multiplied by the number of days migrant receive assistance). Indicator disaggregated: gender, adult, and children | Project report - | 10,522 migrants x days/year (76% male; 13% female; 11% children) (2018) |  | Around 10,000 migrants x days/year if the migration flows is like the present one. | Around 10,000 migrants x days/year if the migration flows is like the present one. |  |  |  |  |  |
| IPA 2020/041831.02 | Number of migrants receiving medical assistance (number of medical checks provided to migrants). Indicator disaggregated: gender, adult, and children | Project report - | 2,930 migrants/year (73% male; 14% female; 13% children) (2018) |  | Around 3,000 migrants/year if the migration flows is like the present one. | Around 3,000 migrants/year if the migration flows is like the present one. |  |  |  |  |  |
| IPA 2020/041831.02 | Number of migrants that want to return to their country of origin and supported in their request). Indicator disaggregated: gender, adult, and children | Project report - | 21 migrants/year (57% male; 14% female; 29% children) (2018) |  | Around 20 migrants/year if the migration flows is like the present one. | Around 20 migrants/year if the migration flows is like the present one. |  |  |  |  |  |
| SUB SECTORS JUSTICE AND HOME AFFAIRS |
| IPA 2020/041831.04 | Rule of Law Index (Global) | World Justice Report http://data.worldjusticepr oject.org/ | Score 0.54 Rank 56/126 (2019) |  | 0.60 | 0.65 |  | 0.53 | 0.53 | 0.54 | 0.53 |
| IPA 2020/041831.04 | Rule of Law Index (Fundamental Rights) | World Justice Report http://data.worldjusticeproj ect.org/ | Score 0.57 Rank 60 out of 126 (2019) |  | 0.60 | 0.62 |  | 0.54 | 0.54 | 0.57 | 0.59 |
| IPA 2020/041831.04 | Rule of Law / Worldwide Governance Indicator | World Bank (WB) | 47/100 (2017) |  | 50/100 | 55/100 |  | 46,63/100 | 43,75/100 | 46,15/100 | N/A |
| IPA 2020/041831.04 | Control of Corruption score / Worldwide Governance Indicator | World Bank (WB) | -0.31 (2017) |  | < -0.2 | < -0.1 |  | -0.31 | -0.36 | -0.41 | N/A |
| IPA 2020/041831.04 | Corruption Perception Index (points) | Transparency International Index (http://www.transparency.org) | 35 (2019) |  | 40 | 50 |  | (35) | (37) | (35) | 35 |
| IPA 2020/041831.04 | Freedom of the Press - Freedom House Index | Freedom House | 57 out of 100 (2017) |  | Positive trend | Max 55 |  | 57/100 | 58/100 | 59/100 | 63/100 |
| IPA 2020/041831.04 | Freedom of the Press – Reporters without Borders (RSF) | Reporters without Borders (RSF) | score 32.43 (2018) |  | Positive trend | Max 30 |  | N/A | Score 32.43 | Score 31.66 | Score 31.28 |
| IPA 2020/041831.04 | Progress made towards meeting accession criteria. Chapters 23 and 24 | European Commission Enlargement Country Report | Some level of preparation (2018) |  | Moderately prepared | Good level of preparation |  |  |  | 23. Some level of preparation/moderately prepared 24. Moderately prepared | 23. Some level of preparation/moderately prepared 24. Moderately prepared |
| IPA 2020/041831.04 | Implementation rate of Judicial Strategy 2017-2022 (% of targets met). | Report on the implementation of the Judicial Strategy and its Action Plan | < 10% (2018) |  | 100% | NA | 0 | 0 | 10 | Around 50% | Around 60% |
| IPA 2020/041831.04 | Number of key indicators on justice system being reported annually to the public | e-Justice system/Performance assessment framework | 0 (2018) |  | 10 | 15 |  |  |  |  | 16 |
| IPA 2020/041831.04 | Clearance rate of civil and commercial litigious cases | Judicial Council Statistical | 100% (2018) 111% (2018) |  | 110% (2018) 114% (2018) | 110% (2018) 114% (2018) |  |  |  |  | Civil - 95.53 Commercial 82.22 |
| IPA 2020/041831.04 | Disposition time of civil and commercial litigious cases | Judicial Council Statistical Report | 108 days (2018) 268 days (2018) |  | 90 days 220 days (2018) | 90 days 220 days (2018) |  |  |  |  | Civil –140.53 Commercial 462.25 |
| IPA 2020/041831.04 | Number of detected crimes asper SOCTA Threat Assessment (SOCTA) of 2012, developed by Europol | Organised crime statistical data, as per SOCTA Threat Assessment developed by Europol – MoI (Aggregated information) | 51 (2017) 12 |  |  | > 80 |  |  |  |  | NA |
| IPA 2020/041831.04 | Percentage of re-offenders versus total convicted. | Penitentiary statistics | 53% (2017) |  | < 53% | < 50% |  |  |  |  | On 31.12.2020 a total number of convicted persons in the prisons in RNM is 1870. From them 756 persons are re-offenders or 40,42%. |
| IPA 2020/041831.04 | Number of detected cases of corruption and conflict of interests by SCPC | Annual Report SCPC | 0 (2018) |  | 6 | 10 |  |  |  |  | Corruption cases In 2020, 406 applications were submitted to the SCPC and 12 cases were established on the own initiative by the SCPC or a total of 418 cases. In 2020 378 cases were resolved by the SCPC. SCPC submitted 11 Initiatives for determining the responsibility of managers and officials of the competent institutions. SCPC submitted 2 initiatives for initiating criminal prosecution of managers and officials to the Basic Public Prosecution Office. Conflict of interest’s cases 1. Total submitted applications - 80. 2. Open cases ex officio-6 3. Opinions requested from the SCPC and given opinion - 47. |
| IPA 2020/041831.04 | Number of cases where SCPC initiated misdemeanour procedure | Track record on corruption cases | 0 (2018) |  |  |  |  |  |  |  | In 2020, 96 misdemeanour payment orders were issued by the authorized officials in the SCPC. In 2020, 22 requests for initiating misdemeanour proceedings were submitted to the Misdemeanours Commission in the SCPC. |
| IPA 2020/041831.04 | Record of financial crime against public finances, payment operations and the economy (total number of reported perpetrators) | Annual report of judicial bodies including Skopje. Basic Court, Public Prosecutor for Prosecuting Organised crime and Corruption Annual reports of SCPC SSO, perpetrators of criminal offences report, T- 03 | 664 (2017) 13 |  |  |  |  |  |  |  | NA |
| IPA 2020/041831.04 | Enforcement record of the Unit for financial crime | Reports of the Unit for Financial Crime | 12/48/714 (2017) |  |  |  |  |  |  |  | NA |
| IPA 2020/041831.04 | Number of violations of human rights and freedoms | Ombudsman Annual Report | 1514 (2015) |  |  | < 500 |  | 1137 | 900 | 1219 | In 2020 a total of 622 violations of human rights and freedoms were ascertain by the Ombudsman office |
| IPA 2020/041831.04 | Number of violations of human rights and freedoms declared by the European Court of Human Rights. | ECHR Annual Report | 62% 21 out of 34 (2018) |  | Less than 60% | Less than 60% Positive trend |  |  |  |  | In 2020 the ECtHR delivered a total of 4 judgments against North Macedonia finding a violation of Article 6 (right to fair trail) of the ECHR. Violation of the "trial in reasonable time" requirement was found in only case(judgment). However a single decision based on a friendly settlement reached was delivered with respect to 20 applications concerning alleged excessive length of the domestic proceedings. |
| IPA 2020/041831.04 | Number of cases of domestic violence reported and number | National Statistical Institute | 656 |  | Trend | Trend |  |  |  | NA | NA |
| IPA 2020/041831.04 | Number of cases of sex offence reported (measured as number of perpetrators in Table T-01) (Crimes against Sexual freedom and sexual morality |  | 64 cases / 46 Investigations |  |  |  |  |  |  | NA | NA |
| IPA 2020/041831.04 | Number of judges and prosecutors benefiting of the EU support (cumulative for the different measures and sex disaggregated) | Project Report and administrative data | 3828 (2015) |  | > 5000 | N/A |  |  |  |  | NA |
| IPA 2020/041831.04 | Number of courts benefitting of peer support | Grant report | 0 (2019) |  | At least 7 | 10 |  |  |  |  | NA |
| IPA 2020/041831.04 | Number of inter-institutional joint operations to investigate. serious and organized crime (money laundering, cyber- related crimes, illicit drug trafficking and smuggling of migrants). | Statistical data of the MoI | Unknown |  |  | > 10 |  |  |  |  | NA |
| IPA 2020/041831.04 | Number of pronounced interim measures (freezing of assets). | Agency for management of confiscated property | < 10 |  |  | > 25 |  |  |  |  | NA |
| IPA 2020/041831.04 | Number of staff trained (sex disaggregated rank disaggregated between senior, middle management, executive level) for the suppression of serious and organized crime and terrorism | Grant report | Unknown |  |  | > 50 |  |  |  |  | NA |
| IPA 2020/041831.04 | Number of investigations conducted for violations of the requirements and big differences between assets and revenues. | Public Report of the SCPC | 0 (2018) |  | 100 | 150 |  |  |  |  | 3 investigations |
| IPA 2020/041831.04 | Number of irregularities/violations detected in asset declarations | Public Report of the SCPC | 0 |  | >10 | Trend should be reversed |  |  |  |  | 73 detected irregularities/violation |
| IPA 2020/041831.04 | Number of cases open by SCPC on the financing of political parties | Public Report of the SCPC | 0 |  | >2 | > 5 |  |  |  |  | In 2020 there were no cases for regular financing of the political parties open by the SCPC. |
| IPA 2020/041831.04 | Number of public procurement procedures analyzed by the SCPC | Report of the SCPC | 0 |  | >20 | > 30 |  |  |  |  | During 2020, the SCPC open and acted in 8 cases on applications from individuals and legal entities and 1 case on its own initiative with suspicions of illegalities / irregularities in public procurement procedures. |
| IPA 2020/041831.04 | Number of prisoners having. been transferred to new/refurbished facilities / %of the overall prison population (before the start of the project and at the end) from improved detention conditions (sex disaggregated) | Grant report | 0 (2018) |  | 0 | > 190 |  |  |  |  |  |
| IPA 2020/041831.04 | Number of prisoners involved in resocialisation activities. (Sex disaggregated) | Penitentiary statistics | 88 (2017) |  | > 200 | > 300 |  |  |  |  | During 2020, there were no prisoners involved in special treatment programs for resocialisation, but the convicts are included in the general treatment measures through regular programs, namely: 117 convicted persons in 2020 were working outside the institution. 67 convicted persons were included in Education programs for of convicts. 25 convicted persons were included in the specialized education programs for cooks and carpenters. |
| IPA 2020/041831.04 | Number of persons (police officers, prosecutors, judges, investigators, social worker -sex disaggregated) trained on fundamental rights, including on issues on gender equality | Grant report | Unknown |  | 30 | > 60 |  |  |  |  |  |
| IPA 2020/041831.04 | Number of cases processed by the Ombudsman and the anti- discrimination commission | Annual Reports of the Ombudsman and of the anti-discrimination Commission | OM - 3458 (2018) ADC – 0 (2018) |  | 4000 100 | 4000 150 |  |  |  |  | In 2020 to the Ombudsman office were submitted a total of 2448 complaints. From these, the procedure was stopped for 1872 complaints, in 88 cases a legal advice has been given and in 622 cases of violation were ascertain |
| IPA 2020/041831.04 | Number of cases of domestic violence reported and number of investigations leading to an indictment or a conviction | National Statistical office | 656 (2017) |  | < 600 | < 500 |  |  |  |  | NA |
| IPA 2020/041831.04 | MRT Radio & TV Rating, measured as percentage of population listening/watching. the radio and TV programmes of the public broadcaster (MRT) | Reports of the Agency for Audio-Visual Media Services | Radio - 3.1% TV – 14.4% (2018) |  | 8% 18% | 12% 20% |  |  |  |  | NA |
| IPA 2020/041831.04 | Number of journalists benefiting of enhanced social and economic protection | Project reports Reports of the Agency for Audio-Visual Media Services Report Independent Union of Journalists and Media Workers | 0 (2018) |  | 50 | 150 |  |  |  |  | NA |

# Democracy and Governance, Sub sectors PAR, PFM, and Union Programmes and EUIF

# Democracy and Governance, Sub sector PAR

  - Involvement in programming

In 2016, the IPA Action Document 2017 was elaborated. The main features of the Action Programme are as follows:

Overall Objective: To reform public administration in line with the Principles of Public Administration.

Specific Objectives:

- To optimise overall institutional framework, enhance public service delivery and strengthen ethics, integrity, transparency, and accountability of public administration.

- To improve the quality and availability of statistical data and enhance their use in development and coordination of public policies.

Results:

Result 1.1– Streamlined and optimised institutional framework.

Result 1.2 - Strengthened systems ensuring transparency, integrity, and ethics in the public institutions.

Result 1.3 – Improved delivery, quality, number, and scope of public services to citizens and to business (e-Government)

Result 2.1 – Improved alignment with the acquis in the field of macro-economic, business, and social statistics.

Result 2.2 –Capacity in production and dissemination of EU compliant statistics is strengthened.

EU Financial Support: 11.200.000 EUR

National Contribution: 257.000 EUR

Elaboration procedure: Programming of the IPA II 2017 took place in 2017 and the AD was adopted in January 2018. Following the adoption, the working groups started to prepare the tender dossiers as per the procurement plan and 5 out of 6 contracts are under implementation. One supply contract remains to be tendered as the technical documentation is an output from an ongoing service contract.

The SWG held consultation meeting with donors, NGOs and other partners and institutions relevant for implementation of the Strategy, as well as relevant stakeholders for assessing the performance in the sector...

In spring 2020, the programming of IPA III started. The main elaborated draft documents are as follows:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 2 – Good governance, acquis alignment, good neighbourly relations, and strategic communication (Thematic Priority 1: Good Governance) | EU for Modern Administration Good Governance | EU for Modern Public Administration |

The Action Document will contribute to improve the functioning of the Public Administration in North Macedonia.

In concrete, this Action will improve the organisation of the State Administration and its human resources, the ICT, the collection of statistical data related to Environment and Health, and the payment system in the national bank. Total value is 18.600.000 EUR where 18.000.000 EUR is EU financing. Most of the AD is proposed to be implemented under SBS.

  - Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented in order to fully implement the roadmap are summarised.

| Criteria: Strategic Planning | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| Criteria: Coordination | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reache |
| Criteria: Performance | Self-assessment: All targets for 2017, 2018, 2019 and 2020 have been achieved. |
| Criteria: Budget | Self-assessment: Half of the targets for 2017, 2018,2019 and 2020 have been reached. |
| Strategic planning: The Government on 21 February 2018 adopted PAR Strategy. Reporting mechanisms are defined in the strategy and in place. Two semi-annual and two Annual reports were submitted to the PAR Secretariat and adopted by the Government (annual reports only), as well as published on the MISA website together with all outputs deriving from the Strategy and other relevant documents. Administrative capacity: Resources of the institutions were adjusted to allow smooth coordination, implementation and monitoring of the PAR and the PAR Team sufficiently staffed. In the first year of implementation of the PAR Strategy this issue has been tackled through: Preparation of a manual for the role of the General Secretariat in the process of development and monitoring of policies. Analysis on the regulatory framework and practice related to planning documents, analysis on the strategies adopted and comparative analysis on the practices in the process of preparation of strategic documents. Recommendations for improvement of internal processes, functions, and human resources for strategic planning in the ministries and other state administrative bodies EC Progress report recognizes MISA efforts to improve the capacities for reporting, monitoring, and coordination of PAR Process. Horizontal functional reorganization project is under implementation and 4 draft laws on organization of state administrative bodies were prepared. The reorganization of the institutional structure should optimize the number of institutions and cause new functional reviews and systematizations as per new functions and roles of the institutions. Coordination: MISA has established good practices to ensure efficient sector and donor coordination. Continuous commitment is necessary to keep the achieved results and to ensure sustainability. Performance: In cooperation with the SEA project and EU Delegation, as well as following a discussion on a plenary session, a advanced version of the Performance Assessment Framework has been drafted and should be adopted by the Government. Budget: MISA took into consideration all activities and measures in the preparation of the budget. The same was approved by MF and adopted by the parliament. There is a still need to identify the source of funding for part of the activities. |

  - Coordination with other instruments and/or donors/ IFI's within the sector

The following meeting of the SWG was organised in 2020:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 30 June | 51 | Presentation of the draft Action Fiches |

The following donors, IFIs, Embassies and CSOs were present at these meetings.

| Donors and International Organisations | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| USAID | WB | EU Delegation | Open Society Foundation |
| UNDP |  | British | Centre for Change Management |
| UNOPS |  | German | European Policy Institute |
| UN WOMAN |  | Swiss | Institute for Democracy “Societas Civilis” Skopje |
| IRI |  | Bulgarian |  |
| UNICEF |  | Italian |  |

At present, in the sector PAR the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| British Embassy | 10m for all WB countries | “Schools of 21st century” is a project that aims to improve critical thinking skills, problem solving and coding skills of the Macedonian students. | 2018 - 2020 |

  - The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II has an impact in the sector either through the preparation of Action Programmes or through the implementation of TA projects or through the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning: With the collaboration of all key stakeholders and external technical support throughout the process, the Government approved the PAR Strategy 2018-2022 in February 2018. First annual report was published in May 2019 and according to it 56 activities were implemented, 23 activities are under implementation and there is a delay in the implementation of 41 activities. In general, sufficient resources support PAR Strategy and its AP, and the Government, through the PAR Council chaired by the Prime Minister, guarantees the institutional commitment to the reform. Second Annual Report on the implementation of PAR was drafted and publicly discussed in June prior to its adoption. The revision of the action plan took place in December 2019. The SEA project “Support to the management of EU funds” contributed with preparation of three relevant documents that should improve strategic planning through involvement of different stakeholders in the process. All documents were foreseen in the Strategy.

Administrative Capacity: The MISA has adopted and implemented a Service Quality Management Manual, as well as 78 working procedures, which clearly define the roles and responsibilities of the employees. In addition, there is clear division of responsibilities among the key institutions for implementation of PAR. Institutions have started vertical functional analysis, while the horizontal analyses funded within IPA 2017 National Programmed is under implementation. The close collaboration of MISA staff, as well as the staff of SCPC, SSO, CPRFAPI, with the experts of the project "Support of the Management of the EU Funds" improved the capacity for legislative analysis, which will improve the capacity to transpose and implement the EU acquis. “Support to state reorganisation” provided 4 version of the draft Law on Organisation of State administrative bodies, that will result in transformation of the Macedonian public administration and redefinition of the roles of the institutions. Sharing knowledge and experience through the cooperation with the EU experts, as well as provision of IT tools has significantly strengthened the capacities of the Agency to meet the expectations and requirements stipulated in the law on protection of the right to free access to public information

Performance: The project “Support for Management of EU funds” strengthened the institutional capacities for monitoring and definition of accurate indicators. This support resulted in advanced draft of the Performance Assessment Framework, agreed with the EUD, and discussed with the stakeholders and donors and ready to be adopted by the government.

Budget: Taking into consideration that the activities for 2018 were mostly implemented with the human and technical resources available to the country, the allocated budget was sufficient for the implementation of the planned activities. However, from the second year of implementation, the support of external donors will be necessary. Major budgetary reform supported through the Instrument for Pre-accession assistance is currently under implementation and both major processes (reorganisation of bodies and first-line budgetary users) should be conducted in parallel.

Under indirect management by RoM:

There are no actions under indirect management under the responsibility of RoM.

# Democracy and Governance, Sub sector PFM

- Involvement in programming

The IPA 2018 Action Document “EU Support to Public Finance Management” was elaborated. The Action supports the implementation of the Public Finance Management (PFM) Reform Programme 2018 – 2021. It will significantly improve the strategic framework and address key challenges identified in the PFM system, such as strengthening the fiscal consolidation and discipline, improving revenue collection, enhancing budget control and accountability.

The main features of the Action Programme are as follows:

Overall Objective: To improve governance and ensure fiscal sustainability and sound use and management of the public funds.

Specific Objective:

To raise stability, efficiency, effectiveness, and transparency of the public finance management

Results:

Result 1. Improved budget system based on implementation of a new organic budget law.

Result 2. Improved stability, efficiency, and quality of revenue collection system (tax system and policy and customs system)

Result 3. Improved legal compliance, efficiency, and transparency of the public procurement system.

Result 4. Strengthened internal control in line with the new PIFC Policy Paper

Result 5. Improved external audit efficiency and impact.

EU Financial Support: 18.600.000 EUR

National Contribution: 3.670.588 EUR

Elaboration procedure: Programming of the IPA II 2018 for PFM took place in 2017 and 2018 and the AD was adopted in June 2018. Following the adoption, the working groups started to prepare the tender dossiers as per the procurement plan. Regular monthly meetings are recommended to closely follow the procurement process and later on the implementation of the projects.

The SWG held regular consultation meeting with donors, CSOs and other stakeholders for implementation of the PFM Reform Programme, such as the Ministry of Information Society and Administration.

In spring 2020, the programming of IPA III started. Within this programming exercise, the MoF prepared one component of the Strategic Response for Good Governance, under the Window 2, – Good governance, acquis alignment, good neighbourly relations, and strategic communication.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented to fully implement the roadmap, are summarised.

| Criteria: Strategic Planning | Self-assessment: Most of the targets for 2020 have been reached |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: Most of the targets for 2020 have been reached |
| Criteria: Coordination | Self-assessment: All the targets for 2020 have been reached |
| Criteria: Performance | Self-assessment: Most of the targets for 2020 have been achieved. |
| Criteria: Budget | Self-assessment: Most of the targets for 2020 have been reached. |
| Strategic planning: PFM Reform Programme 2018-2021 was adopted in December 2017. 2018, 2019 and 2020 Action Plans adopted by the Government in February 2018, March 2019, and July 2020, respectively. The first Annual Monitoring Report on Implementation of the 2018 Action Plan for Public Financial Management Reform Programme for the period December 2017 - December 2018 was adopted by the Government on the 12th of March 2019 and published on the MoF website. The Semi-annual Monitoring Report on Implementation of the 2019 Action Plan for PFM Reform Programme for the period January 2019 - June 2019 was adopted by the Government and published on the MoF website. The process of preparation of annual Monitoring Report on Implementation of the 2019 Action Plan for Public Financial Management Reform Programme for the period January 2019 - December 2019 and 2020 Action Plan was initiated in mid-December 2019 and finalized in March 2020. The draft documents were sent by e-mail for consultation with members and observers from civil society organizations and the donor community, who are participants in the sector working group for public finance management, in March 2020. The comments received from the responsible institutions were incorporated in the final version of the documents. Both documents were adopted by the Government in July and published on the MoF website. The delay in the process of reviewing, consulting, and endorsing this Action Plan is due to the Government`s measures to deal with the health crisis caused by the COVID 19 pandemic and its consequences. The annual Report for 2019 presents the implementation rate of the activities and indicator targets. The PFM Council has conducted one consultation following a written procedure on the draft Monitoring Report on Implementation of the 2020 Action Plan for PFM Reform Programme for the period January–August 2020 Risk assessment of the PFM RP and annual action plans is conducted regularly, as part of the reporting process. The PFM monitoring reports include a separate annex for risk assessment, in which implementation challenges encountered during the 2018, 2019 and 2020 were analysed and assessed. Corrective/mitigating measures were proposed with assigned responsibilities and deadlines for implementation. The follow up of identified risks will be made during the preparation of the next annual report for 2020. Administrative capacity: The 2020 self-assessment for PFM sub-sector has been conducted and report is prepared and submitted to SEA in February 2020. In general, the issue for strengthening administrative capacities in relation to the implementation of the PFM Reform Programme is addressed at 3 levels: 1. PAR Strategy and Action Plan 2. The PFM Reform Programme and annual action plans envisages a considerable investment in the Human Resources as a part of the reform process. 3. Strategic plans on institutional level are developed on 3 years basis and they provide overview of the human and financial resources needed. All gaps identified are tackled by the relevant existing training bodies established in the sector, as well as within the framework of the various donor projects currently implemented and planned. Coordination: The progress and challenges in PFM area are regularly communicated to the stakeholders and partners and their support is obtained. On policy level, the PFM policy dialogues with all relevant stakeholders (national authorities, EC, donor community, CSO, academia) are conducted regularly. On technical level, SWG meetings are held on concrete PFM sub-areas measures and issues. In 2020, one PFM Policy Dialogue with EC and all other relevant institutions, civil society organizations and donors was held on 7 October 2020 to discuss the progress in implementation of the 2020 Action Plan as of end-August and two SWG meetings with the stakeholders were held. Performance: Continuous efforts and commitment are needed to ensure that monitoring system provides valuable information on implementation of the PFM reforms. PFM SWG meetings are conducted regularly to discuss the progress of the planned reforms and other related issues. The SWG for PFM has finalized the proposal of indicators to be included in the PAF system PAF (pafnorthmacedonia.mk) . The PFM Progress Report for 2018 and 2019 present the status of achievement of indicator targets and the 2020 one will do the same. Budget: Annual action plans for implementation of the PFM RP present an estimation of the planned inputs (budget and sources of financing) for each activity. The 2020 Action Plan is being implemented with funds allocated in the 2020 state budget. The Monitoring Report on Implementation of the 2020 Action Plan for the period January –August 2020 has been published on the MoF website. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The following meeting of the SWG was organised in 2020:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| Written procedure conducted in March/April 2020. | All PFM SWG members – above 80 | Consultation on the draft annual Monitoring Report on Implementation of the 2019 Action Plan for Public Financial Management Reform Programme for the period January 2019 - December 2019 and 2020 Action Plan |
| 7 October - 5thPFM Policy Dialogue | 54 | Draft Monitoring Report on Implementation of the 2020 Action Plan for the period January –August 2020 |
| 3 July and 3 November by video conference call | above 80 | Discussing the draft Strategic response for IPA 3 and Action fiches for 2021 and 2022. |

The following donors, IFIs, Embassies and CSOs were present at these meetings.

| Donors and International Organisations | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| SIGMA/OECD | IMF |  | Analytics |
| Embassy of Germany in Skopje | World Bank |  | Eurotink |
| Embassy of the United States of America in Skopje |  |  | Center for Civil Communications |
| Embassy of Sweden in Skopje |  |  | Finance Think |
| Embassy of the Netherlands in Skopje |  |  | Center for Economic Analysis |
| British Embassy in Skopje |  |  |  |
| EU Delegation |  |  |  |
| EC DG NEAR A3 |  |  |  |

At present, in the PFM sub-sector the following programmes financed by the donors are under implementation:

| Donor | Support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| EU | 2,050,000 | Public Finance Management (Increased data availability for better forecasting of GDP, Developed capacities for compilation of EDP notification tables, General Government Accounts established) | 2019-2022 |
| IMF (EU) or WB |  | PIMA assessment | 2020 |
| IMF (EU) or IMF | TA | TA Government Finance Statistics - Improving GFS for decision making |  |
| UK/WB | 650,000 | Improving Fiscal Sustainability, Efficiency and Transparency in PFM in Macedonia - Support to the finalisation of the new Organic Budget Law and secondary legislation and technical specifications for IFMIS | 2018-2020 |
| Ministry of Finance of Netherlands | Technical cooperation | Internal control - Bilateral cooperational Program 2018-2019 - Assessment-criteria of key control activities in one pilot institution | 2019-2020 |
| UNDP and Slovakia |  | TA- Bilateral assistance on local taxes |  |
| SIGMA (EU) | Consultancy 50,000 | SIGMA - PPB bilateral cooperation | Annual - recurring |
| EBRD | Consultancy & Financial assistance | Support of accession to WTO Agreement on Government Procurement (GPA) | / |
| WB (EU) or WB IPA 2017 Multi-beneficiary programme | Grant/IPA MBP 2017 | MIP indicators (statistics) |  |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II has an impact in the sector either through the preparation of Action Programmes or through the implementation of TA projects or through the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning: In 2018, the SWG for PFM in consultation with the EUD elaborated the Action document for IPA 2018, which will support the implementation of the country's PFM Reform Programme 2018-2021, as well as other related sub-system strategies, such as PIFC Policy Paper.

Administrative Capacity: Measures and activities under each priority of the PFM Reform Programme are defined taking into consideration current HR capacities of the PFM institutions. Significant number of results in the IPA 2018 AD for PFM is related to capacity building of the PFM institutions through new employment, knowledge enhancement and skills development and upgrading. Hence, the IPA 2018AD for PFM will contribute to further strengthen administrative capacities of the PFM institutions. Indicators for institutional development are part of the PFM RP performance indicators framework and are followed regularly in the established monitoring process.

Performance: There is consistency in the definition and measurement of the indicators defined in the PFM Reform Programme 2018 - 2021 and in the IPA 2018 AD for PFM. The activities planned under the AD are an integral part of the Annual Action Plans. Thus, the monitoring of the AD is performed through the same mechanism envisaged under the PFM Reform Programme. The Government in December 2020, following its endorsement by the PFM Council, adopted the Monitoring Report on Implementation of the 2020 Action Plan for the period January –August 2020. The Action Document supports the implementation of the country's PFM Reform Programme 2018-2021 and contributes to improved governance, fiscal sustainability and sound use and management of the public funds. The objective is to raise the stability, efficiency, effectiveness, and transparency of the public finance management through achieving the following direct results: Improved budget system based on a new organic budget law. Improved stability, efficiency and quality of revenue collection system Improved legal compliance, efficiency and transparency of the public procurement system Strengthened internal control in line with the new PIFC Policy Paper and improved external audit efficiency The SWG for PFM has finalised the proposal of indicators to be included in the PAF system.

Budget: The FA for IPA 2018 for PFM was concluded in July 2019 in the amount of EUR 18,6 million. In addition to IPA funds, the national authorities have committed to provide co-financing in amount of EUR 3.670.588.

# II a. Performance indicators in the PAR sector covering both direct and indirect management

Indicators per programmed

| Financing Agreement/Programmed reference | Indicator for sector PAR | Source | Baseline (Year) | Target (2020) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| SUB SECTOR PAR |  |
| IPA 2017/040200.03/EU | Progress made towards meeting accession criteria | Commission annual enlargement country report Composite | Moderately prepared | Advanced Level of preparation | Advanced level of preparation | Moderately Prepared | Moderately Prepared | Moderately Prepared | Moderately prepared |
| IPA 2017/040200.03/EU | Composite indicator (average of: Government Effectiveness, Burden of Government Regulation and Regulatory Quality) /1 (Worst) - 100 (Best) | World Bank / World Economic Forum | Composite 60.73 (2014) GE 60,58 (2014) BGR 3.8/7 (54.28) RQ 67.31 | Above 65 | Above 70 | Composite 56.91 GE 58.17 BGR 2.9/7 (41,42) RQ 71.15 | Composite 61.56 GE 55.77 BGR 3.0 (57.3) (2019) RQ 71.63 | Composite 61.56 GE 55.77 BGR 3.0 (57.3) (2019) RQ 71.63 | Not available |
| IPA 2017/040200.03/EU | Improvement in 60% of the indicators included in the SIGMA baseline measurement report on PAR (the 5 principles – a tot | SIGMA Assessment | Total No of indicators: 98 | Improvement in 30% of the indicators | Improvement in 50% of the indicators |  |  |  |  |
| IPA 2017/040200.03/EU | Percentage of user satisfaction with the administrative services and servants (1 - worst, 5 - best) | Assess the administration– MISA Annual Report of MISA SIGMA | 1 = 3.48(2015) 2 = 12.02 3 = 84.48 | 5 = 75 4 = 15 3 = 7 2 = 2 1 = 1 | 5 = 75 4 = 15 3 = 7 2 = 2 1 = 1 | No longer calculated. |
| IPA 2017/040200.03/EU | Corruption perception index (score and positive trend) and Global Corruption Barometer | Transparency International | 45 (2014) / 37 (2016) GCB - 3 red, 2 orange (2015-2016) | 45 Improvements in at least 2 indicators | 50 Improvements in at least 3 indicators | 35 No data available for 2017 on GCB | 37 No data available | 35/100 No data available | 35/100 No data available |
| IPA 2017/040200.03/EU | Percentage of statistics aligned with EU acquis (Social, Business and National Accounts) / Compliance level calculated with the method of EURtat's strategy for statistical cooperation under IPA II increased to 85% based on the currently existing EU acquis in statistics; | EURtat Strategy for Statistical Cooperation with the Enlargement Countries 2014/20 SMIS+ reports EDAMIS reports | 55% (2015) | 85% | 95% | 66.2% | 67.1% | The value for 2019 is yet to be calculated. SSO is waiting for the assessment from Eurostat |  |
| IPA 2017/040200.03/EU | Extent to which the overall structure of ministries and other bodies subordinated to central government is rational and coherent. | SIGMA Baseline measurement reports | 2 (2014) | 4 (2020) | 4 | No data available. The project is in the second month of implementation | No data available. | No data available. |
| IPA 2017/040200.03/EU | No of institutions having and applying an integrity policy | SCPC reports | 1 (2016)) | 50 (2020 | 75 | 1 | 1 | 1 | 1 (activities have just been launched with IPA project) |
| IPA 2017/040200.03/EU | Percentage of institutions applying pro-active transparency standards | Commission for rights for free access to public info | 0 | 50% | 100% | / | The Transparency Standards by the information holders/state institutions ranges from 30%-35%, approximate 32.5% | Of the chosen 197 state institutions for monitoring in 2019, 89 have no web site. Hence, the transparency standards is 30%. | Report not prepared yet |
| IPA 2017/040200.03/EU | No of whistleblowing cases launched and protection measures taken | SCPC reports | 0 (2015) | 15 | 30 | 0 | 2 cases 0 protection measures taken | 19 cases 2 protection measures taken | SCPC report not prepared yet |
| IPA 2017/040200.03/EU | Requests for information refused/unanswered in breach of law (as a % of the total number of requests) | Commission for rights for free access to public info | (Figure still to be provided) / 650. | Less than 10% | Less than 10% | 44% | 83% | Reporting beginning of March since we are still processing the Annual Reports from the information holders | Report not prepared yet |
| IPA 2017/040200.03/EU | Number of services accessible and available by Single point of contact (OSS or e-services N/A 100 100 MISA - Annual reports 24 | MISA annual report | N/A | 100 | 100 |  |  | 127 public available on the portal. Establishment of physical premises ongoing. | 137 Establishment of physical premises ongoing. |
| IPA 2017/040200.03/EU | Percentage of user’s vs target users’ ratio of eservices | MISA | n/a | 15% | 15% |  | No data available | No data available | No data available |
|  | Pilot statistics on the performance by body and public officers involved in service delivery (coverage by institution and by No of servants) | MISA | n/a | 15 institutions 50 public servants | 20 institutions 100 servants |  | Project has not started | No data available | No data available |
| IPA 2017/040200.03/EU | Coverage of OSS umbrella system (% of relevant institutions covered) | OSS e-circuit reports/ MoU | 5 (2016) | 80% | 100% |  | Implementation of the project has not started yet | Implementation of the project has not started yet | Project is in its Inception Phase |
| IPA 2017/040200.03/EU | Percentage of indicators produced for GDP on quarterly level by expenditure approach at current and constant prices | EDAMIS reports SMIS+ reports EC Progress report for the chapter 18 SSO web sit | 75% available indicators, 10 days’ time lag, missing data series 1995 - 1999 | 90% available indicators, no time lag, data series 1995-1999 available | 95% Available indicators |  | 50% | 50% | 50% available indicators, 10 days’ time lag, missing data series 1995 - 1999 |
| IPA 2017/040200.03/EU | Percentage of indicators compiled for EDP notification tables in accordance with ESA 2010 | Regular OSS system performance monitoring reports Changes of laws and/or by-laws (Official Gazette) | 5 % | 80% | 95 % |  | 46.5% | 46.5% | 80% |
| IPA 2017/040200.03/EU | Percentage of SBPM sub-processes covered by standard metadata driven tools | Implementation of standardized IT tools | SSO website/ SSO Reports | 0 | At least 25% | At Least 30% | 22% | 22% | 22% |
| SUB SECTOR PFM |  |
| IPA/2018/040-860, Objective 1 | Budget deficit below 3% | Medium term fiscal strategy and annual Budget | 2,7% of GDP (Draft budget 2018) | below 3% | below 3% |  | 1.8% of GDP (Executed budget 2018) | 2 % of GDP | 8.1% of GDP |
| IPA/2018/040-860, Objective 1 | Progress made towards meeting accession criteria (economic and political criteria and steady progress in related Chapters 5,8,17,18,32 and 33) | EC Progress Reports | PR 2016 assessment | Progress noted in respective areas of PFM | Progress noted in respective areas of PFM |  | See EC Progress Reports 2018 | See EC Progress Reports 2019 | See EC Progress Reports 2020 |
| IPA/2018/040-860, Objective 1 | No of indicators of the PFM Reform programme fully met | PFM Reform Programme reports | 0 (2017) | 100% | 100% |  | (50 indicators in total for 2018) 26 indicators targets are achieved, 12 partials achieved, 12 not achieved | (72 indicators in total for 2019) 29 indicators targets are achieved, 22 partials achieved, 21 not achieved) | Data will be available after the adoption of the Annual Monitoring Report for 2020 |
| IPA/2018/040-860, Objective 1 | Improvement in PEFA and SIGMA PFM indicators/assessment | PEFA/SIGMA Reports | PEFA 2015 (31 indicators, 94 dimensions) SIGMA (125 criteria) | 50% of PEFA/SIGMA indicators show improvements | 80% of PEFA/SIGMA indicators show improvements | N/A | N/A * the next PEFA could be planned in 2021 | N/A * the next PEFA could be planned in 2021 | N/A * the next PEFA is planned in 2021 |
| IPA/2018/040-860, Objective 1 | Percentage deviation between annual budget of year N+1 and N+2 with MTBF projections year N | MTBF, annual budget | N+1 - 5% N+2 - cannot be calculated at the moment | up to 7% up to 10% | up to 7% up to 10% |  | 0% | 3,7% | 3,2% |
| IPA/2018/040-860, Objective 1 | Level of harmonization of the national legislation with the European acquis in the field of taxesand customs - number of EU tax and customs acquis (existing EU legal provisions in 2018) transposed in the national legislation | Tables of concordance Laws/Official Journal | partly harmonised legislation – level of harmonisation to be established with concordance tables | 50% of the acquis (2018 basis) transposed | 70% of the acquis (2018 basis) transposed | partly harmonised legislation – level of harmonisation to be established with concordance tables | partly harmonised legislation – level of harmonisation to be established with concordance tables | partly harmonised legislation – level of harmonisation to be established with concordance tables | Partly harmonised legislation – level of harmonisation to be established with concordance tables |
| IPA/2018/040-860, Objective 1/ Action 3 | Tax efficiency coefficient | Tables for the national Budget execution (Ministry of finance) and data for Gross domestic product (SSO) | PIT tax efficiency not less than 0,23 CIT tax efficiency not less than 0,14 VAT C-efficiency not less than 0,52 | PIT tax efficiency not less than 0,29 CIT tax efficiency not less than 0,23 VAT C-efficiency not less than 0,60 | PIT tax efficiency not less than 0,29 CIT tax efficiency not less than 0,23 VAT C-efficiency not less than 0,60 | PIT tax efficiency: 0.25 CIT tax efficiency: 0.18 VAT C-efficiency: 0.52 | PIT tax efficiency: 0.28 CIT tax efficiency: 0.20 VAT C-efficiency: 0.52 PIT tax | PIT tax efficiency: 0.27 CIT tax efficiency: 0.17 VAT C-efficiency: 0.52 | PIT tax efficiency: 0.27 CIT tax efficiency: 0.17 VAT C-efficiency: 0.53 |
| IPA/2018/040-860, Objective 1/ Action 3 | Percentage of tax services digitalised | e-Tax platform | 60% (2017) | 80% | 100% |  | 70% | 76,77% | 80% |
| IPA/2018/040-860, Objective 1/ Action 3 | Number of AEOS certificates issued | Customs reports | 2 (2018) | (2022) 10% increased | (2024) 20% increased |  | 2 | 10 | 17 |
| IPA/2018/040-860, Objective 1/ Action 3 | Business continuity and stability of the PRO and Customs electronic systems in case of crisis for the data and the business processes | PFM Disaster Recovery Centre documents | Partial (2017) - data back-up ensured | Partial (2017) - data back-up ensured | 100% business continuity | Partial) - data back-up ensured | Partial - data back-up ensured | Partial - data back-up ensured | Partial - data back-up ensured |
| IPA/2018/040-860, Objective 1/ Action 3 | Competition rate: - number of one bid tenders in electronic procedures) - average No of tenderers per tender | e-Procurement reports/ Annual Report on Public Procurement System | 25% (2016) 2.97 (2016) | Less than 25% Above 3 | -Less than 20% 3.5 |  | 24,92 %. 3,41 | 24,90%. 3,31 | 23,43 % 3,58% |
| IPA/2018/040-860, Objective 1/ Action 3 | Publication rate of procurement plans | e-Procurement reports/ Annual Report on Public Procurement System | Plans: 0 | 100% | 100% | / | % | 76,72 | 78,64% |
| IPA/2018/040-860, Objective 1/ Action 3 | Number of budget users applying decentralised system for managing public funds | Annual report for functioning of PIFC system | 46% | 27% | 70% |  |  | 25% | Data will be available in August 2021 |
| IPA/2018/040-860, Objective 1/ Action 3 | Percentage of implemented internal audit recommendations | Annual report for functioning of PIFC system | 43% | 72% | 63% |  | 43% | 62% | Data will be available in August 2021 |
| IPA/2018/040-860, Objective 1/ Action 3 | Percentage of external audit coverage of the total public expenditure | SAO Annual Report | 45 | 50% | ≥55% (2024) | ≥42% | 54% | data will be available in the SAO Annual Report 2020 (published by June 2021) | Data will be available in the SAO Annual Report 2021 (published by June 2022) |
| IPA/2018/040-860, Objective 1/ Action 3 | % of external audit recommendations leading to corrective measures | SAO Annual Report | 55% | 76,6% | ≥70%(2024) | ≥59% | 76,6% | data will be available in the SAO Annual Report 2020 (published by June 2021) | Data will be available in the SAO Annual Report 2021 (published by June 2022) |
| IPA/2018/040-860, Objective 1/ Action 3 | No of audit reports discussed by the Parliament | Report of the parliamentary body responsible for conducting the discussion of audit reports process | 0 | 8 | 10 | 0 | 0 | 0 | 0 |
| Sub Sector Local and Regional development |
| IPA 2020/041831.01/ | Index of citizens' satisfaction from local services delivered (level of dissatisfaction) | Eurobarometer | 60% (2017) | 55% | Less than 55% |  |  |  |  |
| IPA 2020/041831.01/ | Trust in local governments (level of distrust) | Eurobarometer | 67% (2017) | 65% | Less than 65% |  |  | 64 % |  |
| IPA 2020/041831.01/ | Distance to average GDP per capita measured for the regions where innovative measures will be implemented | EUR tat / State Statistics | Average GDP per capita for the country 4,691 (2016) | NA | 10% decrease in distance to average |  | Average GDP per capita for the country: 5.170 euro |  |  |
| IPA 2020/041831.01/ | Number of persons benefiting from the EU supported innovative solutions in the targeted/selected municipalities | Interim and final reports of the projects | 0 (2018) | >50,000 | >100,000 |  |  |  | - |
| IPA 2020/041831.01/ | Number of smart solutions to significant community recognised service/policy challenges implemented | Interim and final reports of the projects | 0 (2018) | 8 | +24 |  |  |  | - |
| IPA 2020/041831.01/ | Number of local governance arrangements put in place – coordination units, interdepartmental structures, to allow innovations in municipal governance happen | Reports of the TA assisting applicants and grant beneficiaries. External studies from IOs and CSOs. | 0 (2018) | 3 | 12 |  |  |  |  |
| IPA 2020/041831.01/ | Number of trained people (sex disaggregated data included) | Reports of the TA assisting applicants and grant beneficiaries | 0 (2018) | 50 | +100 |  |  |  |  |
| IPA 2020/041831.01/ | New inter-municipal, regional, and international partnerships and networks developed/ Number of new partnerships between EUMK and MK-MK local authorities | Register of the co/financing of the payments for extension services | 0 (2018) | 0 | 12 |  |  |  |  |
| IPA 2020/041831.01/ | Number of social media participants/followers | Project report | 0 (2018) | 0 | > 50,000 |  |  |  |  |
| IPA 2020/041831.01/ | Number of innovative measures financed | Project report | 0 (2018) | 7 | 7 |  |  |  |  |
|  | Number of municipalities involved in innovative measures | Project report | 2 (2018) | 12 | 12 |  |  |  |  |

# Democracy and Governance, Union Programmes

1. Focal Points

Erasmus: The National Agency for European educational programs and mobility oversees the Erasmus + Programmed. In 2020, 50 people were working in the Agency and 42 are fully dedicated to the Erasmus + Programmed. Contact point: Milena Petrusevska, milena.petrusevska@na.org.mk, +389 76 446 824

Europe for Citizens: Unit for negotiation and integration - EU Department of the Ministry of Education and Science oversees the Programme. 3 people are working in this Unit and still just 1 person oversees the Europe for Citizens Programme, although the same person has other responsibilities and tasks in the unit. Contact point: Katerina Gulev, katerina.gulev@mon.gov.mk

EaSI: The Unit for Coordination and Implementation of EU Financial Instruments in cooperation with the Unit for monitoring and evaluation of IPA within the MLSP are in charge of this Programme. Five people are working in these Units and two are dedicated to the EaSi Programme. Contact point: Aleksandra Slavkoska, +389 75 359 856, aslavkoska@mtsp.gov.mk, alternate: Ankica Ivanovski, +389 75 341 020 aivanovska@mtsp.gov.mk

Civil Protection Mechanism the Protection and Rescue Directorate is in charge the Civil Protection Mechanism. Currently 270 people are working in this directorate (40 temporaries employed) and 1 is fully dedicated to the Mechanism (Head of international cooperation department) and 1 dedicated for the EUCPM training program. Contact point: Valentina Atanasovska, valentina.atanasovska@dzs.gov.mk, +389(02) 2433 318, +389 75 457 591

FRA The Human Rights Department within the Ministry of Justice, in cooperation with the Ministry of Foreign Affairs, is in charge of the activities related to the European Agency for Human Rights. Contact point: Tanja Kikerekova, National Liaison Officer- TKikerekova@mjustice.gov.mk, + 389 76 40 44 62, Elena Bodeva, Deputy National Liaison Officer- elena.bodeva@mfa.gov.mk . + 389 75 26 87 31

COSME: The Department for European Integration, Unit for programming, technical implementation and monitoring and evaluation of IPA projects within the Ministry of Economy is in charge of the COSME Programme. 7 people are working in this Dpt and 2 are part time dedicated to the COSME Programme. Contact point: Ardiana Abazi- Ramadani, ardiana@economy.gov.mk, +389 2 3093453

Horizon 2020: The Ministry of Education and Science, Department for International Cooperation, is in charge of the implementation of the Horizon 2020 Programme. 2 people are working in this Dpt and 1 is fully dedicated to the Horizon2020 Programme. Contact point: Marina Nikolovska, +389 3 140 186, +389 76 485 077 marina.nikolovska@mon.gov.mk

Customs 2020: Department for International Cooperation in the Customs Administration is in charge of the Customs 2020 Programme. 3 people from the Department of International Cooperation are fully dedicated to the Customs 2020 Programme. Contact point: Sladjana Damjanoska, Sladjana.damjanoska@customs.gov.mk, Irina.tileva@customs.gov.mk +389 2 3293942;

Fiscalis: The Fiscalis 2020 programme within the Public Revenue Office (PRO) is coordinated by the Sector for International Cooperation. 7 people are working in the Sector and 3 are fully dedicated to the Fiscalis Programme. Contact point: Marjan Mihajlovski, Marjan.Mihajlovski@ujp.gov.mk, , Office: 3299 543, Mobile: 076/445 471

Creative Europe: The Coordinating body responsible for implementation of the Creative Europe programme (Culture and MEDIA) is the Ministry of Culture. North Macedonia Film Agency is nominated as co-beneficiary, responsible for implementation of the MEDIA sub–programme from 1st of January 2016 based on the mutual Agreement between the Ministry of Culture and the Film Agency. Creative Europe Desk of the Republic of North Macedonia Team: Creative Europe Culture (Ministry of Culture) : Project manager and project assistant (civil servants - full time job). Contact point: Biljana Prentoska e-mail: biljana.prentoska@ced.mk , 'biljana.prentoska@kultura.gov.mk'тел: +389 2 3207 446/443; Creative Europe MEDIA (North Macedonia Film Agency): Project manager (Bistra Georgieva) and project assistant (Emilija Romeva) (full time job) Contact point: Bistra Georgieva e:mailbistra.georgieva@ced.mk , emilija.romeva@ced.mk + 38902 3224 100

Life +: The Administration of Environment within the Ministry of Environment and Physical Planning is responsible body for coordination and implementation of LIFE + programme. Contact point: Vlatko Trpeski, Head of department of nature protection, mail: v.trpeski@moepp.gov.mk

| 2. Information on the implementation of the Programmes in 2020 |
| --- |
| Programmes | Number of financed projects | Number of events | Value of the financed projects/events |
| Erasmus +: | Erasmus+ 290 European Solidarity Corps 5 | 25 | Erasmus+ 11.127.724 EUR European Solidarity Corps 59.269 EUR |
| Europe for Citizens: | 2 projects | - | 204.120 EUR (financed projects in 2020) |
| EaSI: | Progress: 11 projects in total (2 projects under the 2019 Calls for proposal, 1project financed under 2018 Call for proposal, 6 projects financed under 2017 Calls, 2 projects under 2016 Calls) Note: Awarded grants of 2020 Calls have not been published yet. Microfinancing axis: Approved Financial Guarantees (1 signed in 2018, while the second one in 2020) | None in 2020 | Total: 3.439.768,59 EUR Progress: 2.583.268,59 EUR (total value of all 11 projects, the amount was corrected with the exact amount awarded to MK organisations for the project where MLSP is recipient) Microfinancing axis: 901.500 EUR (total value of the two EaSI Financial Guarantees signed with banks from North Macedonia) |
| Civil Protection Mechanism: | EUCPM training program, according to the dedicated quote | - | Due to COVID-19 pandemic, the Training Program of the UCPM for 2020 was cancelled. |
| FRA: | None | 1 | None |
| COSME: | 5 (active projects in 2020) | 1+8 (EEN) | 186.976,00 EUR (the value of active projects in 2020 the data is not fully accurate since we still don’t have info for 2 new projects) |
| Horizon 2020: | 12 | 30 Online or phone consultation sessions with individual or institutional applicants | EUR 2.6 M. e-corda cut of date- January 2020 |
| Customs 2020: | - | 25 (5 physical presence +20 online) | 12.530.00 Eur (Due to the COVID 19 this amount is spent in the first two months of 2020) |
| Fiscalis: |  | 3 | 6.376,78 Eur (Financial year 2019 (01.04.2019 – 31.03.2020) for the period 01.01.2020 -31.03.2020) |
|  |  | 10 | 0 (Financial year 2020 (01.04.2020– 31.03.2021) for the period 01.04.2020-31.12.2020 by 11.01.2021) |
| Creative Europe: | MEDIA: 5 Culture: 13 WB Cooperation Call: 10 projects (2 lead partners, 10 co-organizers) Cooperation projects: 3 projects (3 co-organizers) | MEDIA:9 Culture: 1 regional and EU level two days event Number of individual consultancy meetings: over 50 | MEDIA: 108.216 EUR Culture: WB Cooperation Call 3.632 832 EUR Cooperation projects: 75.081 EUR\ |
| Life +: | - | - | -2 Regional multiannual projects |

| 3. Main achievements of the Programmes in 2020 |
| --- |
| Programme | Objectives | Achievements |
| Erasmus +: | To support education, training, youth, and sport in Europe | Concerning the Erasmus+ programme implementation, in Key action 1, 98 projects were granted in amount of 4.354.702 euro. In Key action 2, 21 projects were granted in amount of 2.446.100 euro. In Key action 229 Strategic partnerships for school exchange (child projects), 164 projects were granted in amount of 4.306.746eur (with central clearing in EC). In Key action 3, 3 projects were granted in amount of 20.176 euro The National Agency also implements European Solidarity Corps programme. In 2020 5 projects (solidarity and volunteer) were granted in amount of 59.269 euro Erasmus+ Breakdown by most used topics (or receiving country) by field: KA1 school education mobilities: ICT-new technologies-digital competences, new innovative curricula/methods, pedagogy and didactics, inclusion-equity, disabilities-special needs. Top receiving countries are Spain, Italy, Malta, Bulgaria. KA2 - Strategic partnerships for schools: early school leaving/combating failure in education, ICT-new technologies-digital competences, romas and/or other minorities, inclusion. Strategic partnerships for school exchange (parent projects): ICT-new technologies-digital competences, environment and climate change, social dialogue, inclusion-equity. Strategic partnerships for school exchange (child projects) detailed data are not yet available due to central clearing procedures. KA1 VET mobilities: quality improvement institutions and/or methods, new innovative curricula/methods, labour market issues including career guidance/youth unemployment, agriculture. KA2 VET strategic partnerships: labour market issues including career guidance/youth unemployment, new innovative curricula/methods, ICT-new technologies-digital competences. KA1 Adult education mobilities: inclusion-equity, research and innovation, new innovative curricula/methods, disabilities-special needs, international cooperation. KA2 Adult education strategic partnerships: new innovative curricula/methods, inclusion-equity, disabilities-special needs, key competences – basic skills. KA1 Higher education mobilities top receiving countries are Turkey, Poland, Italy, Croatia, Slovenia. KA2 Higher education strategic partnerships: inclusion-equity, new innovative curricula/methods, gender equality/equal opportunities, regional dimension, and cooperation. KA1 Youth mobilities: youth (participation, youth work, youth policy), entrepreneurial learning, environment and climate change, labour market issues including career guidance/youth unemployment. Top project partners are from Italy, Greece, Turkey, Bulgaria. KA2 Youth strategic partnerships: youth (participation, youth work, youth policy), new innovative curricula/methods, inclusion-equity, entrepreneurial learning, ICT-new technologies-digital competences. KA3 Youth dialogue: youth (participation, youth work, youth policy), reaching the policy level/dialogue with decision maker, EU citizenship, EU awareness and democracy, social dialogue. European Solidarity Corps: Volunteering projects: 4 granted projects with 22 participants. Most used topics are culture, skills development, youth work, inclusion. Solidarity projects: Due to the low available budget amount for solidarity projects 1 solidarity project is granted. The solidarity project is specific from the point of targeted participants in projected activities – youngsters with a special need and the grant beneficiary is from rural part of country. Quality Label: 8 awarded organizations. |
| Europe for Citizens: | To contribute to citizens' understanding of the EU, its history and diversity To foster European citizenship and to improve conditions for civic and democratic participation at EU level. To raise awareness of remembrance, common history, and values To encourage democratic participation of citizens at EU level, by developing citizens' understanding of the EU policy making process and, by promoting opportunities for societal and intercultural engagement and volunteering at EU level | In 2020 , there were supported 2 projects: - 1 project within the Sub-Networks of Towns (Selecting year 2020 – Round 1) – with an amount of 60.480 EUR (the Applicant organization: Centre for improvement of the quality of life of the persons with intellectual disability and their families PORAKA NOVA, and the Project title: Social Innovation Network). -1 project within the Strand 2 Measure 2.3 Civil Society Projects (Selecting year 2020) – with an amount of 143.640 EUR (the Applicant Organization: EVROTINK Center za evropski strategii Skopje, and the Project title: Tackling liberal/EURceptic Narratives from Below). Taking into consideration that the amount that has been paid as national contribution for 2020 was 6.750 EUR, and the amount of the projects that have been supported is 204.120 EUR, we can say that the financial participation ration is positive. All data is provided by the official website of EACEA. Even though there is no data available about the projects where the Republic of North Macedonia is a Partner country, so the amount of the supported projects could be higher. |
| EaSI: | To promote a high level of quality and sustainable employment, guaranteeing adequate and decent social protection, combating social exclusion and poverty, and improving working conditions | Under the “Progress axis”, the grant projects mainly contributed to enhancing transnational administrative cooperation among social partners from EU and candidate countries and securing better information prospects for all posted workers. These projects also promoted greater involvement/consultation of employees, capacity building of national stakeholders and addressing the institutional weaknesses for implementation of the EU acquis in this area. In 2020, the Ministry of Labour and Social Policy in partnership with Redcross Macedonia received grant project which will support the implementation of the national reforms in long-term care. A new social service “Emergency button” will be piloted and the intention is to further standardise its delivery. Under the “Microfinancing and Social Entrepreneurship axis”, the "Step by Step" programme promotes micro-financing and thus development of start-up businesses. "Step by Step" provides economic and social support to young entrepreneurs and micro-enterprises which are in the initial phase of establishing their own business, with up to EUR 25,000 and educational, financial, and mentoring support. According to the information available in media, the bank approved loans for 13 business plans in 2019 under the first call. More than 50 business start-ups, which applied to the call, participated in the training workshops organised by Business Impact Lab и Start-up Academy. About 23 business plans were developed, but only 13 were positively assessed. In 2020, Sparkasse Bank Macedonia, in collaboration with SEEU Tech Park, Start Up Academy and Business Impact Lab, launched the second cycle of the “Step by Step” acceleration program. Due to the pandemics, the mentoring programme was organised online. The information about the total approved microcredits for 2020 is not available yet. Following the signature of the cooperation agreement with the European Investment Fund (EIF) in November 2020, Silk Road Bank AD Skopje will be able to issue up to €5 million in microcredits to micro-companies in North Macedonia. Silk Road Bank has created the Bizz UP package of products intended for financing of vulnerable categories of clients as well as start-ups and companies in their development phase with an operating history of up to 36 months. The Bizz UP package consist of several micro finance products, such as overdraft, loans for working capital needs and investment loans. Loans under this agreement will be available to companies with a maximum of 9 employees. The annual turnover of the company should not exceed €2 million. |
| Civil Protection Mechanism: | To foster cooperation among national civil protection authorities across Europe. | In 2020 non new programmes were financed. However, results achieved in the past and linked to the international cooperation on civil protection were consolidated. Online meetings were held in the framework of the civil protection Director General meeting and of the Union for the Mediterranean’s (UfM) Directors General of Civil Protection. Thanks to the good international cooperation developed in the previous years, the Protection and rescue Directorate, as a national authority for coordination of all the activities of the UCPM, based on the decision of the Government, activated the UCPM, requesting international assistance because of the COVID-19 pandemic. Until 20th January 2021, we have received assistance via the UCPM from Germany, Austria, Romania, Greece, Slovakia, Estonia, Czech Republic, and Sweden, most of it from the resc EU medical stockpile. The Host Nation Support and facilitation of all the procedures regarding receiving and distributing assistance has been done by the PRD, in coordination with Ministry of health, Ministry of Interior, Secretariat of EU affairs, and the Customs of North Macedonia. |
| FRA: | To contribute towards ensuring full respect for fundamental rights across the EU and Accession Countries | The programme has increased the attention of the Macedonian Society towards very important fundamental rights like LGBT equality, Data protection and privacy, security concerns and experiences, strengthening of the institutional framework on fundamental rights and fundamental rights in an era of artificial intelligence. Additionally, it has strengthened the cooperation among the stakeholders (FRA, Ombudsman, CSOs, MoJ and MFA) and strengthened the International cooperation on fundamental rights |
| COSME: | To facilitate access to finance. To support internationalisation and access to markets. To Create an environment favourable to competitiveness. To encourage an entrepreneurial culture. | Throughout the reporting period, the activities of the Ministry of Economy as national partner institution for this program were affected from the COVID 19 pandemic, however, it manages to fulfil its obligations. In this direction, payment of annual entry ticket for COSME 2020 was realized. In terms of dissemination of the program, the pandemic situation made impossible much of the promotional activities, thus most of them were realised through online facilities. In addition, the Enterprise Europe Network in Macedonia project during the period October 2019 to October 2020 has delivered the following COSME activities: advice, support, and information activities; cross-border partnering activities for business cooperation, technology transfer and innovation; SME feedback activities; promotion of Network services and communication activities and network building and reinforcing the Network. Furthermore, it conducted special H2020 activities related to enhancing the innovation management capacities of the SMEs. During 2020 under COSME Programme, one project was renewed, and two new projects were awarded; Business & Innovation Centre (BIC) and its partners were awarded an EU grant: CEnTOUR Project that aims at boosting sustainable tourism development and capacity building of tourism. National centre for development of innovation and entrepreneurial learning and its partners were awarded an EU grant, for the implementation of the project South Eastern European coalition to cultivate SMART SMEs in Europe. The projects started in 2020 and will run until 2023. Up to date, COSME Programme under different calls has supported 11 projects in the country, out of which 6 are closed, while the other 5 are being implemented. |
| Horizon 2020: | The goal is to ensure Europe produces world-class science, removes barriers to innovation and makes it easier for the public and private sectors to work together in delivering innovation. | According to the official EC database E-CORDA, during 2020, there were signed 12 grant agreements with 16 participants from Republic of N. Macedonia. Total EU contribution for these projects is EUR 2.6 M. There are several projects in the pipeline and a few approved for financing projects waiting to sign the grant/ consortium agreements. It means that the financial year regarding H2020 is not closed yet. It is worth of mentioning that in frame of H2020 calls North Macedonia applied and became the first and only Western Balkan country member of the European High Performance Computing Joint Undertaking. Responsible institution is the Faculty of Computer Science and Engineering at the SS. Cyril and Methodius University in Skopje (FEIT). FEIT is granted with EUR 1 M project to establish and coordinate the National High Performance Computing Competence Centre. Review of NM participation in period 2014-2020: Within the participation of the H2020 associated countries from the region, North Macedonia is in the group of successful countries given the fact that great part of the received projects are collaborative (research and innovative) projects, Macedonian legal entities participate in all parts of H2020. So far, almost 800 proposals have been submitted, out of which 663 in eligible proposals. 75 projects are financed with 101 participants and a total EU contribution of 12.05 mil EUR. Success rate is 11.01% (EU success rate is 12.5%) ( E-CORDA database extraction date November 2020) Benefit of participation in H2020: H2020 projects are generally largerin terms of funding than nationally funded projects. • Each H2020 project gives Macedonian participants access to on average 15 international partners • Through H2020 projects, North Macedonian participants get access to more knowledge and R&I infrastructure than in national instruments, including knowledge and R&I infrastructure not available in Macedonia. • The benefits of international collaboration do not only apply only to project participants, but also to policy makers, innovation agencies and other stakeholders participating in various H2020 activities. |
| Customs 2020: | To support the functioning and modernization of the customs union to strengthen the internal market by means of cooperation between participating countries, their customs authorities, and their officials | Under this program, representatives of the CARNM can establish closer contacts with their colleagues from other countries and exchange knowledge, expertise, and experience. In 2020, more than 60 customs administration representatives attended specific online events in several areas through projects groups, covering the following topics: •E-Customs, IT Technology and Infrastructure, CCN/CSI Trainings •Customs Laboratory •Cash controls project group •EU Communication Network Project group •CUP (Customs Union Performance) Project group •Training Support Group etc. Also, High level managers have participated in the meetings in different areas as a part of this programme. For instance, through this program offers the possibility for the Customs Administration of the Republic of North Macedonia has the possibility to connect with the customs and tax IT systems of the EU (via CCN\CSI). For example, since 2015 the IT communication node CCN/CSI, required for NCTS, is established through the Customs 2020 program. By participation in meetings, seminars and workshops, the Macedonian customs officers are timely informed about actions which are to be undertaken and planned by the Member States, regarding the improvement of customs work, as well as realisation of EU Strategic Policies and Objectives. |
| Fiscalis: | To enable national tax administrations to create and exchange information and expertise. To enhance the administrative capacity of participating countries, to support the fight against tax fraud, tax evasion and aggressive tax planning; to support administrative cooperation activities; to reinforce the skills and competency of tax officials; to enhance the understanding and implementation of Union law in the field of taxation. | The participation in the joint activities (workshops, working visits, Project groups etc.) within the current Fiscalis 2020 programmed, helped the Public Revenue Office, by exchanging the best experiences and practices, in the process of implementation of EU legislation during the process of EU integration. Furthermore, the employees of the PRO have developed good business relations with their colleagues from the tax administrations in the EU member states/candidate countries, beneficiaries to this programmed and to exchange the experiences and best practices which will result in reaching improved administrative capacities, higher level of improvement of the working processes, as well as strengthening the capacities of the human resources. |
| Creative Europe: | Culture: To enhance the cultural area shared by Europeans. Provides support for the cultural and creative organisations pursuing cross-border activities in Europe. It ensures the financial support for cooperation projects, literary translations, European platforms, and network activities. MEDIA: To supports the EU film and audio-visual industries financially in the development, distribution, and promotion of their work. | Culture: Transnational cooperation projects involving cultural and creative organizations from different countries taking part in the program with aims to improve access to European culture and creative works and to promote innovation and creativity. The programme supports translation and promotion of literary works across EU markets, with the aim of increasing access to and readership of high-quality European literature. CED Culture sub- programme: The CED Culture sub programme has organized a Regional Seminar dedicated to, Creative Europe - Western Balkan’s Window Call and the Regional Cultural Cooperation’’ (5th and 6th of February 2020, European House, Skopje) in cooperation with the European Commission (DG EAC) and the Delegation of the European Union in Skopje. 13 projects and 15 Macedonian cultural organizations participated in the selected projects in 2020 under the following categories of the Culture sub programme: - Cooperation projects smaller scale – 3 projects (organizers) - Cultural Cooperation in the Western Balkan Call – 10 projects (2 lead partners, 12 co-organizers) https://eacea.ec.europa.eu/creative-europe/selection-results/cultural-cooperation-projects-in-western-balkans-2019_en Other achievements: - Literary translation projects – the selection results still have not been published yet. - Music Moves Europe – 1 project partner organization - EUPL – Laureate from North Macedonia for 2020, Petar Andonovski, author MEDIA: In 2020 for the first time in one year two Macedonian projects received support from “Development Single Project” call of Creative Europe MEDIA. Makedox- Creative Documentary Film Festival received support for the 5th time (every year since North Macedonia is part of the sub programme MEDIA). “European Film Challenge”, a platform for promoting European films and connecting large community of film lovers, received support for the second time. All activities of CED MEDIA MK were focused on helping the Audio-visual Sector and build the capacity of the professionals. |
| Life +: | The LIFE programme is the EU’s funding instrument for the environment and climate action. LIFE contributes to the implementation, updating and development of EU environmental and climate policy and laws by co-financing projects with European added value. | The Civic association, Macedonian Ecological Society” as a partner organization implement a LIFE+ project "Urgent Actions to Strengthen the Balkan Population of the Egyptian Vulture and Secure Its Flyway” (LIFE16 NAT/BG/000874)” in partnership with 14 organisations and institutions from Balkan Peninsula, Middle East and Africa. The period of implementation of the project is 5,5 years (1 July 2017 – 31 December 2022). Budget: overall 5,848,458 € (maximum EU contribution 4,386,343 €) The 'BalkanDetox LIFE' project is a five-year endeavour with a €1.8 million budget, which aims to raise awareness and strengthen national capacities to fight the problem of wildlife poisoning across Albania, Bosnia & Herzegovina, Bulgaria, Croatia, Greece, the Republic of North Macedonia and Serbia. |

4. Recommendations for further actions for better promotion of the Union Programme and increase of the participation of Macedonian organizations and institutions

Erasmus +: More target oriented promotional activities, particularly for newcomers especially bearing in mind the increased funds in MFF 2021-2027. The NA in the work programme for 2021 envisaged to open local info offices in other cities in the country where more targeted presentations and trainings will be held. Also, cooperation with the local self-government will be strengthened for the promotion of the programme. Further strengthening the coordination and communication between central governmental bodies on policies relevant for the NA actions/European education policies. Internal adaptation of the NA looking towards the new programme 2021-2027, including digitalization of the NA.

Europe for Citizens: Engaging more persons who will work on the Programme on regular basis; providing Budget for organization of Info-days.

EaSI: Facilitate establishment of partnership for projects that support national reforms. Early engagement of potential applicants (share the information about the Calls while the EaSI work programme is in draft phase, so that the organisations have enough time to develop the idea and establish partnership); Organise thematic meetings with potential applicants and grant beneficiaries to discuss the obstacles/difficulties.

Civil Protection Mechanism: Most of the activities of the EUCPM in 2020 were focused on response to the Covid-19 pandemic; therefore, all the MS/PS shaped their activates in that way. The global phenomenon triggered a need of revision and reinforcement of the existing civil protection systems to meet the new reality. The PRD identified the critical points in the system that must be revised. And as a lesson learned, they were presented in the survey prepared in the frame of German Presidency with the European Council. The following difficulties are notified: Need of revision of the legal framework in order to develop more flexible, dynamic and adoptable system Better planning and preparedness in order to ensure timely interoperability and to minimize the crisis effects More comprehensive response is required Need of adequate and flexible budget Creation of national stockpiling of medical, but also other capacities (similar to the rescEU) Inadequate information management Better coordination in management with the international assistance Early warning, rising the awareness of the population Good practices: Synergy between the institutions and with the international partners Dynamic mobilization of the resources Joint effort Inter-sectorial approach to the crisis management and comprehensive engagement Intensive and well organized bilateral and regional cooperation Host Nation Support Activation of the EUCPM and assistance received mostly via rescEU stockpile (hosted by Germany, Austria, Romania and Greece) and from Slovakia, Estonia, Czech Republic and Sweden. Excellent communication and coordination with the ERCC

FRA: Ministry of Justice is of an opinion that the findings in the above mention documents of FRA are tools for creation of effective policy for the protection of human rights in North Macedonia. In future, more debates (platform with governmental and nongovernmental organizations for further discussion of the findings and recommendations) are recommended on the findings in the documents published by the FRA and which include North Macedonia. After the constitution of the Assembly, as well as the forthcoming appointments of the new Commission for prevention and the protection against discrimination and the Ombudsman, greater input is welcome.

COSME: Engaging more persons who will work on the Programme on regular basis; providing budget for organization of Info-days. Governmental incentives should be applied for successful participants.

Horizon 2020: Strengthening the organisational structure and human resources capacities in MES for successful implementation of the Programme. Governmental incentives should be applied for successful participants, especially for those that have projects with high score but unfinanced by EC.

Customs 2020: Active participation in program activities

Fiscalis: As the PRO is the main beneficiary of this programme; the promotion of the Fiscalis 2020 programme is done internally through the Intranet and continuous communication with the Sectors with the PRO.

Creative Europe: The pilot action Cooperation projects with WB’s countries has been recognized in our region as a successful attempt to overcome the gaps in the national policies on regional level and as an opportunity for easier access, participation, and utilization of the program. Organisation of networking events between AV and CCS professional from European countries and North Macedonia. Organisation of thematic events related to better implementation of the programme on national, regional and EU level. Development of mobility schemes with the aim to support the participation of Macedonian operators at European level.

Life+: More info days and events, trainings and workshops that will provide better knowledge and skills for the applicants to follow the procedures and prepare proposals.

# II a. Performance indicators in the sector Democracy and Governance – Support to the participation in the Union Programmes

| Financing Agreement/Programme reference | Indicator for UPs | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2014) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA 2016/039-618/01.01/MK | Country’s participation rate | Commission | 70 (2014) |  | 100 | 100 | 70 | See chapter 2 |
| IPA 2016/039-618/01.01/MK | Number of programmes for which an International Agreement has been concluded | Commission | 11 (2014) |  | 12 | 12 | 11 |  |  | 11 | 11 | 11 |
| IPA2014 /037-701.2 | Number of projects implemented by the beneficiary country | Commission | 10 (2014) | 18 | 25 | 25 | 10 | See chapter 2 |
| IPA2014 /037-701.2 | Number of Programmes in which the beneficiary country participates | Commission | 11 (2014) | 12 | 12 | 12 | 11 |  |  | 11 | 11 | 11 |
| IPA/2015/037-906.02 | Participation rate | NIPAC Report | 0 (2014) | 1 | 1.2 | 1.2 (2024) | 0 | See chapter 2 |
| IPA/2015/037-906.02 | No of concluded International Agreements | NIPAC Report | 0 (2014) | 11 | 12 | 129 | 0 |  |  | 11 | 11 | 11 |

# Democracy and Governance, EUIF

- Involvement in programming

The EU Integration Facility is programmed under the sector Democracy and Governance on annual basis, in agreement with the NIPAC. During 2019, the mandate for using the EUIF derives from the adopted 2014/2015/2017 IPA Annual Programmes and the respective EU Integration Facility Action Documents. The aim of the EU Integration Facility (EUIF) is to assist the national administration to efficiently manage the EU Integration process and pre-accession funds, by targeting ad-hoc requests by different national entities that are not covered with the relevant sector support programmes, but extremely relevant in meeting the objective of EU Accession.

The deadline for contracting of funds under the EUIF 2015 expired on 14/11/2019.  Out of allocated budget of 4.000.000 EUR, 3.977.261,79 were contracted through 16 projects, which makes 99.43% contracting rate.  The decommitted amount is 22.738,21 EUR.  The information on the contracts can be found under the Table bellow.

The EUIF 2017-2018 allocations are also planned, and the following information gives you the state of play.

| YEAR | AP 2017 | AP 2018 |
| --- | --- | --- |
| ALLOCATED | 3,909,607.00 | 5,800,000.00 |
| CONTRACTED by 31/12/2019 | 1,827,926.00 | 0.00 |
| Waiting for contract approval | 0.00 | 0.00 |
| Under Procurement by 31/12/2019 | 240,000.00 | 0.00 |
| PAID | 168,415.20 | 0.00 |
| RAC | 2,081,681.00 | 5,800,000.00 |
| RAL | 3,741,191.80 | 5,800,000.00 |
| Remainig project proposals to be financed with 2017 envelope | 1,810,000.00 | 5,800,000.00 |

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the Sector planning document)

Please refer to the different sectors.

- Coordination with other instruments and/or donors/ IFI's within the sector

Please refer to the different sectors.

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

EUIF is already an established facility that provided ad-hoc assistance for many areas that are not traditionally covered by the established IPA II sectors.  The assistance is usually used to support the national institutions in designing policy documents, implementation of strategies and capacity building activities.

# EUIF Summary table

List of contracted projects under AD 2014

| Contract | Status | Title /Contracting party | Nature | Contractor' signature date | End date of activities | Currency | Amount (EUR) | Paid (EUR) | Balance (EUR) | Under preparation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA/2016/373-268 | CL | Supply of the equipment for the Special Prosecutor's office COMPANY FOR TRADE OF GOODS AND SERVICES SAGA MK DOOEL EXPORT-IMPORT SKOPJE | SUP | 26/02/2016 | 20/05/2017 | EUR | 19,990.00 | 19,990.00 | 0.00 | 0.00 |
| IPA/2017/380-134 | EC | Support for the management of the EU funds BUSINESS AND STRATEGIES IN EUROPE | SER | 31/05/2017 | 30/05/2020 | EUR | 2,576,900.00 | 0.00 | 2,576,900.00 | 0.00 |
| IPA/2017/383-278 | EC | Quality control of produced ortho-photo maps and digitized of agriculture land use layers CARDNO EMERGING MARKETS (UK) LTD | SER | 06/03/2017 | 04/03/2019 | EUR | 99,790.00 | 0.00 | 99,790.00 | 0.00 |
| IPA/2017/383-878 | CL | Migration of old court decisions to the new Web Content Management System COMPANY FOR TRADE OF GOODS AND SERVICES SAGA MK DOOEL EXPORT-IMPORT SKOPJE | SER | 17/02/2017 | 16/09/2017 | EUR | 30,000.00 | 30,000.00 | 0.00 | 0.00 |
| IPA/2017/384-095 | EC | Technical Assistance support for the Deinstitutionalization process in social sector AGRICONSULTING EUROPE SA | SER | 23/03/2017 | 03/09/2018 | EUR | 178,740.00 | 0.00 | 178,740.00 | 0.00 |
| IPA/2017/384-799 | CL | Revision of the Industrial policy 2009-2020 POHL CONSULTING & ASSOCIATES GMBH | SER | 09/05/2017 | 01/08/2018 | EUR | 240,579.45 | 240,579.45 | 0.00 | 0.00 |
| IPA/2017/385-896 | CL | Supply of Readymade software (of the shelf) - Audit software for statistical sampling and Software for office operations and E-Archive NEKSTSENS DOO SKOPJE | SUP | 17/05/2017 | 24/07/2017 | EUR | 20,000.00 | 20,000.00 | 0.00 | 0.00 |
| IPA/2017/385-934 | EC | Development and re-engineering of business processes of the new tax integrated IT system DANSK ENERGI MANAGEMENT & ESBENDENAS | SER | 12/06/2017 | 24/01/2019 | EUR | 297,891.00 | 0.00 | 297,891.00 | 0.00 |
| IPA/2017/386-471 | EC | Upgrade of the existing Management Information System with comprehensive monitoring tool ASSECO SEE DOOEL SKOPJE | SER | 13/06/2017 | 16/04/2018 | EUR | 20,000.00 | 0.00 | 20,000.00 | 0.00 |
| IPA/2017/387-418 | EC | Supervision of works for upgrade of the customs clearance and inspection facilities at the road Border Crossing Kjafasan EPTISA SERVICIOS DE INGENIERIA SL | SER | 28/07/2017 | 30/11/2019 | EUR | 235,900.00 | 0.00 | 235,900.00 | 0.00 |
| IPA/2017/387-664 | EC | Support to Parliament in implementation of reforms IBF INTERNATIONAL CONSULTING | SER | 16/08/2017 | 03/09/2019 | EUR | 280,900.00 | 0.00 | 280,900.00 | 0.00 |
| IPA/2017/387-989 | CL | Supply of IT equipment for strengthening the capacity of the PRО – Contact Centre/Call Centre LADKANI OFFICE SOLUTIONS SAL | SUP | 14/09/2017 | 30/01/2018 | EUR | 229,675.00 | 229,675.00 | 0.00 | 0.00 |
| IPA/2017/389-189 | EC | Technical assistance for development of consumer protection policy TRANSTEC | SER | 20/11/2017 | 03/07/2019 | EUR | 262,344.00 | 0.00 | 262,344.00 | 0.00 |
| IPA/2017/390-728 | EC | A Canvas for Innovation: a way forward to strengthening the national innovation ecosystem - feasibility studies TRANSTEC | SER | 21/12/2017 | 21/05/2019 | EUR | 211,290.00 | 201,811.67 | 9,478.33 | - 9,478.33 |
| IPA/2017/391-110 | EC | Drafting a feasibility study for establishment of science and technology park DAI EUROPE LIMITED | SER | 13/12/2017 | 31/01/2019 | EUR | 174,380.00 | 0.00 | 174,380.00 | 0.00 |
| IPA/2017/394-397 | CL | Obtaining of building permission for the CBC project ''New common infrastructure at the border crossing point Beljanovce-Stancic'' TAJFA ARCHITEKTI DOOEL UVOZ IZVOZ KUMANOVO | SER | 28/12/2017 | 12/04/2018 | EUR | 29,350.00 | 29,350.00 | 0.00 | 0.00 |
| IPA/2017/394-673 | EC | Legal harmonization and capacity building for market surveillance EVOLUXER SL | SER | 26/12/2017 | 11/07/2019 | EUR | 438,000.00 | 0.00 | 438,000.00 | 0.00 |
| IPA/2018/394-037 | EC | EU Opinion Poll and EU Campaigns Assessment PRIVATE MARKET RESEARCH & POLLING AGENCY GFK SKOPJE DOOEL | SER | 06/03/2018 | 05/01/2019 | EUR | 18,700.00 | 0.00 | 18,700.00 | 0.00 |
| IPA/2018/398-639 | EC | Preparation of Needs Assessment report, Analysis of the existing legal framework and Technical Specification for supply of equipment for Upgrade of the ICT system of the National Coordinative Centre for Border Management (NCCBM) PLANET AE | SER | 26/07/2018 | 15/07/2020 | EUR | 188,690.00 | 0.00 | 188,690.00 | 0.00 |
| IPA/2018/399-367 | EC | Addendum to Technical audit for the road construction project of new motorway section Demir Kapija - Smokvica along Corridor X - Linked to contract 377865 PLANET AE | SER | 25/07/2018 | 09/11/2018 | EUR | 53,644.00 | 0.00 | 53,644.00 | 0.00 |
| IPA/2018/399-600 | EC | TA in the Evaluation of the Call for Proposals: Assessors for the Call for Proposals - IPA 2 Civil Society Facility 2019, Cross Border with Albania and European Instrument for Democracy and Human Rights BUSINESS AND STRATEGIES IN EUROPE | SER | 21/09/2018 | 31/12/2020 | EUR | 149,975.00 | 0.00 | 149,975.00 | 0.00 |
| IPA/2018/399-783 | EC | Preparation of Study for sustainable economic development possibilities in the wider Prespa/Prespes Lakes area | SER | 07/09/2018 | 15/02/2019 | EUR | 87,526.00 | 0.00 | 87,526.00 | 0.00 |
| IPA/2018/400-081 | EC | MK 14 IPA FI 01 18 TWL Strengthening the capacities of the system for fight against counterfeiting of EUR DEUTSCHE GESELLSCHAFT FUR INTERNATIONALE ZUSAMMENARBEIT (GIZ) GMBH | ACT | 08/10/2018 | 30/06/2019 | EUR | 250,000.00 | 0.00 | 250,000.00 | 0.00 |
| IPA/2018/400-138 | EC | MK 14 IPA FI 02 18 TWL Further improvement of internal control system SREDISNJA AGENCIJA ZA FINANCIRANJEI UGOVARANJE PROGRAMA I PROJEKATAEU | ACT | 19/09/2018 | 14/06/2019 | EUR | 250,000.00 | 0.00 | 250,000.00 | 0.00 |
| IPA/2018/400-324 | EC | Functional review of the Ministry for Agriculture, Forestry and Water Economy (MAFWE) INTERNATIONAL BANK FOR RECONSTRUCTION AND DEVELOPMENT | ACT | 14/09/2018 | 31/10/2019 | EUR | 500,000.00 | 0.00 | 500,000.00 | 0.00 |
| IPA/2018/400-493 | EC | Enhancing Democracy through promotion and protection of Minority Rights GFA CONSULTING GROUP GMBH | SER | 30/10/2018 | 06/07/2020 | EUR | 288,090.00 | 0.00 | 288,090.00 | 0.00 |
| IPA/2018/401-009 | EC | MK 14 IPA JH 04 18 TWL ''Standardization and harmonization according to ISO 17025 standard of the laboratories within the Institute for forensic medicine, criminalistics and medical deontology" | ACT | 11/10/2018 | 13/11/2019 | EUR | 250,000.00 | 0.00 | 250,000.00 | 0.00 |
| IPA/2018/401-076 | EC | MK 14 IPA OT 01 18 “Strengthening of the capacities of the Postal Agency” FUNDACION INTERNACIONAL Y PARA IBEROAMERICA DE ADMINISTRACION Y POLITICAS PUBLICAS | ACT | 27/11/2018 | 02/06/2020 | EUR | 600,000.00 | 0.00 | 600,000.00 | 0.00 |
| IPA/2018/403-855 | EC | Training based upon the 1999 & 2017 FIDIC Conditions of Contracts, the former Yugoslav Republic of Macedonia (MK) ECV CONSULTANCY LIMITED | SER | 12/12/2018 | 30/01/2019 | EUR | 11,450.00 | 0.00 | 11,450.00 | 0.00 |

List of contracted projects funded under AD 2015.

| Contract | Status | Title /Contracting party | Nature | Contractor' signature date | End date of activities | Currency | Amount (EUR) | Paid (EUR) | Balance (EUR) | Under preparation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA/2018/395-950 | CL | THEMATIC EVALUATION OF EU SUPPORT TO ROMA COMMUNITIES AND ROMA SOCIAL MAPPING DT GLOBAL IDEV EUROPE S. L | SER | 30/03/2018 | 31/07/2019 | EUR | 114,954.00 | 114,954.00 | 0.00 | 0.00 |
| IPA/2018/395-953 | CL | Support to Operating Structures in closure of Operational Programme for Regional Development (2007-2013) and Operational Programme for Human Resource Development (2007-2013) ARS PROGETTI SPA - AMBIENTE RISORSE E SVILUPPO | SER | 29/03/2018 | 11/04/2019 | EUR | 136,379.90 | 136,379.90 | 0.00 | 0.00 |
| IPA/2018/399-593 | EC | Support to the national authorities for effective fulfilment of the conditions stipulated in the financing agreements and audit findings regarding the implementation of IPA II assistance DT GLOBAL IDEV EUROPE S. L | SER | 16/11/2018 | 02/02/2020 | EUR | 255,186.00 | 0.00 | 255,186.00 | 0.00 |
| IPA/2018/399-662 | EC | Analysis of Secondary and Tertiary Healthcare System Effectiveness CONSEIL SANTE | SER | 27/09/2018 | 04/06/2020 | EUR | 403,280.00 | 0.00 | 403,280.00 | 0.00 |
| IPA/2018/399-970 | EC | External independent observers for supply and works tender evaluations in Environment and support to the IPA operating structure during tendering PLANET AE | SER | 02/10/2018 | 31/12/2020 | EUR | 185,600.00 | 0.00 | 185,600.00 | 0.00 |
| IPA/2019/405-472 | EC | Support to Justice Sector Reform NIRAS AS | SER | 03/06/2019 | 09/12/2020 | EUR | 916,454.00 | 0.00 | 916,454.00 | 0.00 |
| IPA/2019/405-546 | EC | Implementation of Business continuity and Disaster Recovery Data System-phase 2 RAMBOLL DANMARK AS | SER | 13/05/2019 | 12/11/2020 | EUR | 225,200.00 | 0.00 | 225,200.00 | 0.00 |
| IPA/2019/405-962 | EC | MK 15 IPA HE 01 18 TWL Harmonisation of the legislation for medicinal products with EU legislation and building capacities for its implementation | ACT | 02/04/2019 | 12/03/2020 | EUR | 250,000.00 | 0.00 | 250,000.00 | 0.00 |
| IPA/2019/406-368 | EC | Preparatory Actions for IPA 2020 Municipal Support Programme BUSINESS AND STRATEGIES IN EUROPE | SER | 05/07/2019 | 25/02/2021 | EUR | 408,650.00 | 0.00 | 408,650.00 | 0.00 |
| IPA/2019/406-405 | EC | Video/audio Service Roma Integration Award 2019 MUNLAJT DOO | SER | 03/04/2019 | 07/04/2019 | EUR | 1,200.00 | 1,200.00 | 0.00 | 0.00 |
| IPA/2019/406-445 | EC | Publication of works procurement notices in local newspapers MEDIA PLAN DOOEL SKOPJE | SER | 12/04/2019 | 11/10/2019 | EUR | 1,761.00 | 0.00 | 1,761.00 | 0.00 |
| IPA/2019/406-493 | EC | EU for You - Outreach to municipalities AGENCY FOR PUBLIC RELATIONS AND COMMUNICATON MANAGEMENT IMAGE PR DOO SKOPJE | SER | 16/04/2019 | 15/12/2019 | EUR | 19,999.00 | 0.00 | 19,999.00 | 0.00 |
| IPA/2019/407-132 | EC | Supervision of the Works Contract ''Construction works of the new Forensic Laboratory in Skopje'' SAFEGE | SER | 21/06/2019 | 19/05/2022 | EUR | 196,600.00 | 0.00 | 196,600.00 | 0.00 |
| IPA/2019/408-592 | EC | MK 15 IPA FI 01 19 Strengthening the institutional capacity of the National Bank of the Republic of North Macedonia in the process of its accession to the ESCB DEUTSCHE GESELLSCHAFT FUR INTERNATIONALE ZUSAMMENARBEIT (GIZ) GMBH | ACT | 15/08/2019 | 14/12/2020 | EUR | 600,000.00 | 0.00 | 600,000.00 | 0.00 |
| IPA/2019/410-190 | EC | MK 15 IPA TR 01 19 TWL Support for participation in the ECAA – European common aviation area HRVATSKA AGENCIJA ZA CIVILNO ZRARDPLOVSTVO | ACT | 18/10/2019 | 10/07/2020 | EUR | 249,420.89 | 0.00 | 249,420.89 | 0.00 |
| IPA/2019/411-874 | EC | Support in translation/interpretation of key documents linked to IPA programming and EU related activities EUROLINGUA DOOEL UVOZ-IZVOZ | SER | 14/11/2019 | 14/12/2020 | EUR | 12,577.00 | 0.00 | 12,577.00 | 0.00 |

List of contracted projects under AD 2017

| Contract | Status | Title /Contracting party | Nature | Contractor' signature date | End date of activities | Currency | Amount (EUR) | Paid (EUR) | Balance (EUR) | Under preparation |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA/2019/408-197 | EC | Preparation of a Long-Term National ICT Strategy 2020-2025 STANTEC | SER | 02/09/2019 | 01/06/2020 | EUR | 299,900.00 | 0.00 | 299,900.00 | 0.00 |
| IPA/2019/410-389 | EC | Review of forestry sector in North Macedonia and preparation of 2019 IPA project for forestry AGRICONSULTING EUROPE SA | SER | 15/11/2019 | 17/04/2020 | EUR | 116,176.00 | 0.00 | 116,176.00 | 0.00 |
| IPA/2019/412-001 | EC | Technical Assistance for establishing an executive body for road safety in North Macedonia PLANET AE | SER | 20/12/2019 | 19/10/2020 | EUR | 126,100.00 | 0.00 | 126,100.00 | 0.00 |
| IPA/2019/412-419 | EC | Support for the management of the EU funds - extension of contract 380-134 BUSINESS AND STRATEGIES IN EUROPE | SER | 29/11/2019 | 30/06/2022 | EUR | 1,285,750.00 | 0.00 | 1,285,750.00 | 0.00 |

II a. Performance indicators in the sector Democracy and Governance – EUIF

| Financing Agreement/ Programme reference | Indicator | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2014) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA2014 /037-701.1 | Number of projects submitted | EUD | 0 (2015) | 37 | 40 | 40 (2022) | 0 | 15 | +15 | 0 | 0 |  |
| IPA2014 /037-701.1 | Number of projects supported | EUD | 0 (2016) | 17 | 30 | 30 | 0 | 0 | 0 | 29 | 0 |  |
| IPA2014 /037-701.1 | Progress in accession | Commission | 0 (2016) | Progress in HLAD | Opening negotiation | Accession (2028) | Progress in HLAD | Progress in HLAD | Progress in HLAD | Progress in HLAD | Progress in HLAD |  |
| IPA2014 /037-701.1 | Decrease in ex ante rejection | EUD | 100 (2016) | 85 | 55 | 55 | 0 | 0 | NA | NA | NA |  |
| IPA2014 /037-701.1 | EU Funds absorption in % (only on EUIF contracted under 2014) | EUD | 0 (2016) | 25 | 95 | 95 | 0 | 0 | 0 | 99,9% | 0 |  |
| IPA/2015/037-906.01 | Public recognition of the EU support | Opinion pool | 61 (2014) | 70 | 75 | 80 (2024) | 61 | 0 | NA | NA | NA |  |
| IPA/2015/037-906.01 | Decrease in the number of ex ante controls (%) | Financing agreements | 45 (2014) | 25 | 5 | 5 (2024) | 45 | 0 | 0 | NA | NA |  |
| IPA/2015/037-906.01 | Major audit findings | Audit reports | 5 (2014) | 5 | 5 | 5 (2026) | 5 | NA | NA | NA | NA |  |
| IPA/2015/037-906.01 | IPA II Disbursement rate (only on EUIF contracted under 2015) | Accounting system | 0 (2014) | 20 | 45 | 90 (2026) | 0 | 0 | 0 | 24% | 75% |  |
| IPA/2015/037-906.01 | IPA II Contracting rate (only on EUIF contracted under 2015) | Accounting system | 0 (2014) | 30 | 70 | 95 (2024) | 0 | 0 | 0 | NA | 99.43% |  |
| IPA/2015/037-906.01 | Sector strategies implemented | Sector strategy monitoring | 0 (2015) | 15 | 40 | 95 (2026) | 0 | 0 | 0 | NA | 5 |  |
| IPA/2015/037-906.01 | Sector performance developed | Sector Reform | 0 (2015) | 3 | 7 | 7 (2020) | 0 | 0 | 0 | 0 | 0 |  |
| IPA/2015/037-906.01 | No of Sector approach developed development strategies adopted and under implementation | Sector planning | 0 (2014) | 3 | 7 | 7 (2020) | 0 | 0 | 0 | 7 | 7 |  |
| IPA 2017/040-200/01.02 | Number of project proposals submitted under the EUIF /Number of proposals approved for funding | EUIF Steering Committee reports | 28 submitted/13 approved under EUIF 2014 | NA | 30 submitted /8-10 approved | 30 submitted /8-10 approved | 0 | 0 | 0 | 0 | 62/12 (contracting deadline is 2/11/21) |  |
| IPA 2017/040-200/01.02 | Number of institutions involved in submission of proposals / Number of institutions involved in project implementation | EUIF Steering Committee reports | 1 | NA | 30 | 120 | 0 | 0 | 0 | 0 | 15 |  |
| IPA 2017/040-200/01.02 | Average length of project launch (duration from submission of project proposal until contract signature) | EUIF Steering Committee reports | 12 months | NA | 3-8 months (depending on the type of contract) | 3-8 months (depending on the type of contract) | 0 | 0 | 0 | 0 | 5m |  |
| IPA 2017/040-200/01.02 | EUIF Funds implementation rate (EUIF Contracting and disbursement rate) | Accounting systems (CRIS/ABAC/MIS) | 0.17% | NA | 80% | 100% | 0 | 0 | 0 | 0 | 46,75% (contracting deadline is 2/11/21) |  |
| IPA 2017/040-200/01.02 | Percentage of projects completed successfully, and results delivered (Number of documents adopted, Number of people trained, No of IT tools put in use etc) | EUIF reports/ project reports | 1 project (100%) (IT equipment) | NA | 70% | 100% | 0 | 0 | 0 | 0 | Project implementation ongoing |  |
| IPA 2017/040-200/01.02 | No of people that benefit from the funded actions (segregated data by gender, ethnicity, vulnerability – where possible) | Project reports | 5 (3 women, 2 men, no vulnerable groups covered) | NA | At least 120 | 200 | 0 | 0 | 0 |  | Project implementation ongoing |  |

# Environment and Climate Action

- Involvement in programming

As pointed out in the previous Annual Report, the multiannual Action Programme for Environment and Climate Change for the years 2014-2016 was adopted on the 17.12.2014. The Sectoral Operation Programme for Environment and Climate Action 2014-2020 was amended on 27.06.2018. The programme is implemented through major projects and OIS. The main information for the programming activities in 2020 are summarised in the two tables below.

| Title of the Major Projects | Status | Remarks |
| --- | --- | --- |
| Rehabilitation and Extension of the Sewerage Network of the Municipality of Kichevo – II phase and supervision activities | Approved | The Bilateral Agreement was signed on 03.02.2020. |
| Construction of wastewater treatment plant and rehabilitation and upgrading of the sewerage system in the Municipality of Bitola and supervision activities | Approved | . The Bilateral Agreement was signed on 04.03.2020. |
| Establishment of Integrated and Financially Sustainable Regional Waste Management System in East and North-East Regions and supervision activities | On-going | The revised IPA Application was sent for approval to SEA on 18.08.2020. |
| Wastewater investment project in the agglomeration of Tetovo | Suspended | MoEPP is revising the IPA application. |

| Title of the OIS | Status | Remarks |
| --- | --- | --- |
| Preparation of project documentation for improvement of Waste water collection and treatment infrastructure and water supply network in the Municipality of Arachinovo | On-going | Revised OIS was submitted to SEA on 23.05.2019 OIS was suspended on 08.07.2019 by Delegation of EU. MoEPP to decide whether to submit revised OIS to SEA/EUD. |
| Development and Implementation of Environmental Public Awareness Campaign | On-going | Revised OIS was submitted to SEA on 03.09.2019. Delegation of EU suspended OIS on 06.11.2019. MoEPP is revising the OIS and will submit the revised version of the OIS. |
| Improving capacities for Natura 2000 and CITES | Approved by Delegation of EU on 23/07/2019. Modified OIS approved by Delegation of EU on 05/10/2020. | Modified OIS was sent to SEA on 17.08.2020, with main purpose, for a change of the type of the contract i.e., instead of “fee based” to be changed into “global price” contract, which will really allow the Nature Department as final beneficiary to focus fully and professionally on the results/outputs of the project administration. Modified OIS was submitted to Delegation of EU on 25.08.2020 and approved by Delegation of EU on 05/10/2020. . |
| Development and implementation of River Basin Management Plans for all river basins (River Vardar, Crn Drim, Strumica) under the Water Framework Directive with Implementation of Measures | Approved by Delegation of EU on 06/10/2020 |  |
| Preparation of studies (FS, EIA, CBA) design documentation and tender dossiers for wastewater collection and treatment investment projects in the Municipalities of Gostivar, Kavadarci and Debar | Approved by Delegation of EU on 29/03/2020. |  |
| Technical audit for investment projects in Environment sector | Approved by Delegation of EU on 14/08/2020. |  |
| Technical audit of existing wastewater treatment plants in North Macedonia | On-going | OIS was submitted to SEA on 06/09/2019. Delegation of EU suspended OIS on 28.10.2019. Revised OIS was submitted to SEA on 18.06.2020. Delegation of EU suspended OIS on 14.08.2020. MoEPP is revising the OIS and will submit the revised version of the OIS. |
| Technical audit for investment projects in Environment sector | Approved by Delegation of EU on 14/08/2020 |  |
| Implementation of the priority actions developed under Long Term Strategy on Limitation of GHG Emission and further transposition of Climate Action legislation | On-going | OIS under preparation! |
| Supply of IT and Other Specific Equipment for Noise Monitoring Information System | On-going | OIS under preparation! |
| Direct grant to Ministry of Finance for sub-grant scheme combined with loan programme of WB and implemented by MSIP PIU | On-going | OIS under preparation! |
| Service Contract for preparation of energy audits and project documentation for energy efficiency projects in municipal buildings | On-going | OIS in phase of preparation. The service contract will serve as a basis to Ministry of Economy in their planned IPA3 project pipeline. |

In spring 2020, the programming of IPA III started. The main elaborated draft documents are as follows:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 3 – Green agenda and sustainable connectivity (Thematic Priority 1: Environment and climate change | Environmental standards (2021) EU for Clean Air (2021) EU for Prespa (2021) EU for modern wastewater system | EU for Environment standard and clean air EU for Prespa EU for modern wastewater system |

The Action Documents will contribute to achieve the Specific Objectives of Window 3 Thematic Priority 1.

- Overview of results in moving towards a fully-fledged sector approach (i.e., targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented to fully implement the roadmap are summarised.

| Strategic Planning | Self-assessment: Less than half of the targets for 2016, 2017, 2018 and 2019 and 2020 have been reached |
| --- | --- |
| Administrative Capacity | Self-assessment: Less than half of the targets for 2017, 2018, 2019 and 2020 have been reached, however for the missing ones there is a programme to achieve them |
| Coordination | Self-assessment: The targets are partially achieved, there is still work to be done to fully achieve them |
| Performance | Self-assessment: Less than half of the targets for 2017, 2018 2019 and 2020 have been achieved. However, there are programmed activities to achieve them by the end of 2021. |
| Budget | Self-assessment: Less than half of the target for 2017, 2018 2019 and 2020 have been achieved |
| Remarks: Working progress according to the procurement plan. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The following meetings of the SWGs were organised in 2020:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 17.06.2020 | This data cannot be provided since it has been a video-meeting. | Overview IPA III with Presentation of the Action Fiche/s for IPA III Action Programmes for 2021 and 2022 and Strategic Response for W 3 Green |

The information about the Donors, IFIs, Embassies and CSOs that were present at this meeting cannot be provided since it has been a video-meeting.

;

| Donors | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |

In the NATURA sector, the following programmes financed by the donors are under implementation:

| Donors | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| GEF | 3,360,731 US $ | “Achieving Biodiversity Conservation through Creation and Effective Management of Protected Areas and Mainstreaming Biodiversity into Land Use Planning. | 2016 - 2021 |
| SECO | 3,798,402 CHF | Programme for Nature Protection in North Macedonia (phase II) | 2017 - 2020 |

In the WATER sector, the following programmes financed by the donors are under implementation:

| Donors | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| SECO | 7.254.000 CHF | Construction of WWTP for the Municipality of Delcevo, extension and rehabilitation of water supply system | 2018 - 2021 |
| SDC | 300.000 CHF + 100.000 CHF (register of GW) | RBMP for Strumica and Register of GW. Additional component was added in the project for Preparation of Register for ground waters | 2016-2022 |
| WBIF | 351,750 EUR | Technical support for the PIU within PE Vodovod and Kanalizacija Skopje (related to the project for Construction of WWTP in the city of Skopje) | 2019 – 2020 |
| FASEP, France | 197.863 EUR | Assistant to the city of Skopje related to organizing the tender phase | December 2017 - December 2020 |

At present, in the WATER sector, the following loans financed by the IFIs are under implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| EBRD | 58.000.000 EUR | Construction of WWTP for the City of Skopje | 12 – 2019 – 12.2026 |
| EIB | 68.000.000 EUR | Construction of WWTP for the City of Skopje | 12 – 2019 – 12.2026 |

In the AIR Quality sector, the following programmes financed by the Donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| SIDA | 453.920 EUR | Repair and replacement instruments in strategic monitoring stations (5 stations) | 2019 - 2021 |
| IAEA | 235.990 EUR | Strengthening capacity at the central level for reduction of solid particles in the air through use of nuclear technology | 03.2020-12.2021 |
| IPA-CBC North Macedonia-Greece | 969.331 EUR (332.340 EUR-MoEPP) | Transboundary air pollution health index development and implementation | 03.08.2018-03.08.2020 |

In the sector Environment and Climate Change, the following programmes financed by the Donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| GEF (grant) | 852,000 USD | Macedonia’s Fourth National Communication (4th NC) and Third Biennial Update Report (3rd BUR) on Climate Change under the UNFCCC. The goal of the project is to assist the country in mainstreaming and integration of climate change consideration into national and sectorial development policies by providing continuity to the institutional and technical capacity strengthening process. | Sep 2018 - August 2022 |
| GEF (grant) | 1,320,000 USD | Strengthening institutional and technical North Macedonian capacities to enhance transparency in the framework of the Paris Agreement | Apr. 2019 – Apr.2022 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning, and budgeting

The IPA II has an impact in the sector either through the preparation of Action Programmes or through the implementation of TA projects or through the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning:

Administrative Capacity: The functional review of the Ministry of Environment and Physical Planning, as well as sectoral road map and indicators were prepared with assistance of the on-going project “Support for the management of the EU funds” mainly implemented trough Secretariat for European Affairs. Technical assistance has been provided through the EUD centralized framework contract "External independent observers for supply and works tender evaluations in the area of Environment and support to the IPA operating structure during tendering”. Capacities of the IPA Structure remains limited. There were no new employments in 2020 in the IPA Structure. Limited support is provided from different Sectors in MoEPP to the IPA Structure. Main support remains from the above-mentioned Technical Assistance provided through the EUD centralised Framework Contract which was extended during 2020.

Performance: Indicators for the sector were developed.

Budget:

Under indirect management by RoM:

- OS(s) in place and related changes, if relevant:

Operational Agreement for Sector Operation Programme for Environment and Climate Action was signed by NIPAC, HOS and IPA Coordinator, no. 21-2655/3 on the 26.05.2017. New Systematization Act of Ministry for Environment and Physical Planning was taken in May 2017. IPA operational structure is part of the Department for EU and one Project Implementation Unit for Infrastructure Projects (PIUIPs) within MoEPP for implementation of infrastructure projects funded by IPA.

Operating structure within the Ministry of Environment and Physical Planning includes nine (9) employees from which the designated IPA coordinator/SPO that is Head of EU Department, Head of Unit for Programming and Monitoring of implementation of the Instrument for Pre-Accession Assistance (IPA) and seven (7) employees on positions of advisors, senior and junior associates.

- Information on the implementation of Action programmes under indirect management in the sector

To update the dates of different stages of the procurement procedure and some other minor changes in titles, types and values of the projects, IPA II Procurement Plan has been revised and adopted by CFCD on 24/12/2019, submitted to MoEPP on 09/01/2020. Additionally, MoEPP revised IPA II Procurement Plan in August 2020, but this version was not adopted by CFCD. New revised IPA II Procurement Plan was prepared in December 2020, adopted by CFCD, and submitted to MoEPP on 05/01/2021.

Published Prior Information Notices

- Support in the Implementation of Air Quality Directives (11/02/2020);

- Supervision of the works contract for Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola (18/02/2020);

- Development of Strategic Noise Maps and Action Plans with Programs of Measures (29/06/2020).

- Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo(13/10/2020).

- Implementation and Planning for the Approximation in Priority Areas of Environment(11/11/2020).

- Supporting the Implementation of the Regional Waste Management Systems in the East and North-East Regions(11/11/2020).

Published Contract Notices

- Supervision of the works contract for Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola (23/03/2020);

- Support in establishing Regional Waste Management System - Supply of equipment for waste collection in East and North-East Regions, Phase I (15/06/2020);

- Support in the Implementation of Air Quality Directives (24/06/2020).

Evaluation procedures

- Support in the Implementation of Air Quality Directives;

- Improved Implementation of the EU Floods Directive through Harmonization of National Legislation and Preparation of Flood Risk Management Plans;

- Supporting the implementation of the regional waste management systems in the East and North-East Regions;

- Supervision of the implementation of the works contracts for Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo;

- Supervision of Works Contract for Closure of Non-compliance Landfills and Dumpsites in East and North-East regions - First Phase;

- Supervision of the works contract for Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola;

- Support in establishing Regional Waste Management System - Supply of equipment and vehicles for waste collection in East and North-East Regions, Phase I;

- Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo and

- Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola.

Tender documentation prepared and under procedure of approval.

- Implementation and Planning for Approximation in Priority Areas of Environment.

- Supporting the IPA Operating Structure in Project Planning and Finance Management in Environment Sector;

- Improving capacities for Natura 2000 and CITES ;

- Supporting the implementation of the regional waste management systems in the East and North-East Regions;

- Support in the implementation of the waste management legislation and extended producer responsibility scheme.

- Further Support in the Implementation of the Reforms in the Water Sector ;

- Development of Strategic Noise Maps and Action Plans with Programs of Measures ;

- Supply of IT and other specific equipment for Environmental Monitoring and Information System ;

- Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo;

- Support in establishing Regional Waste Management System - Supply of equipment for waste collection in East and North-East Regions, Phase I;

- Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Bitola.

- Supply of Specific Equipment for Water Monitoring Information System ;

- Construction of WWTP and Rehabilitation and Upgrading of the Sewerage Network in the Municipality of Tetovo ;

- Establishment of Integrated and Self Sustainable Waste Management System in East and North-East Regions ;

- Supply of Office and Technical Equipment and ICT software for the OP Structure of MoEPP for the implementation of the SOPECA 2014-2020.

- Support in the implementation of the waste management legislation and extended producer responsibility scheme.

- Preparation and revision of the National Waste Planning documents and

- Support and preparation of necessary documentation for Supply of Water Equipment for Municipalities of Radovish, Kichevo, Strumica, Bitola, Tetovo, Berovo, Kumanovo and Prilep.

- Main achievements in the sector

The main achievements in the sector that are connected to the implementation of projects under indirect management are presented in the table below. In this table there are two categories of projects, the projects that are already completed and the projects that are under implementation but have already achieved significant results.

| Contract title | Status | Expected result | Achieved result | Remarks |
| --- | --- | --- | --- | --- |
| Supervision of the implementation of the works contract for Improvement of the Wastewater Collection Infrastructure in the City of Skopje | On-going | To improve city wastewater collection infrastructure in compliance with the directive 91/271/EEC through supervision of construction of 3 sections of wastewater collection system. | -Work Plan for supervision (Inception phase) (prepared). - Manual for supervision (Inception phase) (prepared). - Inspection reports during the Implementation period prepared. -Construction works supervision and checking in accordance with FIDIC Conditions of contract. - Verification and checking of all necessary documents prepared by the Contractor - Inception Report - First (6 months) Interim Report - Second (6 months) Interim Report - Third (6 months) Interim Report - Fourth (6 month) Interim Report - Fifth (6 month) Interim Report - Invoice No.1 in amount of 137.225,00 Euro - Invoice No.2 in amount of 147.125,00 Euro - Invoice No.3 in amount of 105.050,00 Euro - Invoice No.4 in amount of 148.215,00 Euro - Invoice No.5 in amount of 108.527,00 Euro - Addendum No. 1 was signed on 28.05.2018. - Addendum No.2 was signed on 14.08.2020. | There has been a delay in the project activities due to the delay of the works contract activities i.e., construction activities. |
| Improvement of the Wastewater Collection Infrastructure in the City of Skopje | On-going | To improve city wastewater collection infrastructure in compliance with the directive 91/271/EEC through construction of the wastewater collection infrastructure (3 Sections). | At the end of November 2019 (last Monthly Brief received up to date, time elapsed is 39,6% (289 days of 730 in total). Certified laid pipes 2079 m. IPC no.1 in amount of 814.470,5 EUR (executed works) has been paid. IPC No.2 in amount of 704.469,31 EUR (executed works) has been paid. IPC No.3 in amount of 614.207,88 EUR (executed works) has been paid. IPC No.4 in amount of 469.327,24 EUR (executed works) has been paid. IPC No.5 in amount of 298.867,37 EUR (executed works) has been paid. Addendum no.1 for reducing the minimum amount of IPC signed on 26.06.2019. Based on the Monthly progress report no. 31 prepared by the Contractor (November 2020) total executed works is 89,1% - 7.594 m of 8.524 m. total. The project used to be finished on 14.02.2020. IPC no. 6 in amount of 677.942,92 EUR (executed works) has been paid. IPC no. 7 in amount of 383.947,33 EUR (executed works) has been paid. IPC no. 8 in amount of 728.320,07 EUR (executed works) has been paid (approved by the MOEPP on 06.11.2020) VO 3 (amount of 56.904,26 E) and VO4 (amount of 28.458,2 E) have been approved on 16.11.2020 by the MOEPP VO 5 (amount of 28.000,00 E) has been approved by MOEPP on 24.11.2020. VO 6 (amount of 432,00 E) has been approved by MOEPP on 20.11.2020. | There is a delay in implementation of the project. |
| Development of Environmental Monitoring and Information System | On-going | To strengthen capacities for monitoring, data collection, data management and reporting through establishment of national environmental information system and monitoring network structure. | The Contract was signed on 10.03.2019 with Contractor Particip GmbH in consortium with Asseco SEE DOOEL (MK). Addendum No.1 regarding replacement of KE 1: Team Leader was sent to EUD on 06.09.2019 and was approved on 30.09.2019. The implementation of this Contract (Contract No. 12-1486/1) has been started. Addendum No.1 regarding replacement of KE 1: Team Leader was sent to EUD on 06.09.2019 and was approved on 30.09.2019In the reporting period there are submitted Inception Report and two Interim Reports. Also, in the reporting period were approved the proposed for non-key experts. Addendum No.2 regarding replacement of KE 3: was approved on 30.12.2020. Amount paid as of October 2020: EUR 392.510 Payment for the First Interim Report (Financial Report) is 118.700,00 EUR on 31.03.2020 Payment for the Second Interim Report (Financial Report) is 93.191,40 EUR on 31.12.2020 |  |
| Preparation of Long-term Strategy and Law on Climate Action | On-going | To support the Country in achieving the long-term goals of climate action: full transposition/implementation of the EU acquis, achieving a low emissions and climate resilient development | The Contract was signed on 15.02.2019 with Contractor GFA Consulting Group GmbH. The implementation of this Contract (Contract No. 12-530/1) has been started. Amount paid as of November 2019: EUR 459.921,6. In the reporting period there are submitted Inception Report and draft of different assessment reports/outputs. Addendum No.1 for time-extension was approved on 24.06.2020. Time duration of the implementation of the Contract with Addendum was extended to 15.11.2020. Amount paid as of February 2021: EUR 459.921,6. |  |
| Support in Establishing Regional Waste Management System - Supply of waste collection vehicles - LOT 1 | on-going | To optimize waste collection services to ensure that services are delivered timely to the citizens and that waste will be delivered to the designated sites thus protecting the environment from uncontrolled waste disposal | The Contract was signed on 25.11.2019 with Contractor Excelor Holding Group EOOD in consortium with Pişirgen Makina Imalat Sanayi Demir Saç Profil Ticaret Limited Şirketi. Provisional Accpetance is signed on 14.12.2020. |  |
| Supervision of the implementation of the works contracts for Rehabilitation and Extension of Sewerage Network in the Municipality of Kichevo |  | To improve city wastewater collection infrastructure in compliance with the directive 91/271/EEC through supervision of construction of wastewater collection system. | The Contract was signed on 07.02.2020 with Eptisa Servicios de Ingenieria S.L. (ES) in consortium with Eptisa South East Europe d.o.o (SR). Administrative order for suspension issued on 02.10.2020 for 90 days. | The project has not been started because the Works contract is not yet signed. |
| Closure of non-compliant landfills and dumpsites in East region – LOT 1 |  | To improve the East region waste management in compliance with Directive 1999/EU | The Contract was signed on 03.03.2020 with Contractor GOKSIN INSAAT LTD – Bursa, (TR) in consortium with ESKAVATORI MK DOOEL SKOPJE. There are two administrative orders for suspension of commencement date. | The project has not been started because the Supervision Engineer is still not appointed. |
| Closure of non-compliant landfills and dumpsites in NorthEast region – LOT 2 |  | To improve the East region waste management in compliance with Directive 1999/EU | The Contract was signed on 05.03.2020 with Contractor STRABAG Umwelltehnik GmbH (DE) in consortium with STRABAG AG (AT). There are two administrative orders for suspension of commencement date. | The project has not been started because the Supervision Engineer is still not appointed. |
| Support in establishing Regional Waste Management System – Supply of equipment for waste collection in East and North- East Region, Phase1 LOT 2 |  | To optimize waste collection services to ensure that services are delivered timely to the citizens and that waste will be delivered to the designated sites thus protecting the environment from uncontrolled waste disposal. | The Contract was signed on 24.12.2020 with Contractor AGT S.P.A with capacity provider: Teksin Kontenyer ve Galveniz Sanayi Ticaret Limited Sirketi |  |

- Recommendations for further actions

The main recommendations according to the last 5th Monitoring Committee held on the 29.10.2020 via WebEx platform are as follows:

Operational conclusions:

- Continue with the monthly progress review meetings, as of November 2020.

- The good practice that existed under IPA 1 with CFCD preparing statistics and overviews on the procurement processes (statistics and rejections rate), should be applied to IPA 2 as well. On quarterly basis, CFCD will send it to the EU Delegation.

- On short term, the MoEPP should provide for more flexible arrangements and undergo an internal redistribution of tasks for its staff to ensure that IPA unit is receiving the appropriate support from the technical departments of the ministry (such as those in charge with nature, water, waste) in revising the tender documents, by December 2020. On a medium term, 16 competent staff with required technical knowledge and English language proficiency should be hired to fill in the vacant positions in 2021.

- Timely approve evaluation committee members, ensure regular presence of the members of the evaluation committee, and ensure integrity and ethics in evaluation. The nomination of evaluation committee must be submitted to EU Delegation 1 month prior to the deadline for submission of offers. Evaluation committees must provide at least 2 alternates voting members, 1 chairperson and 1 secretary alternates with relevant technical and language skills. If persons found not to participate in evaluation committees directly inform the cabinet. Regarding the conclusion derived from the JMC on integrity of the tendering and evaluation SEA and CFCD proposed an Information in the Government in which there is an explanation on the rules that apply for the functionally of the evaluation committee members including the nomination of the members and the full working hours until the evaluation is concluded. The Information is horizontal and will cover all the tendering documentation in indirect management mode.

- Take mitigating measures to ensure smooth evaluation by end of 2020. These could be but not limited to oblige the evaluators to work full time on evaluations, e.g., from Monday to Friday, or create a national fund tool to be used for organising and conducting evaluation committees. The national authorities will provide information on the mitigating measures taken by the end of November. [13 October Gov took decision to organise such fund. Now looking for the models how to do it. - SEA to further specify as per the SMC discussion]

- Government to take a decision related to the future of the major project “Skopje collector”, by end-November 2020. The bi-lateral agreement to be modified in the light of the delays generated.

- To submit the major application and Tender Dossier for Tetovo Wastewater investment project by the end of 2020.

- To revise the tender dossiers for the cancelled tenders including Bitola Wastewater investment project and to submit them to CFCD by end of November 2020.

- To submit to EUD for ex-ante approval all pending tenders related to solid waste investments by end of 2020.

- To accelerate all necessary actions of municipalities for ensuring the sustainability of the major project investment (land acquisition; operationalise the regional waste management boards and establish the Regional Waste Management Company for East and Northeast Regions) by end of 2020. Tenders to be launched only upon all pre-conditions are met.

- To address the Audit Authority's and other audit findings and recommendations, within the deadline agreed between the auditors and the auditees. Continuously decrease the open findings in follow-up audits with target of 70 % fulfilled findings until the next SMC.

- Capacities of inspection services, especially of the ones on local level, should be increased. Better coordination between the central and local level should also be demonstrated. Adoption of the Law on environmental inspections should take place by end-Marc.

# II a. Performance indicators in the Environment and Climate Action sector covering both direct and indirect management.

Indicators per programme

| Financing Agreement/Programme reference | Indicator for sector Environment and Climate Action | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2014) | Value (2015) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP indicator | Quality of energy supply (WEF) 1 = Not reliable and 7 = Fully Reliable | World Economic Forum | 4.60 (2010) |  |  |  | 4.95 | 4.90 |  |  | No longer available for MK | No longer available for MK | No longer available for MK |
| IPA/2014/037702.3 | 2. No of pilot measures for sustainable use of natural resources prepared. | IPA Report | 0 (2015) | 0 | 20 | 20 (2025) | 0 | 0 | 0 | 0 | Circa 20 under finalisation | 20 under finalisation (in May 2020) | 20 |
| IPA/2014/037702.3 | 1. No of pilot measures for climate change and energy efficiency prepared. | IPA Report | 0 (2015) | 0 | 20 | 20 (2025) | 0 | 0 | 0 | 0 | 0 | 0 | 0 (Analysed 63. Under development 5) |
| IPA/2014/037702.1 | 9. Completion of sector-based approach conditions/framework | EUD Regular assessment | 0 (2014) | 80 | 100 | 100 (2020) |  |  |  |  | In time | In time | In time |
| IPA/2014/037702.1 | 8. Availability of information to public, decision making and reporting | European Institutions | Basic (2015) | Advancing | Advanced | Very Advanced (2025) | Basic | Basic | Good | Good | Good | Good | Advanced |
| IPA/2014/037702.1 | 7. Institutions responsible for approximation of environmental legislation in priority areas capable to undertake approximation tasks | EU Progress report | Early stage (2015) | Early stage | Advanced | Very Advanced (2025) | Early stage | Early stage | Early stage | Improved but still at early stagy | Improved but still at early stagy | Improved but still at early stagy | Improved, but still at early stage |
| IPA/2014/037702.1 | 6. Completion of environmental statistics framework | SSO | 20 (2015) | 20 | 80 | 80 (2022) | 20 | 20 | 20 | 20 | 20 | 20 | 20 |
| IPA/2014/037702.1 | 5. % of actions completed/implemented in the strategic framework | Ministry of Environment | 0 (2015) | 10 | 80 | 80 (2025) | 10 | 13 | 15 | 20 | 20 | …. | ….. |
| IPA/2014/037702.1 | 4. % of natura 2000 territories identified | MoEPP Report | 0 (2010) | 25 | 70 | 70 (2025) | 0 | 0 | 3,99 % | 3,99 % | 3,99 % | 3,99 % | 4.06% |
| IPA/2014/037702.1 | 3. Number of laws, by-laws and implementing acts in compliance with EU legislation developed (new or amended) | MoEEP | 0 (2010) | 126 | 200 | 200 (2025) | 24 | 28 | 32 | 36 | 36 | 36 till 2018 plus 10 under development | 19 in procedure of adoption |
| IPA/2014/037702.1 | 2. Number of planning documents developed | MoEEP | 0 (2010) | 8 | 13 | 13 (2025) | 2 | 2 | 4 | 8 | 8 | 8 | 8 + 1 in consultation phase (National Waste Management Plan) |
| IPA/2014/037702.1 | 1. Level of transposition of environmental legislation | EC | 69 (2014) | 70 | 85 | 85 (2025) | 69 | 69 | 69 | 69 | 69 | 69 | 69 |
| IPA/2014/037702.2 | 6. Number of new constructed landfills in East and North-East Regions | MoEPP | 0 (2012) | 0 | 1 | 1 (2025) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| IPA/2014/037702.2 | 5. Km rehabilitated and extended of sewerage network | MoEPP and PUC | 0 (2012) | 69 | 96 | 96 (2025) | 0 | 0 | 0 | 0 | 0 | 4,7 | 7,5 |
| IPA/2014/037702.2 | 4. WWTPs meeting the EC required criteria constructed | MoEPP and PUC | 0 (2012) | 0 | 0 | 2 (2025) | 0 | 0 | 0 | 0 |  | 0 | 0 |
| IPA/2014/037702.2 | 3. % of household served with waste collection service | MoEPP and SSO | 70 (2012) | 70 | 80 | 85 (2025) |  |  |  | 0 | 0 | 0 | 0 |
| IPA/2014/037702.2 | 2. % of households connected to the wastewater treatment plants for agglomerations above 10 000 p.e. | MoEPP and SSO | 12.5 (2012) | 24.5 | 31 | 25 (2025) |  |  |  | 15% (including WWTPs in Strumica and Gevgelija | 15% (including WWTPs in Strumica and Gevgelija | > 15% (including Kocani) | > 15% (including Kocani) |
| IPA/2014/037702.2 | 1. % of household connected to sewerage systems. | MoEPP and SSO | 65 (2012) | 70.8 | 75 | 80 (2025) | 65 | 65 |  | 70.8 |  | 0 | 0 |

# Transport

- Involvement in programming

As pointed out in the previous Annual Report, the multiannual Action Programme for the Republic of Macedonia for the year 2014 - 2016 was adopted on the 17.12.2014. The programme was amended on 29.11.2017. The programming in the sector transport was done in close coordination with all the relevant sector institutions: Public enterprise for state roads, Public Enterprise Macedonian railways Infrastructure, Macedonian Railways Transport Ltd and with the CFCD (Ministry of Finance). All the relevant stakeholders were also a part of the Sector working group.

The programme is implemented through major projects (with a value above 10 mil EURO) submitted for approval through IPA applications and other projects with a value below this amount (submitted for approval through OIS). The main information for the programming activities in 2020 are summarised in the two tables below.

| Title of the Major Projects | Status | Remarks |
| --- | --- | --- |
| Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d, | Approved | Works Contract No. 12-4986/1 with TirrenaScavi S.p.A., Italy signed on 21.09.2017 in process of Assignation |
| Supervision of the Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d, | Approved | Service Contract No. 12-5554/1 with Egis International, in consortium with Egis d.o.o. Beograd - Stari Grad and Hill International N.V., France signed on 02.10.2017 and under implementation |

In 2020, one OISs was approved by the EUD,

| Title of the OIS | Remarks |
| --- | --- |
| Development of Implementation plan under the National Transport Strategy 2018-2030 with system, tools and capacity for its monitoring | Approved by EUD 18.06.2020 |

# According to the Country Strategy Paper for IPA II for 2019, the available amount for Transport in 2019 was EUR 40.049.177.

The key strategic documents for the transport sector and its related sectors are already in place. The NTS 2018-2030 recognises the importance of the Transport Community Treaty-TCT, thus the country remains committed to aligning with the transport acquis as well as related standards well before accession, aiming to integrate the national transport market within the transport market of the European Union.

One of the key objectives in the transport sector in the coming period is to reduce the GHG emissions from the transport which is in line with the European Green Deal. With support, financing and implementation of concrete measures as set in the NTS 2018-2030, contribution could be made to reducing pollution in the country and re-thinking growth that is mindful of the environmental limits.

The transport sector strategic documents and cross-sectoral planning documents are in line with the objectives of 2030 Agenda for Sustainable Development, thematic priority No 9: Industry, innovation and infrastructure and thus aims to improve connectivity, reduce transport emissions and support efficient transportation services as a key driver of economic development. The National State statistical office is producing and integrating a set of indicators that provide statistical support for monitoring the degree of implementation of the concept of sustainable development in the country.

Planned areas of intervention and key-priorities for the period 2021- 2027, in line with the NTS 2018-2030:

- Construction of new and reconstruction, rehabilitation, and modernization of existing railway links along the Core and Comprehensive network according to the EU technical standards to provide quality and safe TEN-T connections with the neighbouring EU members and the wider region in the Western Balkans.

- Construction of new and reconstruction, rehabilitation, upgrading and modernization of the road network on the Core and comprehensive network according to the EU technical standards to provide quality and safe TEN-T connections with the neighbouring EU members and the wider region in the Western Balkans.

- Support multimodality and sustainable transport systems, with stronger integration of various transport modes.

- Improvement of the road and rail safety, through intervention in infrastructure and soft measures implementation, including but not limited to preparation of strategic documents, capacity building of the relevant stakeholders, improvement of the administrative capacities, communication activities and campaigns, surveys, and analysis etc.

- Promoting modal shift through advancement of transport services with quality and innovations as well as improvement of availability, affordability, and accessibility of the transport services, to the vulnerable groups.

- Further reducing the transport impact on the environment through introducing and supporting green transport modes and increasing transport and infrastructure efficiency with using smart and IT tools.

- Advancement of sector planning and development through preparation of sector and project documentation (planning documents, project preparation studies such as feasibility studies, cost-benefit analyses, environment impact assessments, design documentation, tender documentation).

- Further elevation and advancement of the transport sector integration to the EU transport area with approximation of the legal framework with the EU acquis and EN standards and increasing transport stakeholder capacity to assume the obligations of an EU membership.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap are presented. In the table below, the achieved targets and the concrete actions that are going to be implemented in order to fully implement the roadmap are summarised.

| Strategic Planning | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| --- | --- |
| Administrative Capacity | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached |
| Coordination | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| Performance | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| Budget | Self-assessment: Most of the targets for 2017, 2018,2019 and 2020 have been reached |
| Remarks: The commitment for the Sector Based Approach is good and is confirmed with the adoption of the National Transport strategy 2018-2030 adopted in December 2018 and the functioning of well-structured institutional set-up, among other the Sector Working Group for Transport. Administrative capacity: On the 15th meeting of the Subcommittee on Transport, Environment, Energy, and Regional Development held in March 2019 between the European Union and the Republic of North Macedonia joint conclusions were agreed. Two of them are related to the new National transport strategy 2018-2030 specifically addressing the administrative capacity: 1. The Commission recommended to the national authorities that drafting of strategies and legislation need to be accompanied by a proper stakeholders’ consultation, by the allocation of resources adequate to the objectives of the strategy, to favour quality over speed, to improve data collection statistics and to ensure a monitoring mechanism for the implementation of the strategy. 2. Adequate staffing will be ensured for the implementation of the National Transport Strategy 2018-30 and keep the Commission regularly informed once a year. Also on the 16th meeting of the Subcommittee on Transport, Environment, Energy, and Regional Development held in March 2020 between the European Union and the Republic of North Macedonia the previous agreed joint conclusions continued. i.e.” Strengthen operational and administrative capacity for all modes of transport (continuous)” SOPT management capacity regarding the existing OS/ sector for EU staff needs improvement in terms of trainings and retention policy, as well engagement of new staff according to the WLA (Workload Analysis) and the Recruitment plan. Coordination mechanism is good, tasks and responsibilities are clear per Ministerial decision, and rules of procedures are drafted. However, the motivation and feedback of the SWGT members is below expectation. Administrative capacity: Based on lessons learned, the NTS 2018-2030 foresees transparent institutional settings for the NTS interventions (incl. those under the SOPT) monitoring and reporting. Coordination: Within the NTS 2018-2030, more accurately within the Monitoring and evaluation chapter, an online data platform (IT application tool) is foreseen to be created. This tool will automatically collect, systematise and produce a Report, which will be used for the regular progress reporting of the strategy. Innovative management tools, to improve motivation of SMC members, needs to be explored. All other targets formulated under the Road map were met. |

- Coordination with other instruments and/or donors/ IFI's within the sector

As per the guidelines of the NIPAC, the Ministry of Transport and Communications starting with the meeting on May 11th, 2018 invited the donors (IFIs) involved in the sector transport (World Bank, EBRD, KfW, USAID). After setting up of the reformed SWGT, the representatives of donors are included and regularly invited to the meetings. The World Bank and the EBRD were also consulted in the process for preparation of the National Transport Strategy 2018-2030, were also invited to the event for public consultation for the new Transport strategy 2018-2030 and were present to the meeting of the SWG themed for the strategies’ indicators. They were also present at the meeting of the SWGT held in 2020.

The following meetings of the SWGs were organised in 2020:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| July 2nd, 2020 | 35 | Presentation of the Strategic response for sector Transport for IPA 3 and - Presentation of road and rail project-proposals (Action Fiches-AF) for the financial years 2021 and 2022 under IPA3 |

The following donors, IFIs, Embassies and CSOs were present at these meetings;

| Donors | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| EU Delegation | World Bank | / | / |
| WBIF |  | / | / |

In the sector Transport, the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| European Union (IPA) | 109 mil EURO | Rail transport infrastructure, Road transport infrastructure, Horizontal assistance in the transport sector | 2014-2020 |

At present, in the sector Transport the following loans financed by the IFIs are under implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| World Bank | 135 mil EURO | Modernization of the road network infrastructure in the Republic of Macedonia | 2014-2023 |
| EBRD | 275 mil EURO | Modernization of the road network infrastructure in the Republic of Macedonia | 2014-2023 |
| EXIM Bank | 580 mil EURO | Construction of motorways | 2014-2021 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II has an impact in the sector either through the implementation of Action Programmes or through the implementation of TA projects or through the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning: With a GoRM decision, NTS 2018-2030 was adopted in December 2018. The first report to the Government was submitted and adopted by the Government in November 2020.

Administrative Capacity: Additional measures were formulated under the NTS 2018-2030 aiming to improve monitoring and assessment capacity and to strengthen the NTS 2018-2030 monitoring.

Performance: Under IPA 2014-EU Integration Facility “Support for the Management of the EU funds Project”, in cooperation with the EU department in the MoTC indicators for the Performance Assessment Framework (PAF) were developed to back up the new NTS 2018-2030 including targets and milestones, information sources and data collection procedures (incl. actors, roles and responsibilities and frequency/deadlines). Additionally, in 2020 a project for Development of Implementation plan under the National Transport Strategy 2018-2030 with system, tools and capacity for its monitoring was launched.

Budget: Multi annual budget plan updated (and implemented) for 2020, The Procurement plan 2014-2020 is based on the approved IPA funds for the period 2014- 2019. The procurement plan was revised in July 2020 and in December 2020 ccoridng to the latest developments in the programming of the projects and allocation of funds.

Under indirect management by RoM:

- OS(s) in place and related changes, if relevant:

The sector structure includes all the relevant institutions in the sector transport: The Ministry of Transport and Communications as a lead coordinating institution, the CFCD as a contracting authority and head of operating structure, the NIPAC office, the Public enterprise for state roads, Public Enterprise Macedonian railways Infrastructure, Macedonian Railways Transport Ltd as final beneficiaries of the projects implemented under IPA II. Operational Agreement was signed between NIPAC, HOS, IPA Coordinator and PIU coordinator in PESR. Operational Agreement for the Sector Operational Programme Transport 2014-2020 was signed between NIPAC, HOS, IPA Coordinator and PIU coordinator in PE for railway infrastructure with ref. No. 12-8646/1 from 14.12.2020 (MF), No. 45-6976/4 from 22.10.2020 (MoTC), No. 1707-5196/1 from 25.11.2020 (PEMRI), No. 11-48/48 from 16.10.2020 (SEA).

Workload analysis is prepared annually for a three-year period for the IPA structure in the Ministry of Transport and Communications. According to the latest IPA WLA for 2020 it is indicated that additional 3 employments are necessary (2 in the programming unit and 1 in the monitoring unit).  In 2020 with a Decision on assignment of civil servants/employees, working post Head of IPA Monitoring Unit is filled.

According to the EC Annual Progress Report for Republic of North Macedonia for 2020, the country is moderately prepared in transport. Limited progress was made in the reporting period but only in relation to connectivity. Increased political commitment is still required to deliver on necessary sectoral reforms and more efforts are needed to strengthen the administrative and operational capacity for all modes of transport. There was no progress in completing key sector reforms and the 2019 recommendations remain valid. In the coming year, the country should: strengthen the operational and administrative capacity of the inspection bodies and develop enforcement capacity to reduce fatalities along road and rail infrastructure; implement the connectivity reform measures on rail reform and open the rail transport market, set up a national system to continuously collect data on road crashes, and finalise pending border crossing agreements/protocols; adopt legislation on Intelligent Transport Systems (ITS) and combined transport, and make further efforts to produce a strategic framework for implementing ITS and the core networks.

On general transport acquis, the key strategic documents for transport and its sub-sectors are already in place. The 2018-2030 national transport strategy does not yet have a dedicated action plan. There was no progress in strengthening the operational and administrative capacity for all modes of transport. The Law on air and railway accident investigation is already in place. However, there are still delays in setting up the independent rail accident investigation body. Further efforts are needed to implement the EU passenger rights legislation in all modes of transport. Further efforts are also needed to fully transpose the

Intelligent Transport System (ITS) Directive and introduce the relevant national laws. An overall strategy for ITS with accompanying resources is needed.

The country maintains a good level of preparation in transport networks. Limited progress was achieved during the reporting period. There was no progress in completing sector reforms and the 2019 recommendations remain valid. In the coming year, the country should in particular: further strengthen the operational and technical capacity of all management and stakeholder institutions dealing with the development of both Trans-European Transport (TEN T) and Trans-European Energy (TEN E) networks and harmonise the legal framework with the Trans European Network Regulation; mobilise sufficient resources to implement the Transport Community Treaty; sign the pending Railway Border Crossing Protocol with Kosovo.

On transport networks, the country actively participates in the Transport Community Treaty and is actively involved in its meetings. The authorities of North Macedonia authorities are encouraged to intensify cooperation under this Treaty. As a reaction to the COVID-19 pandemic, green corridors were established and are functioning effectively throughout the major corridors.

.In the Chapter 22: Regional policy and coordination of structural instruments the following was found: The country is moderately prepared in the area of regional policy and coordination of structural instruments. Some progress was made in strengthening the national capacity for strategic planning and sector-based programming and monitoring. The established management and control systems are functional and support the implementation of the Instrument for Pre-accession (IPA). In the coming year, the country should in particular: upgrade the administrative and technical capacity across the IPA operating structures, adopt a retention policy and improve the dynamics in implementation of the EU-funded

projects, particularly in the areas of transport and environment; strengthen significantly the regional development policy, improve the financial instruments put in place for its implementation and improve the administrative capacity at central and local level; ensure the sustainability of project results.

Currently in the Ministry of Transport and Communications, Department for EU there are IPA programming and project preparation unit and IPA Monitoring unit, which currently count 6 (six) employees and according to the WLA for 2020 the optimal number of employees is 9 (nine). The WLA showed that 3 (three) additional employments are needed: 1 (one) in the unit for monitoring of contracts and 2 (two) in the unit for project preparation.

However, to strengthen the administrative, operational and technical capacity, the stakeholders will need to decide on new jobs, new trainings and new staffing in other units as well, which are of paramount importance . The EC progress reports, and the SAA subcommittee conclusions also state that it is necessary to “Mobilize sufficient resources for the implementation of the Transport Community Treaty”. It must be stressed that for all of this to be effective, the so far non-existing retention policy needs to be building up. This especially is essential in this sector considering the experience needed and the length of a single project considered not ignoring the length of a single programme or a strategy on which all falls onto.

More specifically, the MoTC should focus to capacity building (mobilization of resources and administrative capacities) for monitoring the implementation of the agreement that will cooperate with the bodies of the Transport Community. The ministry should already have the administrative capacity in order to cope with the huge number of obligations to be fulfilled, that will arise prior and after the assessment mission envisaged in the protocol of this treaty. Having in mind the aforementioned, a quick intervention from the aspect of building administrative capacities is needed also to ensure proper National Transport Strategy 2018-2030 monitoring and implementation.

- Information on the implementation of Action programmes under indirect management in the sector

The procurement plan was adopted on January 8th, 2016. The last revision of the procurement plan and the amendments were adopted on December 27th, 2019. Amendments to the plan were submitted in 2020 twice from MoTC to CFCD (July and December) for adoption.

Under IPA II until now, there are three priority actions financed in the sector transport: (i) rail transport infrastructure, (ii) road transport infrastructure and (iii) horizontal sector assistance. Until now there have been activities implemented for the following projects:

- Priority action 1 Rail transport infrastructure

- Construction of rail section from Kriva Palanka - Border with Republic of Bulgaria – Draft IPA application for Major project is prepared in cooperation with JASPERS and submitted to the EUD on 20.03.2020 and comments received by EUD on 27.05.2020. The amended IPA application was finalized by the PE Macedonian Railways Infrastructure in cooperation with MoTC, MF, JASPERS in December 2020.

- Priority action 2 Road transport infrastructure

- Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d, works Contract No. 12-4986/1 with TirrenaScavi S.p.A., Italy signed on 21.09.2017

- Supervision of the Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d, service contract No. 12-5554/1 with Egis International, in consortium with Egis d.o.o. Beograd - Stari Grad and Hill International N.V., France signed on 16.10.2017

- Rehabilitation of State road A2, section Kumanovo – Stracin (phase 1) – OIS was approved on 23.01.2019. Tender procedure launched for the service contract for supervision and for the works contract for rehabilitation. An agreement has been signed with the consortium Hidrostroj and Excavators on 10.08.2020. A signed road rehabilitation contract was submitted by CFCD to the selected bidder Consortium Hidrostroj and Excavators. The company submitted a guarantee and signed the contract on 14.09.2020. On 20.10.2020 it was sent by the CFCD to the Contractor Administrative Order No. 1 (Administrative order) which stops the work without financial implications until the selection of the Supervisor.

- Construction of new expressway from Prilep – bridge on Lenishka river and Construction of third lane of road section from village Belovodica – Mavrovo quarry – Tender for the service contract for supervision was launched. The tender dossier for the works contract is under amendment due to the changes in the detailed design.

- Replacement of guardrails according to EN standards on 100 km motorways on Corridor 10 – OIS was approved on – OIS was approved on 26.07.2019. Market analysis for the simplified procedure was conducted by PESR in Q4 of 2020.

    - Supply and installation for signalization of the railway level crossings - Operation Identification Sheet approved on 29.08.2018. No progress in terms of reply from PEMRI.

- Priority action 3 Horizontal assistance

- Preparation of project documentation for multimodal node Trubarevo – Contract notice published on 27.12.2019. The evaluation is completed, and no bidder has been selected. Cancellation notice was published on 23.12.2020.

    - Technical audit for the Major project Construction of road section Gradsko – Interchange Drenovo as part of road Corridor X-d - Tender dossier was submitted to the CFCD on 22.02.2019. Activities for market analysis and short-listing of three companies were conducted by the PESR and the report with the TD was submitted to MoTC on 28.12.2020.

    - City of Skopje Sustainable Urban Mobility Plan- Operation Identification Sheet approved on 23.01.2019. Tender dossier was finalized after several consultations with the EUD, CFCD, JASPERS, MoTC and the City of Skopje. CN was published on 11.02.2020. The TD and ToR were approved by EUD on 26.10. 2020.Development of Implementation plan under the National Transport Strategy 2018-2030 with system, tools and capacity for its monitoring – OIS was approved on 18.06.2020. TD was sent to CFCD on 02.10.2020.PIN is published on 11.11.2020.  The revised TOR was submitted to the CFCD on 07.12.2020.

- Preparation of National aviation strategy 2021-2030 – OIS was approved on 20.05.2019. The tender dossier and the Market Research Report were sent to CFCD on 04.09.2020. CFCD submitted the TD to the EUD. Comments from EUD were received on 28.10.2020, Preparation of design documentation and implementation of measures for improvement of road safety – OIS was approved on 27.12.2019. TD is under preparation by PESR.

- Main achievements in the sector

So far, it is not possible to report on any substantial achievements of the IPA II actions within the sector. Because of the nature of the transport infrastructure projects whose implementation is multi-annual, the social and economic impact could be measured only after road and railway infrastructure is put into operation. However, the main achievements in the sector are related not only to the implementation of still ongoing major projects under indirect management. Good progress related to adoption by the GoRM of the National transport strategy for the period 2018-2030. Progress has been made also in road safety with the Ministerial Decision for formation of a Working group for formation of an executive body for road safety.  Additionally, an application to the CONNECTA instrument (engaged by DG NEAR) for technical assistance for establishing of the executive road safety body was submitted. However, the application was rejected i.e., technical assistance was not approved under the CONNECTA instrument. There was no official notification for the rejection and no argument as to why the application is rejected.

The Ministry of Transport and Communications applied to the EUIF instrument for a TA for establishing an executive body for road safety that was approved and the selection procedure was launched in November 2019. Contracts start on 20th January 2020 with an envisaged duration of 9 months. Project was amended for 1 month and finish on 30.11.2020. In the course of 2021, the executive body should be operational.

Apart from IPA II, but because of the commutative effect of the called “soft” interventions successfully implemented by the partners, as traffic control and public awareness campaigns for road traffic safety increased, the number of accidents with casualties in 2019 was decreased .

- Recommendations for further actions

The main recommendations according to the SWGT held on July 2nd,2020 were related to the selection and submission of project proposals for IPA 3 financing. Additionally, an annual revision of the Single project pipeline was conducted in December 2020as well and the institutions must start the activities in due time considering the guidelines submitted by the SEA.

5th meeting of the IPA II Transport Sectoral Monitoring Committee (SMC) that took place on-line via WebEx on the 9th of November 2020.

5th IPA II Joint Monitoring Committee meeting- JMC held on the 14th of October 2020 via WEBEX.

# II a. Performance indicators in the Transport sector covering both direct and indirect management

Indicators per programme

| Financing Agreement/Programme reference | Indicator for sector Transport | Source | Baseline | Milestone (2018) | Target (2020) | Final target (Year) | Value (2014) | Value (2015) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP Indicator | Logistic Performance Indicator 1 = worst and 5 = best | World Bank | 2.56 (2012) |  |  |  | 2.50 |  | 2.51 |  | 2.62 |  |  |
| IPA/2014/037702.6 SOPT 2014-2020 | 1. Length (km) of rail infrastructure reconstructed/rehabilitated/ constructed along SEETO Comprehensive Network with IPA II funds | Ministry of Transport | 0 (2017) | 0 | 0 | 23 (2025) | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | 2. Goods transported (thousands of tons) on annual basis by 2022 on C-VIII | SSO | 0 (2015) | 0 | 0 | 500000 (2025) | 0 | 0 | 0 |  | 0 | 0 | 0 |
| IPA/2014/037702.6 SOPT 2014-2020 | Secured level crossings according to international standards and best practices | Ministry of Transport | 81 (2016) | 0 | 0 | 96 (2025) |  |  |  | 0 | 0 | 0 | 0 |
| IPA/2014/037702.5 SOPT 2014-2020 | Number of communication campaigns carried out for improved visibility in transport sector | IPA media report | 0 (2016) | 0 | 0 | 2 (2025) |  |  |  | 0 | 1 | 0 | 0 |
| IPA/2014/037702.5 SOPT 2014-2020 | Production of relevant sector statistics and establishment of a comprehensive data collection system | MoTC | 0 (2015) | 0 | 0 | 1 (2025) |  |  |  | 0 | 0 | 0 | 0 |
| IPA/2014/037702.5 SOPT 2014-2020 | Total number of technical audits made for Major Projects | Ministry of Transport | 0 (2016) | 0 | 0 | 2 (2025) |  |  |  | 0 | 0 | 0 | 0 |
| IPA/2014/037702.4 SOPT 2014-2020 | Length (km) of roads reconstructed/rehabilitated/ constructed along SEETO Comprehensive Network | Eurostat/National Statistic Office/P. E State Roads and SEETO MAP | (baseline 16 km) | 0 | 98 km | 98 (2025) |  |  |  | 0 | 0 | 0 | 0 |
| IPA/2014/037702.4 SOPT 2014-2020 | Increased road safety measures/decreased number of black spots along the SEETO comprehensive network | National Statistic Office/Ministry of Interior |  |  | Reduction by 30% of the road safety fatalities, 3 to 6 eliminated black spots |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

# Agriculture and rural development

- Involvement in programming

As pointed out in the previous Annual Reports, the MAFWE was involved in the preparation of an IPA AD that was financed under IPA 2015. Additionally, an Operation Programme IPARD with DG AGRI for the period 2014 – 2020 was prepared. The OP entered into force in June 2017 and at present it is under implementation. In 2018, the IPA Action Document 2019 was drafted and in 2019 the final version was endorsed by EUD and EC. The main features of the Action Document 2019 are as follows:

Overall Objective: To enhance the sustainable development of Rural Areas.

Specific Objectives:

- To improve farm productivity and sustainable use of forests

- To ensure food safety and improved animal and plant health

Results:

- Modernised and optimised farming and forestry

- Decreased risks to human, animal and plant health.

Requested EU Financial Support: 14.000.000 EUR

National Contribution: 6.450.000 EUR

Elaboration procedure: 3 meetings of the SWGs in plenary session were organised. Donors, Embassies and CSOs were always part of these meetings. The Minister of Agriculture, Forestry and Water Economy chaired these meetings. Next to the meetings of the SWGs in plenary sessions, 10 thematic meetings including the concerned parties were organised.

Financing Agreement for the IPA AD 2019 is signed.

In spring 2020, the programming of IPA III started. The main elaborated draft documents are as follows:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 4 – Competitiveness and Inclusive growth (Thematic Priority 3: Agriculture and Rural Development and Thematic Priority 4: Fishery) | EU for the development of Agriculture. | EU for a sustainable and competitive economy. |

The Action Document will contribute to improve sustainable competitiveness of North Macedonian economy and to the achievement of the specific objectives of Window 4 Thematic Priority 2: Private sector development, trade, research and innovation and Thematic priority 3 “Agriculture and rural development”,

In concrete, this Action will improve the sustainable competitiveness of the North Macedonian economy to achieve a greened, recovered and modernized economy. Regarding ARD, the Action will focus on the preparation of the country for participation in the EU Common Agricultural Policy, harmonize agriculture with the European standards and increase the competitiveness of the agricultural production. The ARD section of the AD includes two activities “Establishing four Common Market organizations in North Macedonia” and “Construction of four small-scale irrigation systems and ancillary activities”. Total value is 6.000.000 EUR where 5.000.000 EUR is EU financing.

- Overview of results in moving towards a fully-fledged sector approach (i.e., targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented to fully implement the roadmap are summarised.

| Criteria: Strategic Planning | Self-assessment: Most of the targets for 2018, 2019 and 2020 have been reached |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: Most of the targets for 2018, 2019 and 2020 have been reached |
| Criteria: Coordination | Self-assessment: Most of the targets for 2018, 2019 and 2020 have been reached |
| Criteria: Performance | Self-assessment: Most of the targets for 2019 and 2020 have been reached |
| Criteria: Budget | Self-assessment: Less than half of the targets for 2018, 2019 and 2020 have been reached |
| Remarks: Roadmap implementation is progressing well. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The coordination with other instruments is articulated as follows:

- Coordination meetings within the SWG that has the role to coordinate all the stakeholders that are active in the sector.

- Bilateral relationships with Donors.

- Relationships with IFIs.

The following meetings of the SWGs were organised in 2020:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 24.06.2020 | 20 | Discussing on IPA3 SR and AFs |
| 07.10.2020 | 24 (Online WEBEX meeting) | Discussing on IPA3 SR ARD plus Fishery (targets and indicators) |

The following donors, IFIs, Embassies and CSOs were present at these meetings:

| SWG – ARD |
| --- |
| Donors and International Organisations | IFIs | Embassies | CSOs |
| GIZ | KFW | Greek | CARE |
| EUD | World Bank | German | UN Woman |
| UNDP | EBRP | Dutch | CNVP |
| USAID |  |  | NFF National Federation of Farmers |

In the sector ARD, the following programmes financed by the Donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
|  |  | FAO Technical Cooperation Programme TCP |  |
| FAO | 401,000$ | Support to Mainstreaming of the National Land Consolidation Programme Mainstreaming the National Land Consolidation Programme (contribution to: GCP/MCD/002/EC) | 1/1/2020 8/31/2021 |
| FAO | 100,00 $ | Support to privatization of state-owned land- To assist the smallholders and family farms to get access to purchase and rent of state-owned agricultural land and to overcome the problems arising from excessive land fragmentation through the use of state land to catalyse the land consolidation process | 6/15/2018 7/31/2020 |
| FAO | 275,000 $ | Support to Integrated Community Development -The project aims to provide FAO technical assistance in (1) capacity development on rural development policy and community development planning of MAFWE staff, staff of regional and local government, and of other relevant institutions and organizations; (2) capacity development on rural development principles and practices in pilot areas through participatory integrated community development. The project will be implemented in close coordination with the ongoing GCP/MCD/002/EC supporting integrated local community development in addition to the land consolidation efforts in the MAINLAND LC project areas – Sokolarci, Spancevo, Cesinovo (Cesinovo-Oblesevo Municipality), Egri, Opticari and Zhabeni (Bitola Municipality). | 15/05/2019 14/05/2021 |
| FAO | 64,000 $ | TCPF: Food Safety and Quality Standards in the Dairy Sector-The project will focus on 1) Strengthening the system on quality and safety requirements as a dimension of adopting and implementing CMO requirements, 2) Improvement of the capacities of all stakeholders along the dairy value chain to adopt, implement and enforce food quality and safety standards (Tailor-made codes of practices and guidelines will be developed for different stakeholder groups (competent authorities and producers) | 4/1/2020 4/1/2021 |
| FAO | 93,000 $ | TCPF: Strengthening of Agriculture and Rural Development Policy Analysis and Programming- The project aims to support the Government of North Macedonia in its efforts to reform the country’s direct payment scheme by preparing a report about the consequences of the Common Agricultural Policy (CAP) alignment process, in view to the process of accession to the EU on solid and sustainable basis. The objective of the report is to provide evidence-based guidance to the government for their policy formulation process to align the direct payment scheme with CAP regulations. Specifically, the report will analyse the impact of decoupling direct payment on farmer income. The report will analyse various scenarios of decoupling direct payments - all in accordance with CAP regulations. The project will closely work with MAFWE to build up the capacities of selected officials who should carry out the policy assessment and analysis of this form. | 9/1/2019 3/11/2021 |
| FAO | 280,000 $ | Increased resilience of agriculture sector through promotion of climate smart agriculture practices- Increased resilience of the agriculture sector by strengthening institutional capacity and coordination at the national level, and promotion of climate resilient good practices at local level | 1/1/2020 12/31/2021 |
|  |  | REGIONAL FAO TCP Projects |  |
| FAO – Regional project in: North Macedonia Albania Armenia Moldova | 320,000 $ | Strategies for Food Loss and Waste Reduction-To enhance food loss and waste reduction in the programme implementation areas, resulting in a reduction of the national contribution to climate change, and a mitigation of the pressure on national food systems for increased production | 1/8/2018 12/31/2020 |
| FAO - Regional project in: North Macedonia Ukraine Armenia Belarus Bosnia and Herzegovina Georgia Moldova | 388,000 $ | Support for the enhancement of national plant pest surveillance and phytosanitary certification systems -Support to the efficient phytosanitary services required for sustainable and climate resilient transitions to address threats caused by climate change such as plant pests to food systems and trade. | 2/1/2019 12/31/2020 |
| FAO (Regional project in: North Macedonia Albania Bosnia and Herzegovina Montenegro Serbia | 500,000 $ | African Swine Fever Emergency preparedness in the Balkans -Improved and protected livelihoods against African Swine Fever (ASF) in the Balkans. | 11/1/2018 12/31/2020 |
| FAO - Regional project in: North Macedonia Albania Montenegro | 320,000 $ | Improved data methodology for sustainable management of inland fisheries resources in the West Balkans-Human capacity increased for standardized data and methodologies to support sustainable management of inland fisheries in West Balkans | 11/8/2018 12/31/2020 |
| FAO – Regional project in: North Macedonia Tajikistan Armenia Kyrgyzstan | 405,000 $ | Creating enabling environments for enhanced climate resilience in agriculture - The project will contribute to mainstreaming climate change adaptation processes in agriculture and food system through enhancing resilient seed systems and promoting quality seeds of climate tolerant varieties | 4/15/2020 4/14/2022 |
| FAO – Regional project in: North Macedonia Albania Armenia Belarus Kyrgyzstan Russian Federation Tajikistan Uzbekistan | 420,000 $ | Strengthening Capacity in Price and Market Information Systems and Policy Monitoring in Response to COVID-19 and Other Shocks - Strengthened institutional capacities to address the countries` needs in developing and maintaining MIS for commodity and value chain development and in developing robust and flexible policy strategies to deal with short-term risks and long-term market uncertainties | 5/15/2020 5/14/2022 |
|  |  | Donor funded (Trust Funds/GCP), implemented by FAO |  |
| FAOGCP/MCD/002/EC (Entity: 640031) (donor: European Union/IPA) | 2,653,928 $ | Mainstreaming of the National Land Consolidation Programme (MAINLAND-The main aim of the EU-funded project is to assist smallholders and family farms to overcome the problems arising from excessive land fragmentation, small farm sizes and insufficient agricultural infrastructure to increase productivity, competitiveness, and efficiency of farms, thus enhancing the potential of the agricultural sector in the Country, the problems which FAO has been addressing since 2014. By bringing in expertise and strengthening the capacities of the Ministry of Agriculture, Forestry and Water Economy, key public agencies and geodetic companies, FAO supports the implementation of the first round of land consolidation projects under the national land consolidation programme. | 1/3/2017 31/08/2020, with expected extension of 1 year |
| FAO - GCP/MCD/006/GCR (donor: Green Climate Fund) | 611,285$ | Strengthening country capacities for climate change adaptation and mitigation and finalization of country work programme for the Republic of North Macedonia - Based on the progress achieved under the first project from the Green Climate Fund (GCF) Readiness and Preparatory Support Programme (GCP/MCD/003/GCR) successfully implemented by FAO and the Government of North Macedonia in 2019 (more info: http://www.greendevelopment.mk/en/newsReadMore.aspx?id=7 ), a second GCF readiness grant was approved for the country at the end of 2019 - to be implemented starting from June 2020. Based on the priorities defined by the Nationally Determined Contributions (NDCs) of North Macedonia, the Cabinet of the Deputy President of the Government of North Macedonia in charge of Economic Affairs in its role as National Designated Authority (NDA) for the GCF together with other national key stakeholders has identified 9 priority sectors, including Agriculture, Forestry, Energy, Transport, Water Resources, Waste, Biodiversity, Health, and Cultural Heritage, which will be the basis for the development of the GCF Country Work Programme under this second Readiness grant. In this sense, this Readiness Proposal has the intention to strengthen the capacities of key government institutions relevant for climate action, including the MAFWE to become strong national partners that participate in the coordination mechanism and other decision-making bodies related to Sustainable Development and climate change, and particularly to make informed decisions on GCF matters. | 12/19/2019 6/18/2021 |
| FAO-GCP/GLO/893/MUL (donor: Codex Trust Fund | 95,100 $ | Strengthening the national Codex structures in the country - To meet the emerging challenges of food safety and public health in the context of food trade, North Macedonia through its Food and Veterinary Agency has accessed funds from the FAO/WHO Codex Trust Fund to increase capacity of the national Codex structure to engage in Codex Alimentarius work - an important global set of standards, codes of practice and guidelines aimed to protect consumer’s health and ensure fair practices in the food trade. The project aims to support the country in sustainable engagement with Codex work activities. Expected outcomes include: Increased capacity of the national Codex structure of the country to be engaged in Codex work; High level hierarchy commitment and secured budget for future Codex related activities; Common vision, policy and priorities for Codex work agreed; Increased adoption and use of new standards provided by the Codex in North Macedonia | 2/27/2019 8/31/2021 |

In the sector ARD, the following loan financed by KfW is under implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| KfW | 10.800.000 Euro | Project for construction of irrigation system south Vardar Valley - Second phase-The second phase of the project, which includes rehabilitation / modernization and expansion of existing and new irrigation systems in the region of Valadao. | 2018 - 2021 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning, and budgeting

Strategic Planning: The impact of IPA II actions on strategic planning for the ARD sector can be seen in the strong support received from the EU to the Ministry of Agriculture, Forestry and Water Economy (MAFWE) in the preparation of the IPA III Strategic Response Action document and Action Fiche. In line with the steps and targets of the Roadmap in the strategy criteria for 2019 and 2020, the MAFWE developed and approved the relevant strategic documents and legal requirements in the sector (the National Agriculture and Rural Development Strategy for the period 2021-2027 NARDS2021-2027; Law on agriculture and rural development – LARD amendments are currently in the Governmental procedure; According to Law on Wine – LW in 2020 two wine bylaws were adopted in the field of viticulture and winemaking; Rulebook for FADN is fully approximated with actual EU farm return methodology; The new food safety strategy for 2021-2025 is submitted for Governmental approval; National Action Plant (NAP) for sustainable use of plant protection products will be approved 2021; Adopted Programme for Phytosanitary Policy 2021, etc.). All relevant strategies set out the priorities in the sector for agricultural and rural development, with clear described objectives and defined measure.

Administrative capacity: A functional review for MAFWE (including the directorates), AFSARD (Agency for Financial Support of Agriculture and Rural Development) and FVA (Food and Veterinary Agency) was prepared with the support of IPA during the 2019. The new IPA project “Support to state reorganisation” started in MIOA, is preparing Functional Review for Public Administration in the Country and the MAFWE is included in this analysis. The sublimate of the recommendations will be implemented by MAFWE accordingly. One of the main critical aspects in the administrative capacity is the absence of a retention policy for high performing staff in all institutions. Responsibilities of MAFWE staff are delegated to individuals that become overloaded and inefficient while bulk of staff remains underused and somehow demotivated.

Performance: Under performance, a list of relevant indicators –qualitative and quantitative- for the sector has been elaborated with the support of the IPA project “Support for the Management of the EU Fund”. Sector Performance Assessment Framework (PAF) is by now established. Monitor the direct payment policy through the FADN (Farm Accountancy Data Network) is implemented. In 2021, it is expected to have update on additional functionality of the Agriculture Information System (AIS) for monitoring and evaluation.

Budget: The new Five-year budget national programme for agriculture and rural development 2018-2022 was adopted in 2018 by Government. The programme links the strategic documents, primarily the National Strategy for Agriculture and Rural Development and multi-annual budgetary planning with the annual operational agricultural and rural policies programs and decrees. The preparation of the program was consulted with the wider stakeholder’s community including the most relevant policy beneficiaries and experts. As to the Program, for the planning period from 2018-2022, a total of MKD 48,072,705,000 or € 781,670,000 is foreseen from the national budget for support of agriculture and rural development. While the direct payments still consume most of the envelope, there is an evident positive trend in projection of allocations for the rural development policy increasing from 35.1 million EUR (over 150.8 MEUR in 2018) to 46.7 million EUR (over 166 million EUR in 2022). The financing of the National Agriculture and Rural Development Strategy for the period 2021-2027 (NARDS 2021-2027) will be done with funds provided from the Budget of Republic of North Macedonia allocated in the budgets of the budget users who have competence in the implementation of the national agricultural policy according to law, primarily the budget of AFSARD and MAFWE. The total amount of funds to support the sector and rural areas allocated from the national budget and IPARD funds for the period 2021-2027 is 1.35 billion EUR, while from the national budget alone the amount is 1.26 billion. The difference is planned for the implementation of the measures from the IPARD program financed by the European pre-accession funds. Over the years, the allocations are planned to increase from 138 million EUR in 2020 to 200 million EUR in 2024 and beyond.

Under indirect management by RoM:

- OS(s) in place and related changes, if relevant:

Financial Agreement for IPARD 2014-2020 entered into force on 29 June 2017, which enabled implementation of IPARD II assistance as well. Continuous efforts are made to develop adequate structural solutions to strengthen the management and control system, having in mind the DG AGRI recommendations as well as previous experience in the implementation of IPARD I. No changes in the operating structure for implementation of IPARD II occurred during rollover process (from IPARD I towards IPARD II).

Administrative Capacities of the IPARD Management and Operating Structure

Management Structure

The number of employees in the Management structure at the end of 2019 was 17 (seventeen), including the NAO.

In January 2020, through internal promotion, the positions of Head of National Fund Unit and Head of NAOSO Unit were filled.

During 2020, two accountants and Assistant Head of MS were internally transferred to other sectors within the Ministry of Finance, while one employee was internally transferred to Management Structure. The current number of employees in MS is 15 (Including NAO). The WLA for the period 2020-2022 was prepared and the optimal number of employees in MS for 2021 is 19 (nineteen). In December 2020 public vacancy call was announced for filling positions in both Units, NASO and NF. The procedure is expected to be finished by end of Q1 2021.

IPARD Agency

According to the Workload Analysis (WLA) for 2021, the optimal number of employees needed in IPARD Agency for the implementation of the IPARD Program 2014-2020 is 151. The current number of employees within the IPARD structure of the Agency is 123 (of which 8 are on temporary basis). During 2020, IPARD structure within AFSARD increased for 12 employees (six new administrative civil servants from employment procedure that started in November 2019, five new temporary employments and one employee was transferred to work from non IPARD to IPARD related issues) and at the same time was decreased for 6 employees (three of the temporary employees and three employees working on IPARD). In 2020, one existing civil servant was promoted in Head of the Unit for Reference Price Database, Department for Registers.

Managing Authority

The number of employees in the Managing Authority at the end of 2019 was 14 (fourteen), including HoMA.

According to the Workload Analysis (WLA) for 2021, the optimal number of employees needed in Managing Authority is 17. During 2020, 1 (one) person was employed with temporary contract. At the end of 2020, the number of employees was 15 (including HoMA).

In the table below are presented the data regarding the human capacities in 2020:

| Institution | Number of staff on 31.12.2019 | Number of staff needed as per WLA 2021 | Realized new recruitments by 31.12.2020 | Left the position 31.12.2020 | Number of current staff 31.12.2020 | Occupancy rate | Turnover rate |
| --- | --- | --- | --- | --- | --- | --- | --- |
| NAO/NF | 17 | 19 | 1 | 3 | 15 | 79% | 17,65% |
| IPARD Agency | 117 | 151 | 12 | 6 | 123 | 78% | 5,13% |
| Managing Authority | 14 | 17 | 1 | 0 | 15 | 79% | 0% |
| Total | 154 | 194 | 13 | 10 | 144 | 82,5% | 12,23% |

- Information on the implementation of Action programmes under indirect management in the sector

The implementation of the IPARD Programme 2014-2020 started in April 2017 with submission of applications under the first call (01/2017, all 3 measures included). Implementation of the Programme continued by announcing public calls for specific measures:

- Public call 01/2018 was for submission of applications under Measure 3.

- Public call 02/2018 was for submission of applications under Measure 1.

- Public call 01/2019 was for submission of applications under Measure 7.

- Public call 02/2019 was for submission of applications under Measure 3.

- Public call 01/2020 for submission of applications under Measure 1.

The status for all public calls with the applications received, contracted, and paid by 20th of September 2020, is as follows:

| Measure | Submitted | Rejected | In processing | Contracted | Paid |
| --- | --- | --- | --- | --- | --- |
|  | Number | EU funds |  |  | Number | EU funds | Number | EU funds |
| 1 | 3.251 | 57.306.327 | 744 | 1.022 | 1.485 | 14.207.820 | 1.217 | 7.418.942 |
| 3 | 183 | 45.098.137 | 39 | 43 | 101 | 18.234.346 | 55 | 6.264.792 |
| 7 | 448 | 85.164.058 | 263 | 125 | 60 | 6.188.748 | 13 | 662.775 |
| 9 | 12 | 148.188 | 9 | 0 | 12 | 148.188 | 8 | 21.126 |
| Total | 3.894 | 187.716.710 | 1.046 | 1.190 | 1.658 | 38.779.102 | 1.293 | 14.367.635 |

Sector for project approval started to evaluate the applications now of receiving the applications during the public call.

Regarding the planned payments from the IPARD II Programme, it will depend on the dynamics of concluding agreements and realization of the investments from the recipients.

For IPARD 2 the following “on the spot” controls were performed in 2020 (till 25.09.2020):

- A total of 274 on-the-spot controls prior approval were carried out of public calls 18/01, 18/02, 19/01,19/02 and 20/01 by IPARD 2 2014-2020, of which 123 controls on Measure 1 investments - Public calls 18/02 and 20/01, 52 controls on investment by IPARD 2 Measure 3 - Public calls 18/01 and 19/02 and 99 controls on investment by IPARD 2 Measure 7 - Public call 19/01

- A total of 376 on-the-spot controls were carried out prior to the payment of public investment 17/01, 18/01 and 18/02 of IPARD 2 2014-2020, of which 350 controls on investment under Measure 1 - Public calls 17/01 and 18/02; 22 controls on Investment from Measure 3 - Public Calls 17/01 and 18/01 and 4 controls on Investment in Measure 7 - Public Call 17/01.

- A total of 324 ex-post on-the-spot controls were carried out for investments from IPARD 1 and IPARD 2 out of which 55 on-the-spot controls were performed at investments from IPARD 2 and 269 at investments from IPARD 1

- 4. A total of 4 controls were carried out to identify hidden matters, 1 control on Measure 3 investments and 3 Measure 7 controls. 3 checks were carried out after signing the contract, but before the payment request for the Technical Assistance Measure is submitted.

On the spot controls, because of COVID-19 pandemic, are performed in very difficult conditions and where is possible they are performed without the presence of the beneficiary. For measure 1 for Public Call 20/01, 120 on the spot controls are performed with changed new procedure using all available data from the Farm register, LPIS register, Cadaster data, data from Veterinary register, data from the annual direct payment subsidies applications and existing new maps.

- Main achievements in the sector

Under the Operational Programme IPARD, whose financing agreement entered into force in June 2017, there is good progress at sector level to be reported. IPARD PA authorised 1.292 claims for payment in total amount of 14.350.060 EUR as EU co-financing. For the first time, there is no decommitment of the available EU budget for IPARD in the implementation of the IPARD Program.

- Recommendations for further action

IPA

The main recommendations according to the 4th IPA II Sectoral Monitoring Committee Meeting on competitiveness, innovation and agriculture and rural development held on the 02.12.2020 are as follows:

- National Authorities will adopt by the end-March 2021 all necessary legal framework in the area of agriculture prepared with IPA support, such as the Law on Agriculture and rural development, Law on CMO, Law on direct payments, Law on extension services.

- MAFWE will observe and monitor all necessary pre-conditions that should be in place before starting of the IPA projects and report during the regular progress meetings between Ministry and EUD.

- MAFWE will prepare clear timetable of actions to address the functional review recommendations by end-January 2021.

- National authorities will adopt by the end of 2020 the Law on Plant Protection Products and by the end-June 2021 all necessary secondary legislation.

- MAFWE will hire IT staff by March 2021 and will provide sufficient funds for maintenance of IT equipment in the budget for the next year and the consequent years.

- The Strategy for Agriculture and Rural development covering the period 2021-2027 will be adopted by the end of December 2020.

- MAWFE to employ a number of staff to which department is feasible to hire and in what time period

IPARD Operational Programme

Due to the Corona virus outbreak the IPARD Programme 2014-2020 Monitoring Committee held only one meeting in December 2020. Key conclusions and recommendations adopted at the meeting are as follows:

- The IPARD Monitoring Committee was informed on the appointment of its new members. In October 2020, the Minister signed the Decision for establishment of IPARD Programme 2014-2020 Monitoring Committee with 34 representatives (14 governmental and 20 nongovernmental).

- The IPARD Monitoring Committee was informed on the status of implementation of the Programme through the monitoring indicators.

- The IPARD Monitoring Committee was informed on the status of activities for implementation of measure “Investments in rural public infrastructure”. The measure will be accredited only if IPARD Agency shows adequate capacity for implementation regarding human resources needed for implementation.

- The IPARD Monitoring Committee was informed on the status of forthcoming modification of the Programme.

- The IPARD Monitoring Committee adopted the plans for procurement under the Technical Assistance measure (APTA) for 2020 (version 3) and 2021.

- The IPARD Monitoring Committee adopted the plan for Communication and visibility for 2021.

- The IPARD Monitoring Committee was informed on the status of activities regarding the ex-post evaluation of the IPARD Programme 2007-2013 and on-going evaluation of IPARD Programme 2014-2020.

.

# II a. Performance indicators in the Agricultural and Rural Development sector covering both direct and indirect management.

| Financing Agreement/Programmed reference | Indicator for sector Agriculture and Rural Development | Source | Baseline | Target (2020) | Final target (Year) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP indicator | Total investment generated via IPA in agri-food sector and rural development – DG AGRI | IPA report |  | 54,181,644 EUR |  |  |  |  |
| IPA/2015/037-907.03 | 13. Number of in-depth Market organization analysis | Project reports | 0 (2014) | 2 | 2 (2019) | 0 | 4 | 6 |
| IPA/2015/037-907.03 | 12. Number of small-scale irrigation systems constructed | Project reports | 0 (2015) | 2 | 8 (2024) | 0 | 0 | 0 |
| IPA/2015/037-907.03 | 2. Additional number of hectares irrigated | Irrigation project reports | 0 (2015) | 0 | 800 (2024) | 0 | 0 | 0 |
| IPA/2015/037-907.03 | 11. Number of tests performed | Phytosanitary reports | 33 (2019) | 45 | 70 (2024) | 29 | 31 | 31 |
| IPA/2015/037-907.03 | 10.Number of accredited methods | Accreditation protocols (Institute for accreditation) | 34 (2019) | 50 | 50 (2024) | 141 | 146 | 149 |
| IPA/2015/037-907.03 | 9. Established and operational Phytosanitary Information System, | Project reports | 0 (2014) | 1 | 1 (2020/2021) | 0 | 0 | 0 |
| IPA/2015/037-907.03 | 8. Compliance of BIPS with EU requirements | Progress reports | 4 (2014) | 5 | 5 (2020) | 5 | 5 | 5 |
| IPA/2015/037-907.03 | 7. % of sampled animals immunized against rabies | Monitoring reports | 48 (2014) | 70 | 70 (2020) | 71 | 96 | 54 |
| IPA/2015/037-907.03 | 6. EU Legislative compliance with chapter 12 in % | Progress reports | 85 (2016) | 95 | 95 (2020) | 88 | 89 | 91 |
| IPA/2015/037-907.03 | 5. Set of CMO Policy Regulations implemented | Project reports | 0 (2014) | 2 | 2 (2024) | 0 | 0 | 0 |
| IPA/2015/037-907.03 | 4. New AFSARD/IACS software developed and interoperability among different IACS elements secured. | Project reports | 0 (2014) | 1 | 1 (2020) | 0 | 0 | 0 |
| IPA/2015/037-907.03 | 3. Number of additional cooperatives with an economic objective and market performance created | Project reports | 27 (2014) | 10 | 10 (2024) | 41 | 54 | 61 |
| IPA/2015/037-907.03 | 1. Number of land consolidation projects (areas) | Land consolidation reports | 2 (2014) | 10 | 12 (2024) | 2 | 9 | 9 |

| Financing Agreement/Programmed reference | Indicator for supports Rural Development and Competitive Sustainable Agriculture | Source | Baseline (Year) | Target (2023) | Final target (2025) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 2019/041263.02 | Gross Value added in the Agriculture, Forestry and Fishing sector at national level and at the target regions | National accounts, Gross domestic product by production approach, at current prices, State Statistical Office | MKD 47,817 million (201814) (EUR 777 million) | MKD 48,000 million (EUR 780 million) | MKD > 50,000 million (EUR 813 million) | MKD 55,979 million (EUR 910 million) | MKD 55,477 million (EUR 902 million) | NA |
| 2019/041263.02 | Gross Value added in the Agriculture, forestry, and fishing sector in the focus regions | State Statistical Office http://www.stat.gov.mk/Pu blikacii/RegionalenGodisn ik2018.pdf | MKD 10,626 million (2015) (appx EUR 173 million) | MKD 10,626 million (EUR 173 million) | MKD > 11,000 million (EUR 179 million) | MKD 9,786 million (EUR 159 million) | NA | NA |
| 2019/041263.02 | GDP/capita at regional level in the focus regions | State Statistical Office http://www.stat.gov.mk/Pu blikacii/RegionalenGodisn ik2018.pdf | MKD (2015) 121,824 212,913 164,161 | MKD > 121,824 > 212,913 > 164,161 | MKD > 121,824 > 212,913 > 164,161 | MKD P: 148,785 SW: 250,902 NE: 184,163 | MKD P: 158,510 SW: 259,131 NE: 187,609 | NA |
| 2019/041263.02 | Number of farmers benefitting. from the action (men and women, of them people of minorities and vulnerable groups) | Reports on the implementation of the financed projects | 0 (2018) | 0 | > 2,400 | - | NA | NA |
| 2019/041263.02 | Farm output for the supported farmers | Dedicated study on farm output | To be established | 20% increase of the farmers output | 50% increase of the farmers output | - | NA | NA |
| 2019/041263.02 | Output of the forestry sector | Income Statement of PEMF | EUR 28 million (2017 | EUR 28 million | EUR 30 million | EUR 27.3 million | EUR 26.1 million | EUR 24.4 million |
| 2019/041263.02 | Number of diseases eradicated. (officially declared free of) on the country territory | Reports of the FVA | 0 | 0 | 2 |  | 0 | NA |
| 2019/041263.02 | Volume of pesticides used | Statistical data of the Customs and Agriculture Inspectorate on imported. pesticides | 1,815 (2015 to 2017 average) | 1815 | 1,500 (2022 to 2024 average) | - |  | NA |
| 2019/041263.02 | Export to EU allowed for seed and mercantile potato produced in the Country | EU Official Journal | Ban under Council Directive 2000/29/EC |  | Derogation from the ban | - |  | Derogation request sent to DG SANTE |
| 2019/041263.02 | Hazard of food contamination (bacteria and pesticides) | Sampling control of the FVA | 2% (2017) | 2% | > 1% (2023) |  | 2% | 2% |
| 2019/041263.02 | Number of hectares of consolidated land in the four selected areas | Re-allotment plans and data of the Agency for the Real Estate Cadastre (AREC) | 0 (2018) | 900 | 1400 |  | 0 | 0 |
| 2019/041263.02 | Hectares irrigated based on the cadaster | Water Economy Directorate in liaison with the Agricultural Irrigation Cooperatives | 250 (2018) | 250 | around 500 |  | 250 | 250 |
| 2019/041263.02 | Number of farmers benefitting. from advisory services (men and women) | NEA Report/ Register of the co/financing of the payments for extension services | 700 (2018) | 750 | Total: > 1000 Female: > 400 MVG: > 50 |  |  | NA |
| 2019/041263.02 | Number of new procedures introduced in the supported entities | Project report | 0 (2018) | 0 | 15 |  |  |  |
| 2019/041263.02 | Number of hectares of high forests (seed origin, high quality forests) within three regional Forest Management Unit in the regions North East, South West and Polog certified by a recognized certifier. | Certifications in the availability of the Public Enterprise North Macedonia Forests | 0 (2018) | 0 | 30,000 |  |  | 4,000 not accredited certificated |
| 2019/041263.02 | Tons of animal by-products safely disposed yearly at the rendering. facility | Register of the Rendering. Plant | 0 (2018) | 0 | 8,500 |  | 0 | 0 |
| 2019/041263.02 | Number of plant protection products approved | Register of the approved. PPP | 0 (2018) | 0 | 3 |  |  | 500 |
| 2019/041263.02 | Number of accredited methods | Report on realized. Monitoring program | 141 (2018) | 141 | 169 |  |  | 149 |
| 2019/041263.02 | Number of species/cultivars stored. in the gene bank | Register of the gene bank | 3,600 (2018) | 3,600 | 5,000 |  |  | NA |

# Competitiveness and Innovation

- Involvement in programming

As pointed out in the previous Annual Report, the following programming document(s) were prepared and are in an advanced implementation phase: IPA 2014 and IPA 2016.
In 2020, the IPA Action Document 2019 was finalized and approved. The main features of the Action Document are as follows:

Overall Objective:To achieve competitive economy based on knowledge and innovation and real convergence with the EU.

Specific Objective:

- To improve compliance of the local markets with the EU acquis

- To support start-ups and SMEs in selected under-developed regions to grow, produce added value and create local living

Results:

Result 1- Strengthened legal alignment and enforcement in the fields of Free Movement of Goods (Chapter 1), Free Movement of Services (Chapter 3), Company Law (Chapter 6) and Chapter 28 (Consumer's rights).

Result 2 - Improved access of start-ups and SMEs to financing and high value-added business services in selected regions.

Requested EU Financial Support: 14.000.000 EUR

National Contribution: 250.000 EUR

Elaboration procedure: 1 meeting of the SWGs in plenary session was organised. Donors, Embassies and CSOs were always part of the meeting. The Minister(s) in charge of the sector chaired a large number of meetings. Next to the meeting of the SWGs in plenary sessions, 3 thematic meetings including the concerned parties were organised.

In spring 2020, the programming of IPA III started. The main elaborated draft documents are as follows:

| Title of the Strategic Response(s) | Title of the Action Fiche(s) | Title of the Action Document(s) |
| --- | --- | --- |
| Window 4 – Competitiveness and Inclusive growth (Thematic Priority 2: Private sector development, trade, research and innovation) | EU for Green Growth. | EU for Green Economy |

The Action Document will contribute to improve sustainable competitiveness of North Macedonian economy and to the achievement of the specific objectives of Window 4 Thematic Priority 2: Private sector development, trade, research and innovation and Thematic priority 3 “Agriculture and rural development”,

In concrete, this Action will improve the sustainable competitiveness of the North Macedonian economy in order to achieve a greened, recovered and modernized economy. Regarding Privte Sector Development,the Action will focus on Innovation, technology development and environmental sustainability for North Macedonian enterprises. Total value is 28,000,000 EUR where 20.000.000 EUR is EU financing.

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented in order to fully implement the roadmap are summarised.

| Criteria: Strategic Planning | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been reached. |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been reached. |
| Criteria: Coordination | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been reached. |
| Criteria: Performance | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been partially reached. |
| Criteria: Budget | Self-assessment: All the targets for 2016, 2017, 2018, 2019 and 2020 have been partially reached. |
| Remarks: Strategic Planning: The Strategy on Competitiveness was adopted in 2016 and the implementation in advanced stage. Regular monitoring is done through Working group and preparation of annual Reports. A Smart Specialization Strategy is under preparation which will inherit the Competitiveness Strategy. It is expected that the SSS will be adopted by the end of 2021 Administration Capacity, Coordination and Performance: The establishment of a System (IT platform) for inter-ministerial coordination, monitoring and implementation is in advanced stage. All the functionalities of the System are tested and the system is expected to be launched by the mid of 2021. Budget: In the period 2017-2020 measures were undertaken which resulted in increasing the transparency of the budget planning mainly by better publicity, inclusion of stakeholders and public, better consultation and feedback mechanism. So far, for some of the measures of the Competitiveness Strategy, the budget is secured on annual and multi annual bases. However, activities for 3 year budgeting are envisaged in the frame of Public Finance Management Program of Ministry of Finance, which still have not achieved any result. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The following meetings of the SWG in plenary session were organised in 2020:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 22/6/2020 | 40 | Programming process for IPA III cycle for the period 2021-2022 |

The following donors, IFIs, Embassies and CSOs were present at these meetings;

| Donors | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| EUD | World Bank | British | Macedonian Chamber of Information and communication Technologies |
| USAID | EBRD | Swedish | Economic Chamber of Macedonia |
| UNDP |  | Swiss | ICT Chamber – MASIT |
|  |  |  | Chamber of North West Macedonia |

In the sector Competitiveness and Innovation, the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| EU Regional funds | EUR 140 mil | Western Balkans Investment Facility (WBIF) - financing and technical assistance to strategic investments in the energy, environment, social, transport, and digital infrastructure sectors. | 2009 - 2021 |
| USAID | USD 13,1 mil | Build prosperity by helping to strengthen the competitiveness of Macedonia’s micro, small, and medium sized enterprises (MSME) sector through enhanced support services, improved access to finance, a more streamlined business environment, and greater energy security. | 2018-2020 |
| UNDP | USD 12,2 mil | Promoting Sustainable Employments by support for self-employment, training of unemployed in skills that are deficient on the labour market, support to the growth of SMES with subsidized employment. | 2007 - ongoing |

In the sector Competitiveness and Innovation, the following loans financed by the IFIs are under implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| WB | USD 24 mil | Skills development and innovation | 2014-2020 |
| EBRD | EUR 30 mil | Support of Industry, Commerce and Agribusiness | 2017-2025 |
| EIB | EUR 100 mil | Enhance the access to credits for small and medium-sized enterprises and mid-caps through Macedonian Bank for Reconstruction and Development | 2018-2022 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning and budgeting

The IPA II has an impact in the sector either through the preparation of Action Programmes or through the implementation of TA projects or through the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning: The national authorities have received TA support by EUD in preparation of Competitiveness strategy as a key document in the sector. Also, revision of Industrial Policy and preparation of new Industrial Policy was supported by EUD assistance. Support was also received for the preparation of IPA ADs in participatory approach.

Administrative Capacity: TA was provided for the preparation of analyses and ToR for the One Stop Shop System project (finance through different sector). Also, TA is secured as a support of EUD to the SEA and all SWG in the IPA process (developing of Programme Documents, Monitoring, and Reporting etc.).

Performance: The IPA 2014 and 2016 Programmes are still under implementation. Support is received for the definition of the monitoring indicators and for the development of a web-based monitoring tool. IPA 2019 Programme was approved and is under tendering.

Budget: The budgeting is still performed on annual basis (short term). No direct support has been provided to the sector. Support is planned to be received indirectly through the MoF.

Under indirect management:

- OS(s) in place and related changes, if relevant:

Not relevant- the sector does not have operation structure.

- Information on the implementation of Action programmes under indirect management in the sector

There are no actions under indirect management, under the responsibility of RoM.World Bank executes the IPA 2014 Programme. The IPA 2016 Programme is executed by EBRD. The IPA 2019 Program is executed by EUD in the country.

- Main achievements in the sector

There are no contracts under indirect management / that have produced any result yet. However, two Agreements for IPA 2014 and IPA 2016 and tendering procedure for IPA 2019 are ongoing. The main achievements in the sector that are connected to the implementation of projects under indirect management are presented in the table below.

| Contract title | Status | Expected result | Achieved result | Remarks |
| --- | --- | --- | --- | --- |
| AD IPA 2014 on Local and Regional development | On going | Increase of competitiveness at local and regional level by supporting municipalities in their integrated local development with a view to stimulate growth and local job creation. Developing tourism capacities by supporting infrastructure interventions. | None yet | Still under implementation |
| AD IPA 2016 on Private sector development | On going | Private sector development by improving the dynamics on the markets of financial services. It will support an EBRD-managed facility providing loans, grants and technical assistance to non-bankable SMEs to help them implement their investment strategies. | None yet | Still under implementation |
| AD IPA 2019 EU Supports Competitive and Fair Markets | Support to the public sector institutions is in tendering phase under direct management Support to private sector is granted under direct management | Support to public sector - Harmonisation with the EU acquis in internal market with a primary focus on free movement of goods and services, protection of consumers' rights and better regulation of the business functioning. Focus is put on improving market surveillance and consumer protection. Support to private sector - Significant part of the EU funds will be channelled to selected under-developed regions to enhance existing and create new business advisory services and to provide direct support to high value-added business initiatives. | None yet | I. Combined Tendering is on-going II. Portion for private sector development is Granted |

- Recommendations for further actions

The main recommendations according to the last Monitoring Committee held on 02.12.2020 are as follows:

- Local and Regional Competitiveness Project - Government and WB urgently to take a decision on the project extension for 6 months and to decide what to do with not committed funds. Increase the speed of ongoing construction works.

# II a. Performance indicators in the Competitiveness and Innovation sector covering both direct and indirect management

Indicators per programme

| Financing Agreement/Program reference | Indicator for sector Competitiveness and Innovation | Source | Baseline | Milestone (2017) | Target (2020) | Final target (Year) | Value (2014) | Value (2015) | Value (2016) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CSP indicator | Distance to Frontier 0 = worst and 100 = best | World Bank | 65.53 (2010) | 76 | 78 |  | 74.03 | 78.95 | 79.19 | 81.39 | 81.55 | 80.75 | 80.7 |
| IPA 2014/037-706 | Increased public sector good governance indicators | World Bank | 0 (2015) | 30 | 100 | 100 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2014/037-706 | New private sector investments linked or triggered by the action (in Euro) | World Bank | 0 (2015) | 0 | 200000 | 200000 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 1.100.546,54 EUR | 1.100.546,54 EUR |
| IPA 2014/037-706 | Number of employments created in targeted economic destinations. | World Bank | 0 (2015) | 50 | 150 | 150 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 56 employees by the beneficiaries | 56 employees by the beneficiaries |
| IPA 2014/037-706 | Municipal revenue tax collection | SSO | 100 (2015) | 100 | 102 | 102 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2016/039-619/06.03/ | 9. Client satisfaction rate (% SMEs stating satisfaction, added value of specific service provided) | EBRD | 0 (2016) |  | 85 | 85 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2016/039-619/06.03/ | 8. No of standards/new technologies introduced | EBRD | 0 (2016) |  | 30 | 30 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 5 | 5 |
| IPA 2016/039-619/06.03/ | 7. Leverage effect | EBRD | 0 (2016) |  | 48.000.000 | 48.000.000(2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 36.000.000 EUR | 36.000.000 EUR |
| IPA 2016/039-619/06.03/ | 6. Number on SMEs supported | EBRD | 0 (2016) |  | 120 | 120 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 60 | 60 |
| IPA 2016/039-619/06.03/ | 5. Speed of growth compared to the average for the country | EBRD | 100 (2016) |  | 110 | 110 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2016/039-619/06.03/ | 4. Employment growth rate of the supported SMEs | EBRD | 100 (2016) |  | 115 | 115 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | 3143 jobs sustained | 3143 jobs sustained |
| IPA 2016/039-619/06.03/ | 3. Turnover growth rate of the supported SMEs | EBRD | 100 (2016) |  | 125 | 125 (2020) | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available | Not Available |
| IPA 2016/039-619/06.03/ | 2. Contribution of SMEs to job creation | EURtat / SSO | 76 (2013) |  | 80 | 80 (2020) |  | 74.4 |  | 74.2 |  | Not Available |  |
| IPA 2016/039-619/06.03/ | 1. Contribution of SMEs to GDP (value added) | EURtat / SSO | 67 (2013) |  | 70 | 70 (2020) |  | 64.5 |  | 63.4 |  | Not Available |  |
| IPA 2019/041263.01/ | GDP per capita in PPS, in % of EU average, Region North East | National accounts, State Statistical Office, EURtat | 21 (2014) |  | 22 | 24 |  |  |  |  | 22 | 21.47 |  |
| IPA 2019/041263.01/ | GDP per capita in PPS, in % of EU average, Region Polog | National accounts, State Statistical Office, EURtat | 17 (2014) |  | 18 | 21 |  |  |  |  | 17.75 | 18.13 |  |
| IPA 2019/041263.01/ | GDP per capita in PPS, in % of EU average, Region South West | National accounts, State Statistical Office, EURtat | 27(2014) |  | 29 | 31 |  |  |  |  | 29.94 | 29.68 |  |
| IPA 2019/041263.01/ | Number of products being exported towards EU (CN codes recording positive export values) | National accounts, State Statistical Office, EURtat | 3257 (2016- 2017) |  | 3257 | 3500 |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Company Survival Rate | Business Demography, State Statistical Office, EURtat | 70.7% (2016 for enterprises born in 2014) 58.5% (2016 for enterprises born in 2013) 38% (2016 for enterprises born in 2012) |  | N/A | 72% for the companies born in 2022 60% for the companies born in 2021 50% 60% for the companies born in 2021 |  |  |  |  | 72,8 % (for companies born in 2016); 63.3 % (for companies born in 2015); 52.9 % (for companies born in 2014) |  |  |
| IPA 2019/041263.01/ | Level of legislative alignment with the EU Internal Market acquis (chapters 1, 3 and 6) | European Commission Country Report | Moderately prepared (2018) |  | Moderately prepared (2020) | Advanced stage of preparation (2024) |  |  |  |  |  |  | Chapter 1 and 3: moderately prepared. Chapter 6: good level of preparation |
| IPA 2019/041263.01/ | Number of new established companies. (of which companies run by women and people belonging to vulnerable groups and minorities) | Project report study/Evaluation | 0 (2018) |  | 0 (2018) | 30 (7/3) |  |  |  |  |  | - | - |
| IPA 2019/041263.01/ | Increase in turnover of the supported companies | Study/Evaluation | N/A |  | N/A | At least 10% 1 year after the company establishment |  |  |  |  |  | - | - |
| IPA 2019/041263.01/ | Jobs created in the targeted initiatives (sex disaggregated) | Project report study/Evaluation | N/A |  | N/A | 100 |  |  |  |  |  | - | - |
|  | Number of EU Directives and Regulations for which the alignment process is completed. and implementation is in place | Official Gazette | Current compliance can only be established after the preparation of ToC |  | 0 | 30 |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of procedures and formalities, which can be completed. online and which support cross-border. businesses | Project report Study / Evaluation | 0 (2018) |  | 0 | 10 |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of users of the . services of the established Single Point of Contact and national Product Contact Point(s) | Ministry of Economy | N/A |  | 0 | 150 |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Rate of companies reporting according to the new Company Law | Ministry of Finance | N/A |  | 0 | 100% |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of beneficiaries (people) trained on the new legal provisions (of the female) | Project report | 0 |  | 0 | 500 (200) |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of beneficiaries (institutions) trained. on the new legal provisions | Project report | 0 |  | 0 | 10 |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of beneficiaries (companies) trained on the new legal provisions | Project report | 0 |  | 0 | 1200 |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Indicators for market surveillance record2 (index) | State Market inspectorate yearly report | 24.104 (2017) |  | 21.104 | 35000 |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of consumers concerns submitted. through the Consumer and addressed (as % of the total) | e-Consumer statistics | N/A |  | N/A | 200 (at least 80%) |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of metrologies laboratories accredited. within the BoM | National Institute for Accreditation | 0 |  | 0 | 2 |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Number of start-ups and SMEs supported. (of them women-run businesses) | Project Report | 0 |  | 0 | 55 |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Improved performance of supported companies. (turnover and profit) | Project Report | To be established after the selection |  |  |  |  |  |  |  |  |  |  |
| IPA 2019/041263.01/ | Level of average salaries in the supported companies. compared to the one in the country | Study / Evaluation | 393 EUR (2018) |  |  | At least 2 % higher 1 year after operation |  |  |  |  |  |  |  |

# Education, Employment and Social Policy

- Involvement in programming

In 2016, the IPA Action Document 2017 was elaborated. The main features of the Action Document “Education, Employment and Social Policy” are as follows:

Overall Objective: To improve the effectiveness of the country's policy in the sectors of education, employment, and social inclusion

Specific Objective: To reduce the high rate of unemployment, increase labour market participation, of young people and women, increase access to quality education and training, improve skills matches and modernize the social protection system.

Results:

- Strengthened sector governance, policy framework and statistics

- Equitable access to quality inclusive education at all levels

- Improved employability and access to labour market and decent work

- Improved quality and availability of social services

EU Financial Support: 23,700,000 EUR

National Contribution: 1,450,000 EUR

Elaboration procedure: The Action document for the education, employment and social policy sector was drafted by the line ministries and relevant institutions in the last quarter of 2016, in parallel with the finalisation of the Sector Planning Document. In the first half of 2017, it underwent three cycles of quality reviews and exchanges with the services of the EU Delegation and the European Commission. In parallel, two rounds of consultations were implemented with CSOs, development partners and other stakeholders.

In 2018, the IPA Action Document and the SRC 2019 were drafted. The Action Document was centred on the Social Policy while the SRC was centred on Youth education and employment.

Elaboration procedure: Four meetings of the SWGs focused on programming in plenary session were organised in 2018 and 2019. Donors, Embassies and CSOs were always part of these meetings. The Ministers in charge of the sector chaired all meetings. Next to the meetings of the SWG in plenary sessions, three bilateral meetings with the EU Delegation, one donor coordination meeting on the VET sub-sector, as well as a number of thematic meetings including the concerned parties were organised.

In 2019 the AD and the SRC were further negotiated ending with a Commission decision as of 28.12.2019 for adoption of IPA 2019 Programme, while the Financing agreement was signed in March 2020. The main features of the adopted programming Documents are as follows:

| Action Document “EU for Inclusion” | Sector Reform Contract “EU for Youth” |
| --- | --- |
| Overall Objective: To reduce poverty in the country Specific Objective: To improve social, education and economic inclusion of people belonging to most vulnerable groups Results: Result 1: Improved housing, education, and economic opportunities for Roma and people living in deep poverty Result 2: Improved accessibility of educational facilities for persons with disabilities Result 3: Improved access to community-based services for vulnerable groups of people Requested EU Financial Support: 6,500,000 EUR National Contribution: 800,000 EUR | Overall Objective: To enhance the employment of young women and men Specific Objective: Improving the quality, relevance and inclusiveness of the national vocational education and training system. Improving employment opportunities for young women and men. Results: Result 1: Improved offer of accredited VET programmes and providers Result 2: Competences of staff of the regional VET centres aligned with Human Resource management plan and accreditation criteria Result 3: Youth Guarantee implemented Requested EU Financial Support: 16,500,000 EUR National Contribution: N/A |

In spring 2020, the programming of IPA III started. This sector corresponds to the thematic priorities Education, employment, social protection and inclusion policies and health under Window 4. Competitiveness and Inclusive growth. The main elaborated draft documents are as follows:

| Strategic Response Education, employment, social protection and inclusion policies and health | Action Fiche EU for Quality Employment and Equal Opportunities | Action Document(s) EU for Improved health and social protection and gender equality (only EESP part without Health) |
| --- | --- | --- |
| Key thematic priorities: 2.1 To raise employment level and the quality of jobs and productivity 2.2 To reduce poverty and social exclusion 2.3 To ensure comprehensive, inclusive, and integrated modern education 2.4 To improve the health and well-being of the population and to improve healthcare by providing a sustainable and high-quality patient-centred health system. | Impact: To support reforms and policies that promote equal opportunities and access to quality employment and social protection for men and women Outcome 1: To improve the OSH system and practices Outcome 2: To support establishment of effective and efficient system which promotes achievement of gender equality, empowerment of women, tackling gender stereotypes and negative gender roles, ending gender-based violence Outcome 3: To create a framework for monitoring the quality social services Output 1.1: Improved OSH legislation and policy framework Output 1.2: Increased capacities for implementation, compliance, and enforcement of the OSH legislation Output 1.3: Promoted positive OSH culture, practices, and awareness Output 2.1: Integrated gender perspective in the policies on local and national level Output 2.2: Reduced gender gap in the labor market and enabled equal and non-discriminatory access to justice, education, health and social protection Output 2.3: Increased capacity to address issues related to gender-based and -domestic violence, including through better inter-institutional cooperation in data collection on national and local level Output 3.1: Strengthened monitoring and quality assurance of social services at all levels | Impact: To improve the health and well-being of the population and promote equal opportunities and access to quality employment and social protection for men and women Outcome 1: The OSH system and practices improved Outcome 2: The establishment of effective and efficient system which promotes achievement of gender equality, ending gender-based violence supported Outcome 3: Strengthened monitoring and quality assurance of social services at all levels Output 1.1: Increased capacities for implementation, compliance, and enforcement of the OSH legislation Output 1.2: Improved and upgraded OSH information system Output 1.3: Promoted positive OSH culture, practices, and awareness Output 2.1: Integrated gender perspective in the policies on local and national level Output 2.2: Reduced gender gap in the labour market and enabled equal and non-discriminatory access to justice, education, health, and social protection Output 2.3: Increased capacity to address issues related to gender-based and – domestic violence Output 3.1: Framework for monitoring the quality social services created Requested EU Financial Support: 11,000,000 EUR National Contribution: 1,500,000 EUR |

- Overview of results in moving towards a fully-fledged sector approach (i.e. targets reached as per sector roadmap in the SPD)

In the Annex 4 of the report, detailed information about the implementation of the roadmap is presented. In the table below, the achieved targets and the concrete actions that are going to be implemented in order to fully implement the roadmap are summarised.

| Criteria: Strategic Planning | Self-assessment: The targets for 2017, 2018 and 2019 have been reached, while for 2020 are on track. |
| --- | --- |
| Criteria: Administrative Capacity | Self-assessment: Most of the targets for 2017, 2018, 2019 and 2020 have been reached. Some sub-targets for 2020 are on track. |
| Criteria: Coordination | Self-assessment: The targets for 2017, 2018, 2019 and 2020 have been reached. |
| Criteria: Performance | Self-assessment: The targets for 2017, 2018 and 2019 have been reached, while for 2020 are on track. |
| Criteria: Budget | Self-assessment: Most of the targets for 2017, 2018 and 2019 have been reached, while for 2020 are on track |
| Remarks: The Strategic documents for the sector have been prepared and approved. In the second half of 2019, the ESRP 2020 was reviewed, and the Government adopted a Revised ESRP 2022. The revision extended the ESRP timeframe to 2022. A limited number of headlines, outcome and process indicators are set for each area to measure the overall progress in each area of ​​the ESRP. New target values ​​for 2022 are set for all indicators. The country performed well with reaching the targets for the most indicators in the area of employment, some indicators in the area of education and social protection. Slow progress is observed with regards to social inclusion of Roma. In the last quarter of 2020, the MLSP made preparations for drafting annual report on implementation of the ESRP 2022. The annual report for 2020 will be produced in Q1 2021. Assessment of EMPLS 2016-2020 implementation is underway. Recommendations and lessons learnt will be integrated in the new Employment Strategy, which shall be elaborated in the first half of 2021. The first implementation report on the Education Strategy 2018-2025 was published in March 2019. In the second half of 2019, MoES start working on developing monitoring mechanisms for implementation of the Education Strategy. Revision of the Education Strategy 2018- 2025 is planned - activities and expert assistance is provided from Erasmus + program for 2021. The update will include new annex for internationalization of education. In addition, the Acton plan from OECD report is in implementation phase and is separated from the report on the Education Strategy 2018-2025 . The second implementation report on the Education Strategy 2018-2025 is expected in Q1 2021and will incorporate status of implementation for the period 2019-2020. The administrative capacities have been continuously boosted. Human resources in lead institutions have been strengthened, though fluctuation of employees is always possible. Several recruitments or internal promotions in lead institutions were implemented in 2019 on positions of relevance for implementation of the reforms. By and large, the policy making in 2020 was happening in a context influenced by the pandemics. Capacities for implementation of sector reforms were enhanced during 2020 (adjustment of the working tools, adjustments of the business processes, etc.), despite the restrictive environment imposed by Covid-19. The pandemic emphasised the need to adjust the working methods of the ministries and its implementing institutions, especially towards greater digitalisation of their business processes.It also emphasised the need for future investments in human and financial resources of the implementing agencies, especially employment service and social services. Capacity building was implemented with own resources and with assistance of the UN agencies, EU and other donors. Further work is needed with regards to introduction of programme budgeting, policy monitoring and gender-sensitive policy making A high-level sector policy discussion on the sector strategy and the PAF was channeled through the SWG with involvement of stakeholders (civil society sector and social partners) and donor community. The Sector-based Performance Assessment (PAF) has been developed throughout 2019, consisting of 48 key indicators necessary to track the performance of the Education, employment and social policy sector. The EESP Sector Working Group reviewed the PAF. Once adopted by the government, the PAF will be available on a web-based platform and will enable monitoring of the country’s progress in the national context, but also its performance compared to the EU average and countries in the region. In 2020, core indicators of the PAF were updated and were translated in the IPA III Strategic Response, together with targets for 2027. The Government has launched a wide-scale PFM Reform programme in 2018. The Programme is still under implementation. |

- Coordination with other instruments and/or donors/ IFI's within the sector

The following meetings of the SWG/donors’ Coordination were organised in 2020:

| Date | Number of participants | Discussed topics |
| --- | --- | --- |
| 18.6.2020 | around 60 attendees (virtual meeting) | Presentation of draft IPA III Strategic Response and its thematic priorities, elaboration of proposed actions for IPA programming 2021-2022 and presentation of draft UN Cooperation Framework for 2021-2025 |
| 16.11.2020 | around 78 attendees (virtual meeting) | Debate about IPA III Strategic Response |

Moreover, three technical level sessions were organized to discuss IPA III priorities and three other meetings to discuss the EU4Youth programme. Regarding the SBS “EU for Youth” (IPA 2019 programme), one meeting was organised with MLSP, ESA and EUD on 7.10.2020. Another common meeting involving national institutions was organised on 11.11 involving the ministers. One workshop on technical level was organised on 3.12.2020 with MLSP, MoES, SEA, MF, ESA and EUD representatives to consider the progress of the EU for Youth and to clarify the SBS implementation modality.

The following Donors, IFIs, Embassies and CSOs were invited/present at these meetings;

| Donors and International Organisations | IFIs | Embassies | CSOs |
| --- | --- | --- | --- |
| EUD | WB | UK | Foundation Open Society Macedonia |
| USAID |  | Swiss | IPA 2 Mechanism |
| IOM |  | Austrian | Gender Equality Platform |
| OSCE SMMS |  |  | National Network to End Violence Against Women and Domestic Violence |
| UNDD |  |  | Coalition Sexual and Health Rights of Marginalized Communities |
| UNDP |  |  | CSO Reactor |
| UNICEF |  |  | Foundation for Education and Cultural Initiatives ‘Step by Step’ |
| ILO |  |  | Nansen Dialogue Centre Skopje |
| UNFPA |  |  | Association for Health Education and Research Hera |
| MCEC |  |  | Macedonia Civil Education Centre |
|  |  |  | CSO Humanost |
|  |  |  | Macedonian Platform Against Poverty |
|  |  |  | European Training Foundation |
|  |  |  | Resource Centre for Parents of Children with Special Needs |
|  |  |  | Progress Institute for Social Democracy |
|  |  |  | Coalition of Youth Organizations - SEGA |
|  |  |  | Foundation Agro-Centre for education |
|  |  |  | Federation of Trade Unions of Macedonia |
|  |  |  | Business Confederation of Macedonia |
|  |  |  | Macedonian Confederation of Free Trade Unions |

In the sector EESP, the following programmes financed by the donors are under implementation:

| Donor | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| UNFPA/ UNPRPD | 196,188 € | UNFPA Country programme/DP/FPA/CPD/MKD/1: Gender-based violence; PwD/deinstitutionalization; prevention of early marriages and family planning services | 2018 - 2020 |
| SDC/ UN Women | 2,949,867 € | Support of gender responsive budgeting | 2018 -2020 |
| Swiss Development Cooperation (SDC) | 4,260,622 € | Fostering employability of hard to employee people | 2017 - 2020 |
| USAID | 1,085,400€ | Strengthening interethnic interaction among children | 2017 - 2021 |
| Swiss Agency for Development and Cooperation | 5,652,429 € | Education for Employment in Macedonia (E4E@mk) | 2018-2022 |
| USAID | 5,800,000 € | Youth Ethnic Integration | 2017-2022 |
| USAID | 1,300,000 € | Advancing Social Cohesion | 2017-2021 |
| USAID | 4,000,000 € | You Think (Media literacy and critical thinking) | June 2019- June 2024 |
| UK, British council | 10 mil. Pounds for all Western Balkan countries | 21 Century Schools Programme in the Western Balkans | 2018- 2021 |
| Children foundation – Pestaloci | 332.000€ | Inclusion of Out-of-school Children in the Educational System | 2018-2020 |

In the sector EESP the following loans financed by the IFIs are under implementation:

| IFI | Value of the support | Addressed issues | Implementation period |
| --- | --- | --- | --- |
| WB-IBRD | 33.4 million $ | Social Service Improvement Project (Development loan) Its overall goal is to expand access to and improve the quality of social services, including pre-school services for vulnerable groups. The loan will support: 1. Social inclusion through improved access to social benefits and services i.e., the project will support creation and expansion of preventive and non-residential social services and 2. Expanding the access to and improving of the quality of preschool services for children from socially disadvantaged backgrounds | September 2019 – June 2024 |
| WB-IBRD | 15.17 million $ | Social Insurance Administration Project (SIAP) (Development loan) The SIAP project will support the government’s efforts to create a more efficient social insurance administration system. The project will consist of the following components: Component 1. Improving the quality of the social insurance administration services, Component 2. Strengthening the regulatory framework for people with disabilities and for hazardous occupations and Component 3. Project management, monitoring and evaluation | February 2020 - April 2023 |
| . WB-IBRD | 24 million $ | Skills Development and Innovation Support Project Its objective is to improve transparency of resource allocation and promote accountability in higher education, enhance the relevance of secondary technical vocational education, and support innovation capacity in the country. The project consists of the following components: 1) improving transparency of higher education; 2) modernization of secondary Technical Vocational Education and Training (TVET); 3) improving the innovative capacity of enterprises and collaboration with research organizations; and 4) project management and monitoring and evaluation. | January 2014 – May 2021 |
| IBRD | 25 million $ | Construction of 145 school sports halls and rehabilitation of schools | 2008- 2024 |
| WB-IBRD | 24 million $ | “Primary Education Improvement Project (PEIP) P171973” | 2020-2027 |

- The impact of IPA II actions within the sector on the development of the relevant national administrative capacity in the sector, strategic planning, and budgeting

The IPA II has an impact in the sector either through the preparation of Action Programmes or through the implementation of TA projects or through the cooperation between the National Authorities and the Institutions of the European Union. Considering that it is not always possible to separate impacts according to the years, in the table below, the main improvements on the functioning of the sector are presented.

Strategic Planning: IPA II supported the strategic planning in a several priority areas of the EESP sector. First, the lead ministries were assisted with the revision of the Employment and Social Reform Programme 2020 (ESRP). This included facilitation of the consultations and participation of social partners and civil society organisations. The Revised ESRP 2022 consists of a limited number of priorities in labour market, employment policies, human resources, and skills development, as well as social inclusion and social protection policies. Second, the Ministry of Labour and Social Policy received a targeted technical assistance for completion of legal framework for delivery of specific social services. Several by-laws were drafted and adopted by the Ministry at the end of 2019. This is also a contribution for completion of deinstitutionalisation and promotion of community-based living in line with the National Strategy on Deinstitutionalisation 2018-2027, developed earlier with EU assistance. Third, the leading ministries received technical assistance to compile the Performance Assessment Framework for the EESP sector. With TA (“Support for the Management of the EU Funds”), the list of indicators was fine-tuned, and the EU and regional benchmarks were collected. In addition, the Ministry of Labour and Social Policy, the Economic and Social Council and its standing committees received assistance (by ILO in the frame of the EU Projects “Strengthening Social Dialogue”) to forecast the key labour market and poverty indicators, which are part of the PAF and the Strategic Response under IPA III. The indicators will be further discussed in the frame of development of new Employment Strategy. Fourth, as reported in the Annual report 2018, the social mapping of Roma that was published in 2019 will enable evidence-based policy making and targeted policy responses for inclusion of the Roma community as part of the new policy cycle after 2020. Fifth, the Ministry of Labour and Social Policy and the Economic and Social Council were presented with analyses on the social and economic impacts of the COVID-19 and planning more targeted solutions to help the employers and workers. During 2019 and 2020, the Ministry of education and science drafted and adopted several crucial laws and by- laws. The Law on Primary education was prepared and adopted in 2019 as well as the Law on Teachers and Professional Associates in Primary and Secondary Education. Additionally, in 2020, the government adopted the bylaws of the Law on Higher Education and the establishment of the Agency for Quality in Higher Education, Board for Accreditation of Higher Education and Board for Evaluation of Higher Education which were considered as priorities. Furthermore, the process continues with the reform of the method of financing the higher education institutions and the adoption of bylaws for the Law on Higher Education. New Law for Adult Education is prepared, and past trough Governmental session (December 2020) and the Law for Vocational education is under revision, first draft is expected end of February 2021. In this direction MOES adopted several strategies and concepts such as Strategy on Entrepreneurial Learning 2014-2020, Strategy on Adult Education 2019-2023, Strategy for Vocational Education and Training in a Lifelong Learning Context 2013-2020 and action plan, Concept for Development of a System on Distance Learning in Primary and Secondary Education (adopted July 2020), Concept on Inclusive Education (adopted July 2020), Concept on National Assessment in Primary Education (adopted June 2020) Three New Concepts are under preparation at the moment Concept for primary education and Concept for Secondary education including Concept for teaching and didactical materials and The Concept for operationalisation of the future Regional VET Centers is in Draft form. Several amendments were included in the law for Primary education and in the Law for Secondary education to make possible education under pandemic, e.g. distant learning. Protocols for students’ dormitories were adopted by the Government and several measures were implemented to support students in higher education such as covering part of the costs for tuition fee, and costs for student dormitories. The Government offered vouchers for covering 50% of the costs of the training for all young people that will attend training for digital competences. Adapted curricula for primary and secondary education were developed and approved National Platform for Online Learning that allows two-way communication between students and teachers was developed (www.schools.mk). The platform contains: Video material, tutorials and manuals. During September, trainings for all teachers were organized by implementing cascade model. An educational TV show with the teaching materials is broadcasted on the National TV Station in order to reach all children. On the aspect of Digitalization, MoES intend to make technological progress in a data-driven education, creating a single space for data allowing flowing freely within the ministry and across sectors for the benefit of public administration, schools, researchers and all other relevant stakeholders.

Administrative Capacity: Capacity building was provided to the relevant authorities involved in design and implementation of community-based services. The sector dialogue was intensified at the level of the EESP SWG, but also through capacitating the social partners to take part in the discussions of the Economic-social councils on national and local level and thus shape the economic and social policy. This was further reinforced by the capacity building of one of the standing committees of the Economic and Social Council for forecasting of the key labour market and poverty indicators. PAF development itself meant a shift towards measuring the effects of the policy interventions and increased awareness of the two-line ministries about the importance of the policy monitoring. Staff from line ministries were trained in policy making. Capacity building was provided to the relevant authorities involved in design and implementation of community-based social services and discussions regarding the pre-school professional development have been initiated. In addition, Ministry of education and science created a specialized Unit in the ministry for Analysis and Research for Developmental of Education Policy with the aim to collect, maintain and evaluate administrative data in the institution. With TA “Support for the Management of the EU Funds”, the quality of detailed designs for the kindergartens in municipality of Tetovo and Terrace were significantly improved, and the projects are mature for tendering. Important lessons for planning works projects were learnt from the whole process of revision of the tender documentation on national and local level. With assistance provided by the TA “Support for the Management of the EU Funds”, Detail Design for reconstruction and adaptation of 13 educational institutions (schools and university’s ) are prepared for tendering.

Performance: The Revised Employment and Social Reform Programme 2022 took note of the changes brought by the policy measures over the past 2,5 years, i.e., since the adoption of the ESRP in 2017. It assessed the performance in the sector by looking into the value of the ESRP indicators against the targets set for 2020. In the Revised ESRP 2022, a limited number of headlines, outcome and process indicators are defined to measure the overall progress in each area of ​​the ESRP. Target values ​​for 2022 were agreed for all indicators. Simultaneously, Performance Assessment Framework for the EESP sector was finalised and discussed by the EESP SWG. In the context of the IPA III programming, targets were set for 2027 and the SWG considered the new long-term targets.

Budget: The Budget of the Ministry of Labour and Social Policy and affiliated sector institutions for 2020 noticed an increase in several areas which will receive IPA funding, such as, for example, pre-school, employment policy and deinstitutionalisation. However, Covid-19 pandemic had an impact on economic flows and therefore, the national budget was revised twice (in April and September 2020) to finance the adopted sets of policy measures aimed at mitigating the impacts of Covid-19 on the economy and the world of work. The budget of the MoES increased by 3,34% in 2020 (26.096.948 thousand MKD) compared to 2019 (26.096.948 thousand MKD). In the Budget for 2020 of the Ministry of Education and Science, noticed an increase in several areas which will receive IPA funding, such as the new budgetary program. Regional VET Centres opened for funds which are foreseen for preparatory measures for establishing Regional VET Centres as anticipated in the Sector Reform Contract 2019 However, Covid-19 pandemic had an impact on the budget therefore, the national budget was revised twice (in April and September 2020) to finance the adopted sets of policy measures aimed at mitigating the impacts of Covid-19 In the Budget for 2021 of the Ministry of Education and Science added significant amount of funds for supporting the establishment of the RVETC.

Under indirect management by RoM:

- OS(s) in place and related changes, if relevant:

Eight out of 21 projects of the AP 2017 are implemented indirectly by the IPA Operating Structures (OS), which were responsible for implementation of the IPA 2007-2013, human resources development component. The Operating structure consists of the CFCD in capacity of Contracting Authority and the IPA units in the Ministry of Labour and Social Policy (MLSP) and the Ministry of Education and Science (MoES), responsible for programming and implementation of the Action programmes. Mutual relationships are regulated in the Operational Agreements between the Head of the CFCD and the IPA Coordinators in the respective line ministries included in the Country Action Programme for year 2017.

There are two units in the MLSP in charge for IPA: Unit for IPA Coordination and Implementation of EU Financial Instruments and Unit for IPA Monitoring and Evaluation of IPA. At the end of 2020, there were 8 persons employed in the IPA Units in the MLSP (three being managerial staff and five expert level staff), thanks to two new employments and internal promotion of staff in 2019. According to the workload analysis the optimal number would be nine, which is calculated for all IPA (both indirect and direct management) and non-IPA related tasks.

Within the MoES there are two units in charge of IPA: Unit for Implementation and Coordination of IPA and Unit for Programming, Monitoring and Evaluation of IPA. During 2020 IPA Structure was left with only 2 permanent contact employees and 1 employee engaged on contract basis until 31.12.2020. In January 2020 one of the officers for implementation and coordination left the ministry. In February, one of the officers for implementation and coordination was appointed as IPA Coordinator and the officers for programming was appointed as Head of Unit for programming, monitoring, and evaluation in the IPA structure. The latest WLA expresses the need of 5 additional officers with total number of IPA staff to be 8 employees.

- Information on the implementation of Action programmes under indirect management in the sector

The procurement plan for the projects implemented under indirect management (Results 2 and 3 of AP 2017, Action 4) was adopted in August 2018 and it was revised twice in 2019 and 2020.

| Result/Activity/Project | 2019 | 2020 | Programmed (EUR) | Contracted (EUR) |
| --- | --- | --- | --- | --- |
|  | P | C | P |  | IPA | Total |
| Result 2: Equal access to quality inclusive education at all levels |
| Improving the quality of pre-school education and care (Activity 2.1.) | x | x |  | 1,500,000 | 1,150,750 | 1,150,750 |
| Expanding the network of public pre-school institutions in rural and urban areas – works (Activity 2.2.) |  |  | x | 2,075,000 |  |  |
| Expanding the network of public pre-school institutions in rural and urban areas -supervision (Activity 2.2.) |  |  | x | 150,000 |  |  |
| Further support to the implementation of the National Qualifications Framework (Activity 2.3.) | x |  | x | 1,500,000 | / |  |
| Further support to the implementation of the National Qualifications Framework - Procurement of equipment (Activity 2.3.) | x |  | x | 412,000 | / |  |
| Improving the quality of education (Activity 2.4.) | x |  | x | 1,500,000 | / |  |
| Result 3: Improving employability and access to the labour market and decent work |
| Increasing attractiveness, inclusiveness and relevance of VET and adult education (Activities 3.1; 3.2; 3.3; 3.4) | x |  | x | 2,300,000 | / |  |
| Support for the active labour measures (Activities 3.5; 3.6) | x | x |  | 3,350,000 | 3,000,000 | 4,191,401 |
| Improving the working conditions (Activities 3.7; 3.8) | x | x |  | 1,000,000 | 855,440 | 855,440 |
| Total: | 7 | 3 | 6 | 13,787,000 | 5,006,190 | 6,197,591 |

- Main achievements in the sector

Under IPA AP 2017, three contracts under indirect management under the responsibility of the MLSP are in phase of implementation. The outbreak of COVID-19 in the first half of 2020 significantly affected the intensity of activities in the sector, especially those that involve greater clients’ participation. The approach adopted was to continue with all that could be implemented remotely without jeopardizing the quality of the work, health, and participation of beneficiaries. Limited progress in terms of achieved results could be reported because it takes time before desired outcomes in social field become visible.

Under IPA AP 2017, Four contracts under indirect management under the responsibility of the MOES are in launching phase. One of them is under relaunching because it was already launched ones and cancel because of the COVID 19

In the table below, the project of the MLSP that are under implementation.

| Contract title | Status | Expected result | Achieved result | Remarks |
| --- | --- | --- | --- | --- |
| AD IPA 2017 EESP - Raising the quality of pre-school education and care | On going | Introduced professional and career development of preschool staff; remodelled (re)licencing of pre-school staff; empowered parents to engage in pre-school education of their children. | None yet | Under implementation, mainly in line with the work plan. The components of the professional and career development system have been developed |
| AD IPA 2017 EESP - Support for the active labour measures | On going | Improvement of employment perspectives for social welfare recipients. Social welfare recipients have acquired skills which will help them improve their participation on the labour market. New services for counselling and motivation targeting social welfare recipients will be developed and tested. | None yet | Under implementation, with project management related delays and by the COVID-19 lock-down. |
| AD IPA 2017 EESP - Improving the working conditions | On going | Established system and build capacities for monitoring and detecting the informal economy; Developed, piloted and rolled out agreed model and measures for strengthening the labour and social security benefits and incentives for transition to formal jobs. | None yet | Under implementation, with project management related delays. |

- Recommendations for further actions

| SMC Operational conclusions | How are recommendations taken on board? |
| --- | --- |
| Direct Grant to the Employment Service Agency value of around EUR 4.2 million, the Ministry of Finance will consent the announcements of the new post for the recruitment. The Employment Service Agency will recruit staff as soon as possible and before the end of 2019. The vacancy notes will be disseminated as widely as possible to attract higher number of qualified applicants. (1st SMC) | The project team in ESA was recruited in full composition in the 1st quarter of 2020. |
| The adoption of the amendment on Regional VET Centres to the Law on Vocational Education concerning secondary education to be done by the end of 2019, immediately followed by a decision on the selected VET Centres for the transforming of those chosen municipal/regional schools into Regional VET centres. (1st SMC) |  |
| The National Agency for European Educational Programmes and Mobility shall be invited to the monthly progress review meetings to give information to EU Delegation and to be involved more in the projects and activities. (1st SMC) |  |
| Increase Audit Authority recommendations implementation rate to 70 % next year, following the agreed deadlines with the auditors. (2nd SMC) |  |
| Ministry of Labour and Social Policy will recruit Head of the Unit for Monitoring and Evaluation of IPA by end-June 2021. The Ministry of Education and Science will recruit at least 2 additional IPA staff by end-March 2021. (2nd SMC) | Head of Unit in the MLSP shall be recruited in the 1st quarter of 2021 in accordance with the Annual Recruitment Plan of the MLSP. |
| CFCD/line ministries to provide a plan for trainings on lessons learnt to the staff directly involved in the tender document’s preparation by end-February 2021. (2nd SMC) |  |
| The revision of work-plan for “Support for the active labour measures” with assessment of delays to be finalised in Q1 2021. The new work-plan should include updated realistic timeline with justification for its extension. The Employment Service Agency will share the mitigation measures work plan by end of 2020 for improving its work in order to avoid delays in implementation. (2nd SMC) | In November 2020, ESA submitted revised work plan along with proposal, mitigation measures and justification for extension of the timeline of the grant contract. The proposal is being considered and discussed with the MLSP. The proposal will be considered by the Steering Committee on 28.01.2021. |
| Tender Documents for construction of kindergartens in Tetovo and Tearce - EUD offers the possibility to sit together with CFCD and make sure comments are understood and action is clear. CFCD will approach EUD couple of days after receiving EUD comments on the TDs. The engineer will participate to the meeting. (2nd SMC) | The tender documentation was revised. MLSP organised a clarification meeting with the CFCD and EUD on 18. 01.2021. |
| Activity 2.4 Improving the quality of education – Ministry of Education will urgently meet CFCD on the preparation of the Tender Documents. (2nd SMC) |  |

# II a. Performance indicators in the Education, Employment and Social Policy sector covering both direct and indirect management

Indicators per programme

| Financing Agreement/Programme reference | Indicator for sector EESP | Source | Baseline | Target (2020) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA 2017/040200.04.EU | Progress made towards meeting accession criteria | EC Country Report | Moderately prepared (2016) | Good level of preparation | Well advanced (2022) | Moderately prepared (2017) | Moderately prepared (2018) | Moderately prepared (2019) | Moderately prepared (2020) |
| IPA 2017/040200.04.EU | Employment rate 15-64 years, total % | EURtat | 43.52% (2010) | 50.8% | > 53% (2022) | 50.52 % | 51,9 % (Q3 2018) | 54,8% (Q3 2019) | 53,26% (Q3 2020) |
| IPA 2017/040200.04.EU | Unemployment rate (15+) Total % | State Statistical Office | 32.0% (2010) | 21.5% | < 19% (2022) | 22,4 % | 20.8% (Q3, 2018) | 17,1% (Q3, 2019 | 16,08% (Q3 2020) |
| IPA 2017/040200.04.EU | Increased students' achievements in international tests | Official PIRLS, TIMSS and PISA Reports | PIRLS – out of 45 participating countries, the former Yugoslav Republic of Macedonia was ranked on place No. 38 (2006) TIMSS – out of 59 participating countries, the Republic of North Macedonia was ranked in mathematics on 43 place, and in science knowledge it was ranked on 52 places. (2011) PISA – out of 72 participating countries, the Republic of North Macedonia in literacy and science was ranked on 69 place and in mathematics it were ranked on 68 places. (2015) | Improved level results in reading literacy since last participation in PIRLS Improved level results in mathematics and science knowledge since last participation in TIMSS Improved level results (closer to the OECD average) in science, reading and mathematics since last participation in PISA | Improved level results in reading literacy since last participation in PIRLS Improved level results in mathematics and science knowledge since last participation in TIMSS Improved level results (closer to the OECD average) in science, reading and mathematics since last participation in PISA | N/A No participation in the latest PIRLS 2016. The next PIRLS is for the 2021 year. TIMSS 2019- the data (official release of international results) will be available in December 2020. The results from PISA 2018 are expected to be published in December 2019. | N/A No participation in the latest PIRLS 2016. The next PIRLS is for the 2021 year. TIMSS 2019- the data (official release of international results) will be available in December 2020. The results from PISA 2018 are expected to be published in December 2019. | PISA – out of 77 participating countries, the Republic of North Macedonia in literacy and mathematics was ranked on 67 place and in science knowledge it was ranked on 63 places. (2019) The next PIRLS is for the 2021 year. TIMSS 2019- the data (official release of international results) will be available in December 2020. |  |
| IPA 2017/040200.04.EU | Number of persons in employment, including self-employment 6 months upon benefiting from employment programmes or services of this Action Segregation of data by gender and age group | ESA data base; ESA/MLSP reports; | Minimum 1000 women - 60% young people (18-29) - 70% | Minimum 1500 women - 50% young people (18-29) - 30% | Minimum 1500 women - 50% young people (18-29) - 30% | n/a | n/a | n/a | n/a |
| IPA 2017/040200.04.EU | Percentage of early leavers from education and training: percentage of population aged 18-24 with at most a lower secondary education and not in further education and training | State Statistical Office | 11,3 % (2015) | 10,5% | 9,5% | 8,5% | 7.1% | 7.1 % | Not yet published |
| IPA 2017/040200.04.EU | Students drop-out rate in compulsory education – segregated data per - type of educational level/type: primary, secondary gymnasium, VET; - gender, - status - students with special educational needs, talented pupils, students from low-income families and from rural areas, minority | State Statistical office, MoES EMIS system, Primary and secondary schools data | - 0,8% student drop-out rate in primary education -0,9% student drop-out rate in secondary education | Students drop-out rate in primary and secondary education decreased by 0,8% from the data for 2015/2016 school year. | Students drop-out rate in primary and secondary education decreased by 0,8% from the data for 2015/2016 school year. | - 0.5% students drop-out rate in secondary education in 2016/2017 school year | - 0.9% Students drop-out rate in primary education - 0.9% students drop-out rate in secondary education in 2017/2018 school year |  |  |
| IPA 2017/040200.04.EU | Number of persons benefiting from non-institutional (alternative) community based social services - segregated data by type of service (day-care centres, homecare and other support social services, excluding foster families) and gender/ethnic group/disabilities - cumulative | MLSP database on social protection institutions, State Statistical Office reports | Total:811 611 (2016) beneficiaries in day-care centres 200 beneficiaries of homecare 0 beneficiaries of other support social services | 1250 | 1600 |  | Total: 894 500 (2018) beneficiaries in day-care centres 326 beneficiaries of homecare 68 beneficiaries of other support social services | 1139 678 (2019) beneficiaries in day-care centres 402 beneficiaries of homecare 59 beneficiaries of other support social services | 937 persons 483 (2020) beneficiaries in day-care centres 300 beneficiaries of homecare 154 beneficiaries of other support social services |
| IPA 2017/040200.04.EU | Trade Union Density rate and Employers’ organisations density rate | The official reports from the social partners; report generated from the MLSP database on SP membership | Trade Union Density rate - 22% (2016) | 25% | 26% | Trade Union Density rate 21,16% | Trade Union Density rate 22% Employers’ organisations density rate 26% | Trade Union Density rate 18.02% Employers’ organisations density rate 26% | Trade Union Density rate 17.5% Employers’ organisations density rate 23.62% |
| IPA 2017/040200.04.EU | No of labour market analysis prepared | MLSP and ESA reports; Governmental information; intervention reports | 0 | 1 | 2 | 0 | 1 | 2 | 3 |
| IPA 2017/040200.04.EU | Percentage of all labour market and employment measures subject to analysis from a gender perspective | MLSP and ESA reports; Governmental information; intervention reports | 0 | 30% | 70% | / | / | / |  |
| IPA 2017/040200.04.EU | Percentage of persons (students/unemployed/employed/adult learners) covered by statistics | MLSP and ESA reports | 0 | 50% | 75% |  |  |  |  |
| IPA 2017/040200.04.EU | No of beneficiaries with improved skills for data collection and data analysis and forecast skills | Intervention’s report | 5 | 15 | 20 | / | / |  | 48 |
| IPA 2017/040200.04.EU | Percentage of NESC opinions on economic and social reforms upon which feedback by the Government is received | NESC tracking mechanism | 0 | 50% | 80% | 100% | 100% | 100% | 100% |
| IPA 2017/040200.04.EU | Number of local employment pacts concluded | LESC meeting minutes | 0 | 3 | 4 |  | / | 4 |  |
| IPA 2017/040200.04.EU | Number of additional spaces for children 0-6 years created in pre- school institutions | State Statistical office, MLSP database on pre-school institutions | 0(2016) | 590 | 590 |  | 1415 | 1842 | 482 |
| IPA 2017/040200.04.EU | Revised programme for pre-schools education meeting the requirements of the ELD Standards adopted | Official gazette | 0 | 1 | 1 | / | / | / |  |
|  | Percentage of pre-school teachers and caregivers involved in professional development | Intervention reports; MLSP database | 0 | 30% | 50% | / | / | / | / |
| IPA 2017/040200.04.EU | % of school staff in primary schools are trained for early recognition and support of pupils with special educational needs | MoES database |  |  |  |  |  | / | / |
| IPA 2017/040200.04.EU | No of revised/modernised and verified educational programmes for adults | MoES/ CAE data base | 0/130 | 3/150 | 200 | 73 additional (315 in total) | 85 additional (400 in total) | / | 43 new +10 (in procedure) |
| IPA 2017/040200.04.EU | Number of qualifications developed, adopted (and integrated/registered inside the NQF register) according to the labour market needs | Government Decisions; MoES Orders; NVETEC Minutes; Reports of the appropriate body | 0 | 60 | 100 | 2 | 38 (40 in total) | 64 | 71 |
| IPA 2017/040200.04.EU | No of Sector Qualification Committees established and operational | Government Decisions; MoES Orders; NVETEC Minutes; Reports of the appropriate body | 0 | 6 | 10 | 0 | 9 | 9 | 11 |
| IPA 2017/040200.04.EU | Number of students enrolled in post- secondary education | MoES EMIS system and CAE data base | 600 (2015/2016 school year | 750 | 900 | 265 in the 2016/2017 school year | 258 in the 2017/2018 school year | / | 240 in in the 2019/2020 school year |
| IPA 2017/040200.04.EU | Number of persons involved in employment programmes and services supported by the Action, segregated data by gender, age group, ethnicity | ESA database; ESA/MLSP reports; documents on the attendance of persons participating in employment programmes; resumes of participants; copies of certificates/diplomas (in case they are issued); evaluation reports. | 472018 women - 60% young people (18-29) - 70% Roma - 32 | 5000 women - 50% young people (18-29) - 30% Roma - 200 | 5000 women - 50% young people (18-29) - 30% Roma - 200 | / | / | / | 153 women – 93 (61%) young people (18-29) - 32 (21%) Roma – 36 (24 |

| Financing Agreement/Programme reference | Indicator for sector EESP | Source | Baseline | Target (2020) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA 2019/041-263/07.03/MK/Youth | Youth employment rate 15-29 years, total % Women in employment rate 15-24 24-29 | Labour Force Survey, State Statistical Office | 30.9% (2018) 12.2% 41.6% |  | 32.8% (2022) 13.0% 42.9% |  | 30.9% 12.2% 41.6% | 34.4% 15.8% 47.8% |  |
| IPA 2019/041-263/07.03/MK/Youth | Percentage of participants (sex disaggregated) who successfully 2 completed the Youth Guarantee (as a % of those neither in education, employment nor training included in the Youth Guarantee) | Employment Service Agency | Pilot exercise: 36% (2018) Target regions: 0 Roll-out 1st half 2019 – 29% | 20% | Average for the 3 years: 22,3 2021 – 20% 2022 – 20% 2023 - 25% |  |  |  | Total exits: 3002 (1362 women) or 28.9% Exits into employment 2507 (1080 women) Exit into active labor market measures (trainings, etc.) 495 (282 women) |
| IPA 2019/041-263/07.03/MK/Youth | Number of participants (sex disaggregated) registered in the Youth Guarantee (entry level) | Employment Service Agency | 5266 (2018–pilot exercise) 10,007 (1st half of 2019 – roll-out), of them 5,255 in the target regions | 3000 | Cumulative new 9700 |  |  |  | 10353 (5184 women) |
| IPA 2019/041-263/07.03/MK/Youth | Number of Youth Guarantee staff trained, sex disaggregated, (6 full day training days per person) | Employment Service Agency | 22 in the target regions (1st half of 2019 – roll-out) | 30 | Cumulative new 90 |  |  |  | 30 |
| IPA 2019/041-263/07.03/MK/Youth | Number of ESA centres modernised/upgraded (in the target regions) | Employment Service Agency | 3 (2018) | 3 | Cumulative new 9 |  |  |  | 1 |
| IPA 2019/041-263/07.03/MK/Youth | Decrease in early leavers rate 5% increase in enrolment rate of students with special needs in VET in 2022 (sex disaggregated) | LFS, 2017 EURtat/SSO | National average 8.5% (2017) | 0 | Down by 1% | 8.5% |  |  | Down by 0,25% |
| IPA 2019/041-263/07.03/MK/Youth | Establishment of regional VET centres in the target regions | VET Law published in the Official Gazette Accreditation certificate Relevant by-laws | 0 | Legal provisions in place to allow the creation of regional VET Centres (YES/NO indicator) | 3 accredited regional VET centres in operation (YES/NO indicator) | 0 | 0 | 0 | VET Law amended |
| IPA 2019/041-263/07.03/MK/Youth | Number of VET qualifications open for VNFIL | Reports from MoES and VET Centres and adult’s education centres | 0 | 0 | 6 | 0 | 0 | 0 | ongoing |
| IPA 2019/041-263/07.03/MK/Youth | Percentage of staff of the RVET Centres trained in line with the HR development Plan (Of them % trained to work with SEN) | Reports from MoES and VET Centres and adult’s education centres | 0 | Adopted organigramme and HR development Plan - 1 per Centre (YES/NO indicator) | 90% of the staff trained (of them, 35% trained to work with SEN) | 0 | 0 | 0 | In progress |
| IPA 2019/041263.04/ | At-risk-of-poverty rate in % of population | State Statistical Office, SILC – Survey on Income and Living Conditions | 22,2 % (2017) | 19 % (ESRP) | 17% |  |  |  | Not available yet |
| IPA 2019/041263.04/ | At-risk-of-poverty rate before social transfers and before pensions in % of population | State Statistical Office, SILC – Survey on Income and Living Conditions | 22,2 % (2017) | 19% | 16,5% |  |  |  | Not available yet |
| IPA 2019/041263.04/ | Number of persons employed (Roma and other people living in deep poverty), as a result of the Action, sex disaggregated data | Project-based documentation showing how many Roma people were employed as a result of project activities (Grants contracts) | N/A | N/A | 100 |  |  |  | Not available yet |
| IPA 2019/041263.04/ | Number of Roma and people living in deep poverty, who benefit from social services and housing improvements as a result of the Action, sex disaggregated data | Administrative data of the Ministry of Labour and Social Policy and Employment Agency | (0) | 1500 | 4000(Cumulative) |  |  |  | Not available yet |
| IPA 2019/041263.04/ | Number of students with disabilities with improved access to education sex disaggregated data | Interim and Final report on the implementation of the Action by the Ministry of Education and Science | 90 | 90 | 110 |  |  |  |  |
| IPA 2019/041263.04/ | Number of vulnerable citizens, who benefit from social? services offered by community based social service (data disaggregated by sex, age, health status) | Administrative data provided by the Ministry of Labour and Social Policy, Institute for Social Affairs | (0) | 150 | 300 |  |  |  | Not available yet |
| IPA 2019/041263.04/ | Number of persons (Roma and people living in deep poverty) benefiting from employment related services, sex disaggregated data | Report on grant project implementation | N/A | 20 | 250 |  |  |  | Not available yet |
| IPA 2019/041263.04/ | Number of children (of Roma families and families living in deep poverty) involved in educational process, sex disaggregated data | Report on grant project implementation | N/A | 50 | 200 |  |  |  | Not available yet |
| IPA 2019/041263.04/ | Number of Roma settlements that are legalised | Report on grant project implementation | 0 | 0 | 3-4 Roma settlements |  |  |  | Not available yet |
| IPA 2019/041263.04/ | Number of houses for Roma and families living in deep poverty that are built, refurbished or connected to the municipal sewerage system | Report on grant project implementation | 0 | 0 | 200 |  |  |  | Not available yet |
| IPA 2019/041263.04/ | Number of primary and secondary schools and university faculties made accessible to people with disabilities as a result of the Action | Annual report on the specific indicator elaborated by the MoES | 0`11 | 0`12 | 3 primary 3 secondary 2 university 13 faculties |  |  |  |  |
| IPA 2019/041263.04/ | Number of community-based social services established as a result of the Action | Database of the social protection institutions in the MoLSP | 0`14 | 0 | 0`15 |  |  |  | Not available yet |

# Cross-Border Cooperation

- Involvement in programming as appropriate

IPA cross border cooperation enables the achievement of sustainable development of the border regions. The Ministry of Local Self-Government of the Republic of North Macedonia (MLSG) is the institution responsible for the implementation of the EU pre-accession assistance instrument IPA – component for cross-border cooperation. Upon completion of the IPA I CBC programmes, the programming process began at the end of 2013 and was completed during 2014 when the European Commission approved 4 of the cross border cooperation programmes. Currently, the cross-border cooperation programme between the Republic of North Macedonia and the Republic of Serbia is in the process of implementation, which is the only CBC programme that lasts 4 instead of 7 years (2016- 2020).

During 2020, activities related to the programming process of IPA III for the period 2021-2027 started as follows:

- IPA Cross Border Cooperation programme between Albania and Republic of North     Macedonia  2021- 2027

The programming period began with the appointment of members of the Joint Working Group for IPA III programming responsible for the preparation of the programming document 2021-2027, i.e.: institutions at national and local level, civil society and business sector. Both beneficiary countries started discussing the thematic priorities of the program for the future period 2021-2027. During 2020, working meetings were held with the Joint Programming Working Group, among other things, the Rules of Procedure of the Joint Working Group were adopted. Three meetings (3) of the JTF with the participation of 106 attendees in total were organised. During the IPA III programming process, the emphasis was on supporting strategic projects like: "Lake Ohrid - bridging two countries to one destination" and "Rehabilitation and reconstruction of Northern Macedonia - Albania Spas (Debar) - Blata (Dibar) Border crossing). These efforts resulted in the inclusion of the two above- mentioned strategic project ideas in the first draft document of the IPA III program between North Macedonia and Albania 2021-2027, already submitted to the EC, Skopje office in December 2020.

- IPA Cross Border Cooperation programme between Kosovo – Republic of North Macedonia      2021 - 2027

The process of preparation for the IPA III 2021-2027 programmes for cross-border cooperation Republic of North Macedonia - Republic of Kosovo started in April 2020. After the creation of the Joint Task Force three meetings were held. Training for the members of the Joint Task Force was also organized.

In September 2020, the process of surveying the stakeholders of the IPA III 2021-2027 programme was concluded. Three questionnaires were prepared for representatives of local government, civil society organizations and the business community. 40 answered questionnaires were received, which provided the basis for the final IPA Programme Thematic Priorities.

On December 26, 2020, the first draft version of the IPA 3 2021-2027 programme documents was sent to the EU Office in Kosovo by the National IPA Coordinator in Kosovo.

- IPA Cross Border Cooperation programme between Serbia and Republic of North Macedonia  2021- 2027

Bilateral meetings between the Republic of North Macedonia and the Republic of Serbia, as well as meetings of the Joint Monitoring Committee, meetings of the Project Steering Committee, were realized. Throughout 2020, activities related to the programming of the IPA III programming period Serbia-North Macedonia 2021-2027 were implemented. The programming process was preceded by several bilateral meetings between the two Operating Structures from North Macedonia and Serbia, all with the aim of successful implementation of the process and timely submission of a draft program document to the European Commission. To that end, a mixed group of eligible representatives from both countries was first formed. The Joint Programming Working Group was formed with the appointment of members, including representatives from ministries, municipalities, regional planning centres and non-voting observers from DEU in MK and DEU in Serbia as well as representatives from the CBIB + 3 project.

One training on programming was organized for the members of the Joint Task Force (JTF), OS and JTS. The Joint Technical Secretariat distributed questionnaires to potential CBC beneficiaries via e-mail.

At the meetings, the Joint Programming Body agreed on a strategic direction for the future program after analysing the filled in questionnaires. Each JTF meeting was preceded by a preparatory meeting with members of MK institutions.

The first thematic priority as part of the first thematic cluster refers to employment, labour mobility, social and cultural inclusion between the two countries. The second thematic priority arises from the fourth cluster and refers to the expansion of tourism, cultural and natural heritage. During December 2020, a public consultation was held in RS and MK to revise the first draft of the program document.

- Interreg  IPA  Cross Border Cooperation programme between Republic of Bulgaria and Republic of  North Macedonia 2021- 2027

In 2020, the Joint working group for programming the new programming period 2021-2027 held several meetings where the draft Logic of intervention for the new programming period 2021-2027 was presented.

As a result of the held cross-border regional consultations, the following common territorial challenges were highlighted: unfavourable demographic development (population aging, net migration); mass depopulation in rural areas on the Bulgarian side of the border; emigration of skilled labour; low rates of entrepreneurial intensity and research and development and seasonal nature of land tourism and low potential for complement / integration in maritime tourism, etc.

Regional and local stakeholders expressed readiness to involve a new type of beneficiaries, partnerships and activities (through direct support to SMEs), but also insisted on the sustainability of previous ones and capitalization of experience in cooperation between the two countries.

Priority Goal 5 "Europe closer to the citizens" was supported by stakeholders as the most appropriate way to implement integrated measures that can contribute to addressing challenges in the border region, inter alia: construction of an access road and the opening of a new border crossing between the two countries at Strumiani – Berovo. In this regard, it was suggested that the Program should support a strategic project to fulfil the still pending bilateral government engagements (signed in 1999).

For the purposes of implementing PO 5 "Europe closer to the citizens", the Governing and National body of the program will support local stakeholders in developing a territorial strategy for integrated measures. A Steering Committee will be established to represent all relevant regional and local authorities and bodies, as well as other local stakeholders involved in the preparation and implementation of the strategy.

- Interreg  IPA  Cross Border Cooperation programme between Republic of North Macedonia and Greece 2021 - 2027

According to the new IPA programming period, the 1st Joint Programming Committee (JPC) meeting of the Interreg IPA Cross-Border Cooperation Programme “Greece-Republic of North Macedonia 2021-2027” was held on July 13th, 2020, via teleconference. The Rules of Procedure were approved by the Programming Committee. It was presented the Concept Paper, and useful comments were provided by the participants, as well by the Programme Manager at DG for Regional Policy and Urban Policy of the European Commission. The Methodology was adopted by JPC. All proposals concerning the content will be examined by the consultant experts through a socio-economic analysis and preparation of the New Programme Document. However, it is underlined that everyone is invited to actively participate in the public consultation which is planned to be concluded in following period. The Public Consultation was initiated through Structured questionnaire vie EU e-survey in 2 official languages of the participating countries in the beginning of 2021. It is estimated that a final Draft could be submitted for comments to the European Commission in September – October 2021.

- INTERREG program EURO-MED 2021 – 2027

As regard Interreg Euromed Programme 2021-2027 and its amendments, on 30.09.2020, the European Commission sent to the working group of the program a revised proposal for the geographical coverage of the Interreg Euromed Program 2021-2027. At the meeting of the Executive Members of the Program, held on 20.10.2020, it was agreed that the Republic of Bulgaria and the Republic of North Macedonia will be invited to participate in the Program. As agreed at the meeting, the European Commission sent a letter inviting the Republic of Northern Macedonia to contact the Steering Body of the transnational program for obtaining information on the procedure and manner of our country's participation in the next Interreg European Mediterranean Area 2021-2027.

- ADRION - Transition Program - Post 2020 Programming

The Ministry of Local Self-Government is involved in the programming of ADRION transnational program. This program, which includes several European-Mediterranean countries, enriches transnational cooperation with new partnerships and better opportunities for better regional development.

A taskforce has been set up at Programme level to discuss among the Partner States the areas and topics of the new ADRION and the ways to involve Programme stakeholders with public consultations. A public and stakeholders’ consultation was organised to receive feedback from citizens, as well as Programme stakeholders on the relevance of the Policy Objective preliminary identified by the Task Force for ADRION post 2020. Stakeholders’ events were also organised to raise the discussion on ADRION post-2020 and ease the compilation of the stakeholder’s survey targeted to experts involved in each specific Priority Objective (PO). These informative events took place in October and November 2020.

The territorial analysis highlighted some important issues that could improve the quality of life of the citizens living in the area as well as increase the economic growth. Preliminary identified ADRION Policy Objectives:

- A smarter Europe by promoting innovative and smart economic transformation.

- A greener, low-carbon Europe by promoting clean and fair energy transition, green and blue investment, the circular economy, climate adaptation and risk prevention and management.

- A more connected Europe by enhancing mobility and regional ICT connectivity.

- Enhance institutional capacity of public authorities and stakeholders to implement macro-regional strategies and sea-basin strategies

- Progress made in implementing the CBC programme and in particular in achieving the specific objectives per thematic priority (including qualitative and quantitative elements indicating progress in relation to targets)

- IPA Cross Border Cooperation program between the Republic of North Macedonia and Republic of Albania 2014-2020

The cross-border cooperation program between Republic of North Macedonia and Republic of Albania aims to ensure a more balanced, inclusive and sustainable socio-economic development of the cross-border region. It covers the following regions: the Pelagonija region, the Polog region and south-western region in the country.

The reporting year was very significant in terms of both programme and projects’ implementation. Major issues were tackled, and very significant challenges were confronted during this period. Due to the situation with the Covid19 pandemic throughout both countries and Europe, many activities scheduled to take place from March 2020 till nowadays, were made mainly online. The OSs together with the JTS and supported by DEU in MK had succeeded to duly perform the planned activities through online meetings/tools, even exceeding the scheduled activities and implementing new activities.

All the necessary measures to ensure a good implementation of the Programme and of its Technical Assistance were taken. It was provided input for the concept regarding the 3rd Call and all the necessary arrangement for the appointment and establishment of Joint Task Force (JTF) in charge of strategic planning and programming of the document 2021-2027 IPA III CBC. Three (3) JTF meetings and other relevant meetings were organized in the frame of programming of IPA. Both Oss successfully carried out in close collaboration with the DEU, the evaluation process of the strategic project ideas / facilitating the process of making the preselected strategic project ideas as much mature as possible so far.

From the total number of 9 project proposals under the 1stCfP, 4 projects were under implementation during 2020 and ended within 2020. The DEU in North Macedonia as Contracting Authority was responsible for all matters related to contracting and payments.

From the total number of 5 project proposals, under the 2ndCfP, all 5 projects were under implementation during 2020. The DEU in North Macedonia as Contracting Authority was responsible for all matters related to contracting and payments.

The 3rd and the last CfP under this CBC programme was launched on 11th of November 2020. Financial allocations for the years 2018, 2019, 2020 / 4,930,000.00 EUR EU contribution.

| Cooperation Programme name | Cross Border Cooperation programme between R. of North Macedonia and R. of Albania 2014- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| I Call for Project Proposals | 96 | 9 |
| Priority Axes 1. Environment 2. Tourism 3. Competitiveness |  | 2 2 5 |
| II Call for Project Proposals | 60 | 5 |
| Priority Axes 1. Environment 2. Tourism 3. Competitiveness |  | 1 4 0 |

- IPA Cross Border Cooperation program between Kosovo – Republic of North Macedonia      2021 – 2027

On March 29, 2019, EUOK launched the Third Call for proposals with a total available budget of 2,040,000 EUR. The third call covers two thematic priorities: Thematic Priority 2 - Encouraging tourism and cultural and natural heritage (840,000 EUR) and Thematic Priority 3 - Protecting the environment, promoting climate change adaptation and mitigation, risk prevention and management (1,200,000 EUR).

In the frame of the CBC programme between the Republic of North Macedonia and the Republic of Kosovo, including the 3rd CfP, 12 projects were approved.  In 2020, the Operating Structure in cooperation with the Joint Technical Secretariat/Antenna Office prepared the proposal for the 4th Call for project proposals in the total value of 2.040.000-euro, EU funds. The 4th Call for Proposals was launched in the end of February 2021.

| Cooperation Programme name | INTERREG Cross Border Cooperation programme between the R. of North Macedonia and the R. of Kosovo 2014- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| I Call for Project Proposals |  |  |
| Total available budget: 2.040.000,00 EUR | 52 application in total 23 pre-selected for full application | 8 projects (Initially 9 projects signed but 1 project cancelled by CA immediately in the first month of implementation) |
| II Call for Project Proposals |  |  |
| Total available budget: 350.000,00 EUR (leftovers from the 1st Call for Proposals) | 15 application | 1 project |
| III Call for Proposals: Total available budget: 2.040.000,00 EUR | 31 applications | 3 projects Tourism 1 Environment 2 |
| Priority Axes 1. Environment – 2. Tourism –3. Competitiveness – |  | Tourism 8 projects Competitiveness 2 projects Environment 2 |

- IPA Cross Border Cooperation Programme  between Republic of North Macedonia –Republic of Serbia  2016-2020

The program area covers the Northeast Region and part of the Skopje Region. The eligible area covers 10,197 km2 with approximately 732,000 inhabitants in 30 municipalities or 15% of the total territory of the Republic of North Macedonia. The goals of the program are to promote employment opportunities, labour mobility and social and cultural inclusion. The program aims to tackle high levels of unemployment, while taking advantage of job opportunities identified in promising sectors, promoting cross-border labour mobility, and improving cooperation between enterprises, education, and employment institutions. It also aims to promote an inclusive society, including cultural aspects, by developing new or upgrading existing services and programs that combat social exclusion. Activation of the natural and cultural potentials of the Sustainable Tourism Program Area was recognized as one of the key areas of cooperation where significant improvements can be made in the long run and where different actors will be involved in the process. Due to the pandemic with COVID-19, the meetings were held on-line.

The proposed projects from the First Call in December 2020 for funding by the Joint Project Evaluation Committee were approved by the EU Delegation to RS. The first call for proposals was announced in the amount of 1,260,000 euros for both countries. The first call for proposals in the amount of EUR 1,260,000 for both countries was announced on 25.07.2019. The evaluation process has completed, and projects are selected as follow in the table below:

| Cooperation Programme name | Cross Border Cooperation programme between the R. of North Macedonia and the R. Serbia 2016- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| I Call for Project Proposals |  | 5 Projects Provisionally selected |
| Total available budget: 1,260.000,00 Euros Priority Axes: 1.TP1 Promoting Employment 2.TP2 Encouraging Tourism | 52 applications in Total received | 2 Projects selected on TP1 Projects selected on TP2 |

- Interreg - IPA Cross  Border Cooperation  programme  between  the Republicof North  Macedonia and  the Republic  of Bulgaria  2014 – 2020

Interreg IPA Program for cross-border cooperation between the Republic of North Macedonia and Republic of Bulgaria 2014-2020 aims to strengthen cross-border cooperation between people and institutions in the region to jointly managing common challenges and use the unused potential for development of the cross-border region through efficient use of resources. The program focuses on measures aimed at mitigating the effects of climate changes as well as addressing issues related to nature and biodiversity, sustainable use of nature resources, environmental protection, and cross-border risk management. The focus of the program is also on the protection of the region’s natural and cultural heritage. In addition, financing helps increase the competitiveness of small and medium enterprises and facilitate their access to new markets.

Within the First Call under Interreg - IPA Cross-border Cooperation Programme between the Republic of Bulgaria and the Republic of North Macedonia, 48 contracts were concluded. A total of 46 projects were completed at the end of 2018 and 2 projects were completed in the middle of 2019. The Second Call for Proposals under Interreg - IPA Cross-border Cooperation Programme between the Republic of Bulgaria and the Republic of North Macedonia for a total amount of EUR 6,917,631.00, was lauched on 09.02.2018. The Joint Program Monitoring Committee, held in Berovo on 17.01.2019, preliminarily approved the financing of 17 projects under the Second Call for Proposals. Additionally, 8 new projects from the reserve were selected and 3 of them were contracted in December 2020 and 5 will be contracted in 2021. Out of the initially contracted 17 projects, 7 were completed in 2020 and 10 investment projects are still ongoing. In the period January – December 2020, a total of 37 requests for national co-financing were submitted by the grant beneficiaries and based on them, the Ministry of Local Self-Government as a national body under the programme paid a total of € 139,737.72.

| Cooperation Programme name | INTERREG Cross Border Cooperation programme between R. of Bulgaria and R. of North Macedonia 2014- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| I Call for Project Proposals | 216 (of which 3 after deadline) | 48 |
| Priority Axes 1. Environment 2. Tourism 3. Competitiveness |  | 14 17 17 |
| II Call for Project Proposals | 162 | 20 (already contracted) |
| Priority Axes 1. Environment 2. Tourism 3. Competitiveness |  | 8 9 3 |

- Interreg IPA Cross Border Cooperation programme between  the Republic of Greece  and   the Republic  of  North Macedonia 2014-2020

The strategic goal of INTEREG IPA Cross border cooperation program between the Republic of Greece and the Republic of North Macedonia 2014-2020 is to improve territorial cohesion by improving living standards and employment opportunities, while considering the natural environment and use of natural resources for development of tourism.

The program, in accordance with the EU IPA II regulation No 231/2014, ensures better utilization of the assistance for the beneficiaries, through their integration in the reforms and development agendas. The sectoral approach of IPA II promotes structural reforms. The program in the Republic of North Macedonia is implemented in 4 regions:  Pelagonia region, Vardar region, southeast   and southwest region. The total budget of Interreg IPA II Program for cross-border cooperation between the Republic of Greece and the Republic of North Macedonia during the program period of 2014-2020 is  45,470,066.00 €.

A Technical Assistance project implemented under shared management mode is managed by the Ministry of Local Self Government (herewith, the National Authority of the Programme) to ensure a sound basis for the implementation of the operational framework of the Programme in the territory of the Republic of North Macedonia. Activities are performed in coordination and in close cooperation with the Main Management Body of the Programme, i.e. the Managing Authority and the Joint Secretariat of the Programme, based in Thessaloniki, Hellenic Republic.

In January 2020, the Joint Secretariat of the Interreg IPA CBC Programme Greece -Republic of North Macedonia was fully staffed with the engagement of the Joint Secretariat Coordinator. Now, the following human resources are engaged: JS Coordinator, 3 Project Officers, 1 Communication and TA Officer, Financial Officer, as well  1 Administrative Assistant and 1 Antenna Officer at the Antenna office in Bitola.

The progress in Programme implementation during the reference period is significant, both in qualitative and quantitative terms. In 2020, all 40 projects contracted under the First Call for Proposals are being implemented. They include 18 projects under Priority 1 and 22 Projects under Priority 2. The committed funds amount to € 15.6 mil. under Priority 1 and € 23 mil. under Priority 2. The projects involve 82 Greek beneficiaries and 68 beneficiaries from the Republic of North Macedonia. Some beneficiaries are participating in more than one project. Therefore, the total number of project partners is 202.

A second Call for project proposals was launched in 2019 and evaluated in 2020. Following the allocation of Programme funds under the 1st Call, and the relevant recommendations of the Programme’s external evaluators, the Call was targeted to Specific Objectives 1.1, 1.3 & 2.4. It was also restricted to partnerships with competence and specialization in the above-selected objectives. Call’s published budget was € 6 million. It attracted 45 proposals, from which 10 were rejected during the A’ phase. Concerning the Programme absorption of the allocated funds, the n+3 2020 target was successfully achieved. The total public expenditure verified was: 12.5 million € by 31.12.2020 (10,7 million € EU contribution). The TA assisted the Ministry of Local Self Government to conclude an agreement with the specialized IT company InTec Systems from Skopje to install IT infrastructure and hardware at the ministry’s premises as a first step in developing the software of the Information module. Within the Technical Assistance activity plan for 2020,  it was launched a tender for supplying of one vehicle exclusively for the needs of National Operating Structure of the Programme. The procurement was implemented from beginning of November through to end of December, and it was implemented in line with the IPA procurement manual in force,   approved by the JMC  through the 20th written procedure on April 27, 2020, in response to the last request for budget modification, namely for reallocation of unspent funds from 2019 in 2020.

The Territorial Cooperation Management Operating Structure within the Ministry of Local Self

Government has continued coordinating the appointment of First Level controllers to IPA

project partners in the country. According to the rules described in the Management and Control System (MCS), the national co-financing rate of 15% has been paid in time to IPA beneficiaries.

The following table illustrates the data for the relevant period under the programme to date.

In accordance with the 20th written procedure of the JMC, a new employee to the post of monitoring and control officer (MCO) was recruited to support the National operating structure and the Antenna officer based in Bitola

In coordination with the Managing Authority, the National Authority submitted the new projections sheet of estimated technical assistance savings (NMK budget) that will occur for the years 2020 - 2023. The savings are intended to be reallocated to the other two priority axis of the programme

- Program for Transnational Cooperation INTERREG V-B Balkan- Mediterranean 2014-2020   (BalkanMed)

In the frame of the Programme for transnational cooperation Balkan- Mediterranean were granted 37 transnational projects. All the projects are ongoing.

| Cooperation Programme name | INTERREG programme for Transnational Cooperation Balkan Mediterranean 2014- 2020 |
| --- | --- |
|  | No. of applications received | No. of actions selected for funding |
| I Call for Project Proposals | 149 projects received | 37 projects selected for funding |
| Priority Axes 1. Entrepreneurship and Innovation 2. Environment |  | 37 |

- Monitoring, including data collection arrangements and where applicable evaluation activities.

All 40 projects signed for funding from the 1st Call for Proposals under the INTERREG IPA CBC Programme Greece- R. North Macedonia 2014-2020 were monitored and controlled, following national legislation for operations in the pandemic situation. However, the actions were mainly monitored through control of the documents and video records of the actions uploaded in the MIS system. At the same time, dozens video conferences and on-line meetings with the project beneficiaries for monitoring of the ongoing project activities were organized. The results were appropriate in a pandemic situation as was during 2020. Most of the joint events, and on-spot-visits could not be organized and the participation by the Programme staff and project staff was disabled.

Many events like the trainings, seminars, workshops, cultural events, networking, and etc. were replaced with on-line events, or were postponed for next implementation period. This problem also raised the issue of having several requests of no-cost extension.

On-the-spot actions mostly were carried out in the Republic of North Macedonia by the Antenna Office and the Programme staff from the Ministry of Local Self Government.

Under IPA CBC Programme between the R. of Kosovo and the R. of North Macedonia for the period January–December 2020, JTS and Antenna Office in cooperation with CBIB+3, finalized the revision of the indicators for the three CfP.  All 12 projects are now entered into a database and submit reports every three months. The data from the monitoring database can be found in AIR 2020. in March 2020, JTS/Antenna Office in cooperation with OSs and CA organized the 5th field monitoring visit. The fields visits were stopped and not all beneficiaries were visited due to the spread of Covid-19 and the request from CA to cancel any activities that require physical presence. Thus, the monitoring were transferred online and the 6th round of monitoring was organized for the projects from the 3rd CfP in September 2020.

Under the IPA CBC programme between the Republic of Bulgaria and the Republic of        North  Macedonia in the course of 2020, 2 final monitoring on the spot and 1 on - line monitoring of "soft" projects of the Second Call were implemented by Main office and branch office staff.  One suspected irregularity was detected by JS Main office Kustendil, as a result financial correction of circa 125,000 Euro was applied. Additionally, four signals of suspected irregularities were received by the Managing Authority of the programme in the period of May - June 2020. The Ministry of Local Self-Government, as the National Authority of the programme, has started the procedure for clarifying the cases of suspected irregularity. In two cases, expenditures are proposed to be considered as non-eligible ones.

Under the IPA CBC programme between the Republic of North Macedonia and Albania, in the course of 2020, the monitoring of the projects financed under the 1st and 2nd CfP took place physically or virtually.

Under IPA CBC Programme between Serbia-North Macedonia 2016-2020, there are 5 projects approved for implementation and 3 contracted in 2020. Since the implementation did not start during the reporting period, the monitoring did not start yet as well.

- Coordination with the partner country.

The IPA CBC Programme Kosovo – Republic of North Macedonia 2014-2020 for the period January – December 2020 has organized 5 bilateral meetings with the partner OS in Kosovo: two technical bilateral meetings and 3 working meetings during the preparation of IPA III. Additionally, the project steering committee organized the 9th and last meeting to approve the final report of the TASC. JMC meeting are organized regularly as foreseen in the working plan.

Under the IPA CBC Bulgaria - Republic of North Macedonia, the National Authority/Operating Structure in the Ministry of Local Self-Government, during 2020, held 4 technical meetings with partner institutions from the Managing Authority in the Ministry of Regional Development and Public Works of the Republic of Bulgaria (9th April, 2020, 10th June 2020, 18en September 2020 and 6th October 2020). Moreover, the 7th Joint Monitoring Committee meeting was held on 16.10.2020 for the first time through an online conference platform and 8 (eight) JMC written procedures.

Regarding the CBC Republic of North Macedonia - Greece, coordination and collaboration among partner countries focused on several issues, particularly on implementation of the projects from the 1st Call for Proposals, launching and evaluation of the projects from the 2nd Call for Proposals, smooth Programme implementation and absorptions of funds through the Priority Axis 3 - Technical Assistance, visibility actions of the Programme implementation, training of the representatives from Ministry of Local Self Government and FLC controllers from the IPA country to use the MIS system, as well collaboration in the programming process related to the programming period 2021-2027.

The participating countries organized the 6th Joint Monitoring Committee on 24th November 2020 through Webex platform, as well 6 written procedures were initiated and closed: the 18th written procedure Feb.24 - Mar. 2, 2020;  the 19th written procedure Mar. 27 - Apr. 06, 2020;  the 20th written procedure Apr.10 - Apr. 27, 2020; the  21st written procedure Sep.17 - Sep. 27, 2020;  the 22nd written procedure Sep.25 - Oct.10, 2020,  the 23rd written procedure Dec. 1 - Dec.8, 20201.

The members of the Joint Steering Committee from both countries brought decisions for the modifications of ongoing projects through 8 written procedures:  the   6th written procedure was approved on  March 4 - March 14, 2020;  the 7th written procedure  was approved on  April 13 - April 23, 2020;  the 8th written procedure was approved on   May 21 - May 31, 2020; the 9th written procedure was approved on   June 19 - June 26, 2020; the 10th written procedure  was approved on  Sep.7 - Sep.18, 2020;  the 11th written procedure was approved on   Sep. 16 - Sep. 27, 2020;  the 12th written procedure  was approved on  Nov. 20 - Nov. 30, 2020 and the 13th written procedure  was approved on  Dec. 10 - Dec.20, 2020.

The representatives of both National Authorities, Managing Authority and Joint Secretariat , beside the regular communication and coordination, had physical working meeting on 20th of October 2020 in Thessaloniki.

Besides that, the 1st Joint Programming Committee Meeting with participation of the representatives from both countries was held on 13th July 2020 through Webex platform.

The Managing Authority organized training for planning and recording of On-the-spot Verifications and related use of MIS (following the procedures from the Management and Control System of the Programme) for the National Authority, Ministry of Local Self Government and the FLC controllers from the Republic of North Macedonia on 23rd June 2020.

The IPA CBC programme Republic of North Macedonia - Serbia in the frame of the bilateral CBC programmes, there are standard joint technical bodies establishes in the very start of the implementation of the programme: The Joint Secretariat and the Antenna Office. Each of these located in one of the countries. Moreover, on programme level there is the Joint Monitoring Committee that represents the highest decision-making body (in shared management) that leads he overall implementation of the programme. The joint Monitoring Committee meets face to face at least two times a year and the meetings take place in each country in the rotation principle. This body is co-chaired by representatives of the two counties. A row of technical meetings is also held, for the IPA- IPA CBC Programmes the Steering Committee Meetings are regularly organized to follow the implementation of the TA service contract that follows these CBC programmes.  During the programming phase both structures form the Joint Task Force groups that lead this process.

Meetings between OSs and JTS

One meeting was organized between the OS and MS in Serbia: NAO Support Office, MoF- Sector for Management of EU Funds and CFCU; MEI- CBCB and HoS Support Unit and JTS staff working on programmes implemented under the indirect management. It was held on 7 September 2020 via MS Team platform.

The topics were: Functioning of the management system of the CBCPs SRB-BIH and SRB-MNE

Review on the status of implementation of the contracted projects within the CBCPs SRB-BIH and SRB-MNE, delays and obstacles in implementation;

Planning and organization of future activities.

JTS team was invited to attend this meeting in order to get acquainted to its format, participants and topics.

Due to the Covid-19 pandemic, the communication between the OSs and JTS team was increased regarding the daily running of the programme activities but no other separate meetings were organized in 2020 between the OSs and JTS.

The draft Implementing manual for the CBCP Serbia- North Macedonia with Annexes was prepared and sent to CA and CB for comments on 18 June 2020. An online meeting via Viber application was held on 24th December, with the participation of OSs, CFCU and JTS.

The manual was sent by CA to CB on 21 December 2020 for final commenting and approval.

JMC meetings and outputs

In line with Article 78, paragraph 1 of the Framework Agreement and Article 19, paragraph 1 of the IPA II Implementing Regulation (EU) No 447/2014, participating countries concerned (IPA II beneficiaries) established a JMC within six months from the entry into force of the first Financing Agreement. The first FA for 2016 allocation entered into force on 30 December 2017, while the first JMC meeting was held on 11 May 2018.

Due to the specific circumstances, namely the Covid-19 pandemic situation, the JMC did not meet physically in 2020. Instead, the relevant decisions were made either through written procedures or alternatively via WebEx online platform. Nevertheless, all the relevant decisions were discussed and adopted by the JMC in timely manner.

The JMC written procedure was launched on 29 January 2020 with one topic on the agenda: Adoption of the Annual Implementation Report (AIR) for 2019 (ref: TASC-2017/394/782). The procedure was closed on 13 February 2020 and the Annual implementation report was adopted.

The 5th JMC meeting was scheduled for 2 December 2020. The topics on the agenda were adoption of the JTS Annual Work Plan (AWP) and Communication Action and Visibility Plan (CAP) for 2021. However, the quorum for this online meeting was not reached.

The JMC written procedure was launched on 3 December 2020 with the same topics on the agenda. The JTS AWP and CAP for 2021 were adopted on 17 December 2020 through the written procedure with no comments or additional remarks from the JMC members. The Communication and Visibility Strategy is adopted for the whole duration of the Programme while the Action plan is adjusted and adopted annually.

The 6th JMC meeting was held on 2 December 2020 via Webex online platform. The JMC members adopted the changes of the JMC RoP concerning the number of days for written procedure in urgent circumstances. The List of operations selected through the 1st CfP Europe Aid /1651171/ID/Multi, under the IPA CBCP Serbia- North Macedonia 2016- 2020.

Technical meetings between the Operating structures

Three Technical meetings were held between the OSs in 2020. The first meeting was held via Webex platform on 15 May 2020. The representatives of both OSs participated in it, as well as CBIB+ and JTS. The second meeting was held via Webex platform on 29 July 2020. The representatives of both OSs participated in it, as well as CBIB+ and JTS.

The third meeting was held via Viber on 13 October 2020. The representatives of both OSs participated in it, as well as MK NIPAC and JTS.

IPA CBC programme Republic of North Macedonia and Republic of Albania 2014-2020

The OSs (MoLSG& MEFA) had taken all the necessary measures to ensure a good implementation of the Programme and of its Technical Assistance. Many meeting under the iniciative of the Oss were organized during the reporting period

JMC meetings:

- - 8th JMC meeting was heald in Hotel “Millenium” in Tushemisht, Albania on 13th of February 2020, in parallel with the “Induction” trainingfor the GBs under the 2nd CfP, with 23 attendees. On this JMC meeting were endorsed AIR for the year 2019 and work plan for the year 2020.

- - 9th JMC meeting was held on 3rd of September 2020 via Zoom Online platform. On this meeting were approved the concept for 3rd CfP (size of grants, investment elements, partnerships, etc) as well as the direction for further evaluation of the strategic project’s ideas.

- 18 technical online meetings among Oss, JTS and DEU had been organized related to project and programme implementation and its progress.

- Both Oss together:

- Provided input for the concept regarding the 3rd Call.

- Provided all the necessary arrangement for the appointment and establishment of Joint Task Force (JTF) in charge of strategic planning and programming programming of the document 2021-2027 IPA III CBC.

- Organization and participated in all three (3) JTF meetings and other relevant meeting organized in the frame of programming of IPA 3,

- Successfully carried out in close collaboration with the DEU, the evaluation process of the strategic project ideas / facilitating the process of making the preselected strategic project ideas as much mature as possible so far.

- Both Oss were involved in the procurement procedures, and different evaluations processes organized to this regar

# II a. Performance indicators in Cross Border Cooperation Programmes

| Financing Agreement/Programme reference | Indicator for sector Competitiveness and Innovation | Source | Baseline 2014 | Target (2023) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CBC RNM - AL | Output indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Number of trainees |  | 0 | 888 | 888 |  |  | 231 | 259 |
| CBC RNM – AL | Outcome indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Number of tourists using new/improved services |  | 00 | 5000 | 5000 |  |  | #N/A | 0 |
| CBC RNM – AL | Impact indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Average length of tourist stay increased (overnights) |  | 2,8 | 3,8 | 3,8 |  |  | N/A | 6.8 |
| CBC RNM – AL | Result: 1.1.2 Mutual co-operation, understanding and respect of cultural heritage and values are furthered |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Output indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Number of new cultural events (festivals, fairs, competitions) to connect people of the programme area organised |  | 0 | 20 | 20 |  |  | #N/A | 0 |
| CBC RNM – AL | New digitised collections/library funds created |  | 0 | 5 | 5 |  |  | #N/A | 0 |
| CBC RNM – AL | Number of cultural heritage sites improved |  | 0 | 4 | 4 |  |  | #N/A | 1 |
| CBC RNM – AL | Outcome indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Number of stakeholders involved in activities |  | 1465 | 1612 | 1612 |  |  | #N/A | 27 |
| CBC RNM – AL | Impact indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Number of visitors visiting supported natural and cultural heritage sites (baseline TBD, increase 15%)) |  | TBD | 15% | 15% |  |  | #N/A | 0 |
| CBC RNM – AL | Thematic priority 3: Enhancing competitiveness, the business environment and the development of small and medium-sized enterprises, trade and investment |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Specific objective: 2.1 The strengthening of the SME productive capacity and access to markets |  |  |  |  |  |  |  |  |
| CBC RNM – AL | 2.1.1 The SMEs and start-ups awareness and capacity to tap into new markets and value chains are enhanced |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Output indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Number of foreign trade activities |  | 0 | 10 | 10 |  |  | #N/A | 1 |
| CBC RNM – AL | Number of businesses/enterprises participating in new foreign trade activities |  | 0 | 50 | 50 |  |  | 0 | 41 |
| CBC RNM – AL | Number of SMEs with new conformity certificates awarded (ISO, HACCP, etc.) |  | 0 | 20 | 20 |  |  | 19 | 45 |
| CBC RNM – AL | Number of new markets and trade facilities developed through agreements |  | 0 | 3 | 3 |  |  | 0 | 0 |
| CBC RNM – AL | Outcome indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Increase in share of export value of goods and services (in %) |  | TBD | 3 | 3 |  |  | #N/A | n/a |
| CBC RNM – AL | Increase in turnover of businesses supported (in %) |  | TBD | 3 | 3 |  |  | 20 | 0 |
| CBC RNM – AL | Impact indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Gross Value Added by Sector (in %) |  | TBD | 3 | 3 |  |  | #N/A | n/a |
| CBC RNM - AL | Thematic priority: Protecting the environment and promoting climate change adaptation and mitigation, risk prevention and management |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Specific objective: 3.1 The awareness of a greener economy, cleaner environment and climate change is enhanced |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Result: 3.1.1 Awareness and knowledge of sustainable use of natural resources and environment is fostered |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Output indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Number of awareness campaigns on sustainable use of resources and a cleaner environment implemented |  | 0 | 12 | 12 |  |  | 2 | 0 |
| CBC RNM – AL | Number of improved waste management systems and value chains within the area |  | 0 | 6 | 6 |  |  | #N/A | 0 |
| CBC RNM – AL | Number of site cleaning actions implemented |  | 0 | 8 | 8 |  |  | #N/A | 0 |
| CBC RNM – AL | Outcome indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Percentage of all businesses and organisations participating in joint actions in wastewater and solid waste management (to be disaggregated) |  | TBD | 10% | 10% |  |  | #N/A | 0 |
| CBC RNM – AL | Percentage (%) of population of the area targeted by the project made aware of sustainable use of natural resources and environment in key sectors |  | TBD | 3,50% | 3,50% |  |  | 8,91 | 8.91 |
| CBC RNM – AL | Impact indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Percentage of waste collected for recycling |  | TBD | 15% | 15% |  |  | #N/A | 0 |
| CBC RNM – AL | Savings (percentage of reduction of water losses) in the use of water by households and businesses |  | TBD | 10% | 10% |  |  | #N/A | n/a |
| CBC RNM – AL | Decrease in the number of illegal dumpsites |  | TBD | 10% | 10% |  |  | #N/A | n/a |
| CBC RNM – AL | Result: 3.1.2 Public infrastructure vulnerable to floods, soil erosion and wildfire is upgraded |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Output indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Number of projects implemented in relation to this specific objective |  | 0 | 12 | 12 |  |  | #N/A | 0 |
| CBC RNM – AL | Number of awareness raising campaigns to prevent or mitigate the consequences of natural catastrophes implemented |  | 0 | 5 | 5 |  |  | #N/A | 0 |
| CBC RNM – AL | Number of flood and wildfire protection facilities equipped |  | 0 | 2 | 2 |  |  | #N/A | 0 |
| CBC RNM – AL | Number of households/farms and other organisations benefitting from the upgraded infrastructure |  | 0 | 250 | 250 |  |  | #N/A | 12 |
| CBC RNM – AL | Outcome indicators |  |  |  |  |  |  |  |  |
| CBC RNM – AL | Length of roads protected from risks and man-made hazards (km) (target is 10% of roads exposed to risks that is TBD) |  | 0 | 10 | 10 |  |  | #N/A | 0 |
| CBC RNM – AL | Size of agricultural area protected (target is 5% of land exposed to risks that is TBD) |  | 0 | 5 | 5 |  |  | #N/A | 0 |
| CBC RNM – AL | Size of forestry area protected (target is 5% of forests exposed to risk that is TBD) |  | 0 | 5 | 5 |  |  | #N/A | 0 |
| CBC RNM – AL | Size of CBC area covered by activities (in %) |  | 0 | 3 | 3 |  |  | #N/A | 907.45 |

| Financing Agreement/Programme reference | Indicator for sector Competitiveness and Innovation | Source | Baseline 2014 | Target (2023) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CBC RNM – BG | Number of supported investments for improving the environmental conditions in the programme region |  |  | 22 | 22 |  | 22 |  | 0 |
| CBC RNM – BG | Number of nature protected areas addressed by supported interventions |  |  | 5 | 5 |  | 0 |  | 1 |
| CBC RNM – BG | Number of supported joint mechanisms for environmental protection, promotion of biodiversity and sustainable use of natural resources |  |  | 5 | 5 |  | 8 |  | 1 |
| CBC RNM – BG | Number of institutions/organizations involved in environmental related activities |  |  | 145 | 145 |  | 145 |  | 2 |
| CBC RNM – BG | Number of participants in environmental related trainings and campaigns |  |  | 1031 | 1031 |  | 1,031 |  | 60 |
| CBC RNM – BG | Supported investments for improving disaster management and risk prevention |  |  | 7 | 7 |  | 6 |  |  |
| CBC RNM – BG | Supported investments for adaptation and mitigation of climate change consequences |  |  | 7 | 7 |  | 1 |  |  |
| CBC RNM – BG | Supported joint mechanisms for disaster management and risk prevention and for promotion of climate change awareness |  |  | 3 | 3 |  | 1 |  |  |
| CBC RNM – BG | Number of institutions/organizations involved in initiatives related to risk prevention and management |  |  | 17 | 17 |  | 12 |  |  |
| CBC RNM – BG | Number of participants in trainings and campaigns in the field of risk prevention (including marginalized communities and other vulnerable groups) |  |  | 300 | 300 |  | 108 |  |  |
| CBC RNM – BG | Population benefiting from flood protection measures |  |  | 350,000 | 350,000 |  | 255,847 |  |  |
| CBC RNM – BG | Population benefiting from forest fire protection measures |  |  | 400,000 | 400,000 |  | 0 |  |  |
| CBC RNM – BG | Number of cultural and historical touristic sites reconstructed /restored / covered by conservation and protection actions |  |  | 16 | 16 |  | 5 | 1 |  |
| CBC RNM – BG | Length of new or reconstructed or upgraded access roads to natural, cultural and historic tourism sites, cycling routes and walking paths |  |  | 5.00 | 5.00 |  | 4.214 |  |  |
| CBC RNM – BG | Number of newly built or reconstructed or upgraded tourist related facilities and attractions |  |  | 16 | 16 |  | 12 | 3 |  |
| CBC RNM – BG | Number of created/reconstructed facilities for disabled people for access to or in the supported touristic sites |  |  | 5 | 5 |  | 3 | 1 |  |
| CBC RNM – BG | Number of joint touristic products, services, brands, thematic routes |  |  | 20 | 20 |  | 20 |  |  |
| CBC RNM – BG | Number of actions, tools and initiatives developed and/or implemented for promotion of sustainable tourism potential of the border area |  |  | 19 | 19 | 1 | 18 |  |  |
| CBC RNM – BG | Number of participants in joint training and qualification initiatives in the field of sustainable tourism |  |  | 256 | 256 |  | 256 |  |  |
| CBC RNM – BG | Number of cross-border networks established or strengthened in the field of sustainable tourism |  |  | 5 | 5 | 3 | 0 |  | 1 |
| CBC RNM – BG | Number of public awareness initiatives promoting sustainable use of natural, historical and cultural heritage and resources (Number) |  |  | 15 | 15 |  | 7 |  | 4 |
| CBC RNM – BG | Number of public awareness initiatives promoting alternative forms of tourism (Number) |  |  | 150 | 150 |  | 0 |  | 0 |
| CBC RNM – BG | Supported joint start-up and self-employment initiatives |  |  | 11 | 11 | 1 | 10 |  | 1 |
| CBC RNM – BG | Number of participants (split into men and women) in supported training and qualification initiatives |  |  | 1807 | 1807 | 365 | 682 |  | 218 |
| CBC RNM – BG | Number of enterprises receiving non-financial support |  |  | 151 | 151 | 3 | 148 |  | 3 |
| CBC RNM – BG | Supported initiatives for economic development and investment promotion |  |  | 70 | 20 | 1 | 18 |  | 5 |
| CBC RNM – BG | Number of cooperation networks |  |  | 18 | 18 | 2 | 16 |  | 0 |

| Financing Agreement/Programme reference | Indicator for sector Competitiveness and Innovation | Source | Baseline 2014 | Target (2023) | Final target (Year) | Value (2017) | Value (2018) | Value (2019) | Value (2020) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| IPA CBC KS-MK | 1.1.1 VET programmes introduced in the curricula based on CBC assessment for addressing market skills needs | Project reports, AIR | 0 | 5 |  |  |  |  | 0 |
| IPA CBC KS-MK | 1.1.2 Share of unemployed women, youth and RAE population included in the targeted group employed | National (labour market) statistics | 0 | 10% |  |  |  |  |  |
| IPA CBC KS-MK | 1.1.3 Share of the new SMEs established in the cross-border areas that are owned by young people and members of marginalized groups | National business registry records | 0 | 10% |  |  |  |  |  |
| IPA CBC KS-MK | 1.1.4 Share of the new SMEs established in the cross-border area are owned by women | National business registry records | 0 | 5% |  |  |  |  |  |
| IPA CBC KS-MK | 1.2.1 Share of participating business organizations introduced new e-business and e-marketing applications | Project reports, AIR | 0 | 20% |  |  |  |  | 33% |
| IPA CBC KS-MK | 1.2.2 Share of export to regional markets for the companies participating in the programme supported activities | Project reports, AIR |  | +5% |  |  |  |  | +1% |
| IPA CBC KS-MK | 1.2.3 Products produced in the CBC area under the CBC regional logo | Project reports, AIR | 0 | 5 |  |  |  |  | 472 |
| IPA CBC KS-MK | 2.1.1 New joint tourism offers, products and/or services introduced in the programme area | Project reports, AIR | 0 | 5 |  |  |  |  | 66 |
| IPA CBC KS-MK | 2.1.2 Target groups (disaggregated by gender and age) establishing new business initiatives in tourism and hospitality | Project reports, AIR | 0 | 10% |  |  |  |  | 46 new businesses established |
| IPA CBC KS-MK | 2.2.1 Tourists in the programme region | National statistic reports | KS=14808 (2011) MK=198407 (2012) | +5% |  |  |  |  | No data |
| IPA CBC KS-MK | 2.2.2 Students from the eligible areas participating in supported VET programmes related to tourism | Project reports, AIR | No data | 50 |  |  |  |  | 0 |
| IPA CBC KS-MK | 2.3.1 Visitors (disaggregated by gender and age) visiting supported natural and cultural heritage sites | Project reports, AIR | No data | +5% |  |  |  |  | 10833 |
| IPA CBC KS-MK | 2.3.2 Share of young people (disaggregated by gender) in the eligible areas participate in the cultural events | Project reports, AIR | 0 | 5% |  |  |  |  | 189 participants |
| IPA CBC KS-MK | 2.3.3 Supported new products commercialized by the handicraft sector | Project reports, AIR | 0 | 10 |  |  |  |  | 47 |
| IPA CBC KS-MK | 2.3.4 Young people and women participating in new creative industries | National labor market statistics | No data | +5% |  |  |  |  | 138 |
| IPA CBC KS-MK | 3.1.1 Areas/ sites at risk of soil contamination covered by joint harmonized plans/studies . | Annual environmental reports | 0 | 30% |  |  |  |  | 0 |
| IPA CBC KS-MK | 3.1.2 New initiatives that introduce good practices/ new international practices in solid waste and/or wastewater/sewage systems management | Project reports, AIR | 0 | 3 |  |  |  |  | 2 |
| IPA CBC KS-MK | 3.2.1 Dwellings/households served in the collection of solid waste in the cbc area because of programme intervention | Project reports, AIR | 0 | 500 |  |  |  |  | 484 |
| IPA CBC KS-MK | 3.2.2 New initiatives that introduce good practices/ new international practices in the area of solid waste and/or wastewater/sewage systems management | Project reports, AIR | 0 | 3 |  |  |  |  | 2 |

# Footnotes

https://mioa.gov.mk/sites/default/files/pbl_files/documents/rja/godishen_izveshtaj_2019.pdf

General objective Nr. 3, NTS 2018-2030; National strategy for environment and climate changes 2014-2020.

All four General objectives of the NTS 2018-2030; National strategy for environment and climate changes 2014-2020; Economic reform

program 2020-2022.

SSO 2019 report publication (Macedonian version only), http://www.stat.gov.mk/PrikaziPoslednaPublikacija_en.aspx?id=47

Issued during October 2020.

Projections for payment for Union Programs are not submitted by CFCD.

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

227 activities, 23 implemented 61 ongoing, 3 late, 22 continuously, 89 a later deadline, 29 activities depend on adoption of laws.

This part is not applicable because the action foreseen in the Country Action Programme for the Republic of Macedonia for the year 2014 has not started its implementation yet. It is planned that the activities planned in the action for ,,Further development  of the capacities for crime scene investigation” to start in the course of 2018. The actions planned in the IPA 2016 programme are still in its initial phase.

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/north_macedonia_report_2020.pdf

https://worldjusticeproject.org/rule-of-law-index/country/2020/North%20Macedonia/

3 https://worldjusticeproject.org/rule-of-law-index/country/2020/North%20Macedonia/Fundamental%20Rights/

http://info.worldbank.org/governance/wgi/Home/Reports

http://info.worldbank.org/governance/wgi/Home/Reports

https://www.transparency.org/en/cpi/2020/index/nzl

https://freedomhouse.org/country/north-macedonia/freedom-world/2020

https://rsf.org/en/ranking/2020

http://ombudsman.mk/en/ombudsman_work/annual_reports.aspx

These should be mostly outcome, as well as selected relevant output indicators.

It must be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report.

In 2018, the Commission for Protection of the Right to Free Access to Public Information monitored 929 information holders' websites, out of 1255 information holders. During the monitoring, the Commission rated each information holder's web content with 10% for all published data, 5% for partially published information data and 0% if no content is published, against a total of 10 items in accordance with the law (Articles 9 and 10). The expert has proposed a Random sampling list that contained 13 columns, out of which for 2018, the expert point out column 1 and column 7 to be considered by the Commission in the report for 2018.

The results for column 1 of the 72 monitored institutions is 30%, while for column 7 the 71 monitored institutions is 35%. Hence, in 2018, out of 929 websites, the total number of monitored institutions was 143 (columns 1 and 7), and the overall average of website monitoring for 2018 was 32.5%.
In 2019, the Commission reported that 312 educational information holders' websites (mostly primary schools and kindergartens) were not included in the monitoring because they do not have websites, while approximately more than 300 websites out of the 929 monitored pages in 2018, were referred, in the submitted Commissions’ report to the expert, as institutions that have non-existent or non-functioning websites. Therefore, it was suggested, by the Commission to the expert, not to include them in the 2019 monitoring process. Consequently, the Commission asked the projected final target of 100% for 2020 to be decreased accordingly.

Despite the indication, the expert in the submitted 2019 Random sampling monitoring list included many of the above mentioned institutions, whose inclusion will certainly affect the result of the transparent standard for 2019, consequently the results for 2019 might be even less than 2018.
We also note that the Commission has no legal obligation to oblige information holders to create a web site, nor does the Commission undertake any additional proposed activities at the suggestion of an expert, since as of April 2018 the Commission is not operational and does not meet the statutory requirements for operation and decision-making, since the statutory number of members of the Commission is missing, necessary for the adoption of valid decisions.
We also emphasize that the new Law on Free Access to Public Information will transform the Commission into an Agency.

.

There is no Commission to act upon complaints/ appeals to reach decisions since April 2018.

| PIT-Tax efficiency indicator 𝑌pit=(𝑇pit/𝐺𝐷𝑃)/𝑟𝑗 𝑌pit- tax efficiency indicator 𝑇pit=PIT revenue 𝑟𝑗- Tax rate first bracket | CIT-Tax efficiency indicator 𝑌cit=(𝑇cit/𝐺𝐷𝑃)/𝑟𝑗 𝑌cit- tax efficiency indicator 𝑇cit=CIT revenue 𝑟𝑗-Standard tax rate | VAT- C- efficiency indicator 𝑌vat=(𝑇vat/FC)/𝑟𝑗 FC-Final consumption 𝑌vat- C-efficiency indicator 𝑇vat-VAT revenue 𝑟𝑗-Standard tax rate |
| --- | --- | --- |

Calculation of percentage is on the base of the old indicator.

Calculation of percentage is on the base new passport indicator.

Calculation of percentage is on the base of the old indicator.

Calculation of percentage is on the base new passport indicator.

https://ec.europa.eu/commfrontoffice/publicopinion/index.cfm/Survey/getSurveyDetail/instruments/STANDARD/surveyKy/2255 , Annexes, T-47.

https://appsso.EURtat.ec.europa.eu/nui/submitViewTableAction.do

Due to the COVID – 19 pandemics, i.e. no face-to-face meetings the budget for fiscal year 2020 (01.04.2020 – 31.03.2021) will not be used at all, or it will be used in a small percentage. Financial resources will be given back to the European Union.

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative.

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative.

These should be mostly outcome, as well as selected relevant output indicators

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative.

General objective Nr. 3, NTS 2018-2030; National strategy for environment and climate changes 2014-2020.

All four General objectives of the NTS 2018-2030; National strategy for environment and climate changes 2014-2020; Economic reform

program 2020-2022.

SSO 2019 report publication (Macedonian version only), http://www.stat.gov.mk/PrikaziPoslednaPublikacija_en.aspx?id=47

General level note remains on strengthening the administrative capacities of the negotiating structure of the administration for the needs of the entire negotiation process. Therefore, the Unit for negotiation and integration in the MoTC as responsible unit for both Chapters for the implementation of the EU acquis, should increase its capacity. This remark among other things also applies to the administrative, operational and technical capacity of the unit to manage Trans-European networks as one of the drivers of EU integration.

From the analyzes of the number of accidents with casualties, 2018 recorded a decrease of 17.52%, as well as a decrease in the number of persons killed by 16.77%, ie in road accidents in 2018, the life was lost by 129 people, which is 26 persons less comparable to 2017.

2. It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

3. Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

https://www.stat.gov.mk/pdf/2020/3.1.20.16_mk.pdf (T-02)

preliminary data: https://www.stat.gov.mk/pdf/2020/3.1.20.16_mk.pdf (T-02)

https://www.stat.gov.mk/publikacii/2020/Regionite-Regions-2020.pdf (page 48) and http://makstat.stat.gov.mk/PXWeb/pxweb/en/MakStat/MakStat__BDP__BDPInvesGodisni__BDPsporedESS2010/675_NacSmA_Reg_BDPreg_ml.px/table/tableViewLayout2/?rxid=46ee0f64-2992-4b45-a2d9-cb4e5f7ec5ef

https://www.stat.gov.mk/publikacii/2020/Regionite-Regions-2020.pdf (page 49) and http://makstat.stat.gov.mk/PXWeb/pxweb/en/MakStat/MakStat__BDP__BDPInvesGodisni__BDPsporedESS2010/675_NacSmA_Reg_BDPreg_ml.px/table/tableViewLayout2/?rxid=46ee0f64-2992-4b45-a2d9-cb4e5f7ec5ef

https://www.stat.gov.mk/pdf/2020/9.1.20.08_mk.pdf (T-01)

PAF based on Food and Veterinary Agency

These should be mostly outcome, as well as selected relevant output indicators

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

Number of columns to be adjusted for all years from 2014 up to the year of the reporting period. Values should be cumulative.

https://ec.europa.eu/EURtat/databrowser/view/tec00114/default/table?lang=en and Makstat, GDP, by year, by regions, ESA 2010: http://makstat.stat.gov.mk/PXWeb/pxweb/en/MakStat/MakStat__BDP__BDPInvesGodisni__BDPsporedESS2010/675_NacSmA_Reg_BDPreg_ml.px/table/tableViewLayout2/?rxid=46ee0f64-2992-4b45-a2d9-cb4e5f7ec5ef

Example for calculation: The GDP/capita, PPS value of North Macedonia is 38% of the EU average according to EURtat in 2018. The GDP/capita of Polog region is 46.7 % of the Macedonian average in 2018, according to Makstat. Thus, the GDP per capita in PPS as % of EU average in Polog region is 0.38*46,7 = 17.75 % in 2018.

Sourse: same as the previous

Source: same as the previous

http://makstat.stat.gov.mk/PXWeb/pxweb/en/MakStat/MakStat__DelovniSubj__DemografijaNaPretprijatija/275_DelSub_Mk_04AN_en.px/?rxid=2d7f8742-3410-4731-ae76-1c3793fbb500%20%20%20%20%20%20(Select:%20Column%201:%20B-N_X_K642%20Business%20economy,%20except%20group%2064.2%20-%20Activities%20of%20holding%20companies;%20Column%202:%20relevant%20years;%20Column%203:%204-year%20survival%20rate%20(%25))

https://ec.europa.eu/neighbourhood-enlargement/sites/near/files/north_macedonia_report_2020.pdf

SDC Country Cooperation Strategy 2017-2020: https://www.eda.admin.ch/dam/countries/countries-content/macedonia/en/Cooperation-Strategy-Macedonia-2017-2020_en.pdf

More information: https://www.usaid.gov/macedonia/social-cohesion

More information for the project: http://mtsp.gov.mk/siap-proekt-za-administriranje-na-socijalnoto-osiguruvanje.nspx and https://projects.worldbank.org/en/projects-operations/project-detail/P170343

More information for the project: http://projects.worldbank.org/P103974/conditional-cash-transfers-project?lang=en&tab=overview

These should be mostly outcome, as well as selected relevant output indicators

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

MoES data on the number of students in primary and secondary education who dropped-out of school for some reason, as a share of the total number of enrolled students in the specific school year.

Day-care centers for persons with disabilities could cater for 815 users, but the average number of daily users was 611.

The figure refers to the homecare provided to elderly citizens who because of physical or mental frailty or disability depend on help with daily living activities.

Day-care centers for persons with disabilities could cater for 825 users (1% increase of the capacity since 2016), but the average number of daily users was 500.

The figure refers to the personal assistance service, which was introduced for the first time aa publicly funded program in 2018.

Day-care centers for persons with disabilities could cater for 881  users (8% increase of the capacity since 2016), but the average number of daily users was 678.

The figure refers to the personal assistance service.

The decrease in the average number of daily users in 2020 is linked to the temporary closure of the day-care centers and the protocols for their operations during pandemic.

Day-care centers for persons with disabilities could cater for 1011  users (24% increase of the capacity since 2016), but the average number of daily users was 483. The decrease in the average number of daily users in 2020 is linked to the temporary closure of the day-care centers and the protocols for their operations during pandemic.

The figure refers to the personal assistance service.

Source ESRP Annual Report for 2017

The Labour Market Units in the MLSP produced one analysis by using the existing HERMAK model for long-term-forecasting

The Labour Market Units in the MLSP produced one analysis by using the existing HERMAK model for long-term-forecasting Occupational Outlook as well

The Labour Market Units in the MLSP produced one analysis by using the existing HERMAK model for long-term-forecasting Occupational Outlook as well. Two analyses papers were produced upon request of the National Economic and Social Council

In 2020, 48 persons from the MLSP, MoES, ESA, State Statistical Office attended the first training on policy making

All 7 recommendations provided by NESC were integrated in the documents adopted by the Government

All 19 recommendations provided by NESC were integrated in the documents adopted by the Government

All 10 recommendations provided by NESC were integrated in the documents adopted by the Government

Thus far, in 2020 two recommendations were provided by NESC

Four local employment pacts were concluded for Bitola, Kumanovo, Skopje and Veles. These four Local Employment Pacts with the most feasible and relevant concept notes were selected to develop full projects. One of the projects will be financed by IPA Project “Strengthening social dialogue”. Moreover, the ILO continues to search for investors, mobilize development partners to support the remaining 3 local employment pacts, based on the diagnostic of the territorial potentials and needs.

There were 96 institutions for childcare and education which enrolled 34.386 children aged 0-6 years

According to the data provided by the Child Protection Department in the MLSP, the total additional spaces created in pre-schools in 2019 is as follows: 1599 spaces distributed in 80 groups (created within existing or new public kindergartens) and 243 spaces in 6 early child development centres (established as part of the public kindergartens).

By 31.12.2020, according to the data provided by the Child Protection Department in the MLSP, the total additional spaces created in pre-schools in 2020 is 482 spaces distributed in 24 groups (created within existing or new public kindergartens). Their creation was funded from other public sources than IPA.

Due to the COVID 19 pandemic the number of revised/modernised and verified educational programmes for adults is decreased

It has to be consistent with the way of programming (annual, multi-annual with or without split commitments) and with the NAO report

The pilot exercise of the YG included only one municipality, which is a part of the target regions, and therefore is not representative for the region. (Gostivar is a part of Polog region)

ESA contracted a company (contract no. 05-3027/2 dated 16.10.2020), which launched the works in the employment center in Kumanovo on 07.12.2020, after obtaining permits from the Municipality of Kumanovo .

The modernization of the other two centres was not procured due to budget cuts made by the Ministry of Finance related to the COVID19 pandemic.

Source EU-SILC: https://ec.europa.eu/EURtat/databrowser/view/tespm010/default/table?lang=en

Source EU-SILC: https://ec.europa.eu/EURtat/databrowser/view/ilc_li09/default/table?lang=en